## Ongoing projects
Construction Projects under process as on 31.01.2020
S. No. | Commissionerate/ Zone / File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Present Status
1 | CGST Dibrugarh/Guwahati/ 916/4/Const./ Shillong/HRD/15 | Construction of office cum residential qtrs. at Dibrugarh. Total office space: 3562 sqm. Total quarters: 56 (Type-II 14, Type-III 28 & Type-IV 14) | CBIC/ CPWD | 60.37 | The proposal was submitted to the Ministry on 21.05.2018. IFU had made some observations regarding budget head, cost index, carpet area and the same were conveyed to Comm'te on 12.09.19. Incomplete reply received Comm'te vide letter dated 14.01.2020 again requested to submit a proper reply.
2 | CGST Kolhapur/Pune/ 916/21/Const. /Pune/HRD/14 | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur-reg. Land area: 12854.8 sqm. Office space : 9244.1 sqm. | CBIC/ CPWD | 43.79 | Proposal was received on 25.01.2019 and file was submitted to the Ministry. While processing the proposal IFU had made observations reg. higher per sq. ft. cost, phasing etc. based on the justification submitted by the Comm'te proposal submitted to Min. on 11.11.19. IFU vide note dt. 31.12.2019 has made some observations which have been conveyed to the Comm'te on 14.01.2020. Reply awaited.
3 | CGST Hyderabad/ Secunderabad/ 916/13/Const./ Hyderabad/HRD/15 | Completion of 287 unfinished Dept. qtrs taken over from M/s Sri Durga Estate Pvt. Ltd. at Hyderabad | CBIC/ NBCC | 49.75 | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Ministry had returned the file with certain observations reg. project status which was conveyed to comm'te on 21.05.19. Reply still awaited. Last Reminder sent on 15.01.2020.
4 | CGST Raipur/ Bhopal/ 916/4/Const./Raipur/HRD/17 | Construction of office building and residential quarters at Rajnandgaon. | CBIC/ CPWD | 2.8 | Proposal received on 12.09.2017 and submitted to Min. for a/a & e/s on 17.07.2019. IFU returned the file with certain queries which were conveyed to Comm'te on 18.09.19. Pr. Commr., Raipur had visited in DGHRD on 16.12.2019 to discuss the project status. Reply awaited. Reminder sent on 13.01.2020.
5 | CGST Udaipur/Jaipur 916/1/Const./HRD/2018 | Proposal for repair/renovation and upgradation of staff houses at Udaipur. | CBIC / CPWD | 25.56 | Fresh proposal was received on 08.04.2019 and submitted to Min. on 05.07.19. File returned by the IFU with certain queries reg. justification of proposal etc. the same were conveyed to the Comm'te on 24.12.2019.
6 | Cus. (P.), Vijaywada/Visakhapatnam 916/15/Const./Visakhapatnam/HRD/16 | Const. of buildings for newly formed Customs Comm'te (P.), Vijaywada-HQRS. Office Complex and Residential Quarters at Sy. No. 29/8 (3.84 acres) of Kesarpally Village of Gannavaram Mandal of Krishna Dist. Andhra Pradesh | CBIC / NBCC | 65.49 | Revised proposal received on 01.03.2019, proposing to award this work to NBCC certain clarifications were sought by DGHRD whcih were conveyed to Comm'te after receiving the reply from the Comm'te on 22.05.2019, the proposal was submitted to Min. for a/a & e/s. But Member (Admn.) returned the file and asked to Comm'te to get in writing a letter from CPWD showing their inability before awarding this work to NBCC. Reply awaited. Reminder sent on 26.12.2019.
7 | CGST Agra/Lucknow /916/5/Const./Aligarh/HRD/19 | Const. of new office building for CGST Division at Aligarh. | CBIC/CPWD | 11.34 | File has been submitted to the Min. on 22.05.2019. File returned from the Ministry with certain observations reg. space requirement, cost of const. etc.and the same were conveyed to the Comm'te on 27.06.2019. Reply received and file is submitted to Min. on 05.09.19 for a/a & e/s. File returned wiht observations, same were communicated to the comm'te on 07.11.19. Reply awaited. Last reminder sent on 16.01.2020.
8 | Chennai Customs/Chennai 916/12/Const/Jaffer Syarang-Chennai/HRD/19 | Construction of office accomodation building for Partner Govt. Agencies, Chennai Customs Audit and Import Comm'te at Jaffer Syarang Street, Chennai. | CBIC/CPWD | 86.75 | Proposal was received in July, 2019. IFU has raised observations reg. existing carpet area, shortage of space etc. and the same were conveyed to the comm'te on 30.10.19 followed by reminders 04.12.2019, 06.01.2020. Reply from the Comm'te is awaited. Last reminder sent on 06.01.2020.
9 | CGST Jaipur/Jaipur 916/2/Const. Jaipur/HRD/19 | Dismantling and reconstruction of T-VI/3 Bunglow at C.Ex. Officers residence colony, JLN Marg, Jaipur | CBIC/CPWD | 2.07 | Proposal for const. of RCC wall sanctioned on 09.01.2020 (partly sanctioned). Further IFU had made observations reg. justification for re-construction of residential quarters conveyed to the Comm'te on 13.12.2019. Reply awaited. Last reminder issued on 17.01.2020.
10
10 | CGST Bhavnagar / Ahmedabad / 916/21-A/Const./Bhavnagar/HRD /11 | Construction of office building at Bhavnagar Total land- 7104 sqm. Office space-4807.50 sqm. | CPWD/ CPWD | 50.28 | Project sanctioned on 30.08.2017. But due to change in PAR 2019. A revised proposal has been forwarded by the Comm'te, which has been submitted to the Min. for a/a & e/s of the increase amount on 31.12.2019. Presently file is pending with US (IFU).
11 | Bhubaneswar/ Bhubaneswar / 916/12/Const. /Bhubaneswar/ HRD/14 | Const. of Retaining wall and Approach Road and from the main road to the office plot at Bagbrindaban Mauja of Balasore Town in state of Odisha. | CBIC/ CPWD | 1.57 | CPWD has submitted a revised P.E for Rs 1.57 Cr. while examining the proposal DG, HRD has raised some queries, based on the reply/clarifications submitted by Comm'te proposal forwarded to the MInistry for a/a & e/s on 26.12.2019. Presently file is pending with US (IFU).
12 | Goa Cus./ Pune/ 916/10/Const./Goa/HRD/17 | Construction of addl. staff quarters for Customs Department at Customs Colony, Headland Sada, Marmagoa, Goa. | CBIC/CPWD | 37.28 | Proposal for demolition of dilapidated RCC overhead tank sanctioned on 16.01.2020. Further IFU vide note dated 06.12.2019 raised certain queries reg. demand survey, justification of joggers park etc. and the same were communicated to the Comm'te on 12.12.2019. Reply awaited. Reminder issued on 22.01.2020.
13 | CGST Guntur/Visakhapatnam/ 916/11/Const./Guntur/HRD/18 | Construction of office building at Eluru (A.P.) | CBIC / CPWD | 6.95 | File was submitted to the Ministry and IFU made observations regarding provision of funds, permissible FAR etc. which were conveyed to the Comm'te. File was re-submitted with replies. However, IFU made observations regarding plinth area, feasibility of construction for given sanctioned strength, etc., based on the reply received from Comm'te on 03.01.2020, file re-submitted to Min. on 14.01.2020. Presently file is pending with US (IFU).
14 | Chennai Cus. (Gen.)/Chennai / 916/08/Const./Chennai/HRD/2018 | Construction of 36 residential quarters at Nungambakkam, Chennai | CBIC / CPWD | 65.42 | Project sanctioned. Due to revision in PAR norms the cost has been increased accordingly, revised PE with a new cost of Rs. 65.00 Cr. was received in Nov, 2019. There is escalation of original cost by Rs. 16.39 Cr. On account of superior sanitary fitting, false sealing, mechaniced car parking. Rs. 10.00 Cr. cost has increased on account of mechaniced car parking only. Proposal submitted to MIn. on 17.01.2020. Presently file is pending with US (IFU).
15 | CGST Tirupati/Visakhapatnam 916/06/Const./Tirupati/HRD/2015 | Construction of office building and staff quarters at Tirupati | CBIC / CPWD | 57.06 | Revenue Secretary on 22.06.2017 made observations regarding PPP Model, Cost benefit analysis etc. Comm'te withdrew the proposal. Revised proposal has been received and after submission to Min. file returned by the IFU with ceratin queries which were conveyed to Comm'te on 18.09.19. Further, based on the reply received from the Comm'te file re-submitted to the Min. on 22.11.19. Presently file is pending with AS & FA (Fin.).
16 | CGST Nagpur-I/Nagpur 916/18/Const./Nagpur/HRD18 | Const. of 6 nos. of T-VI qtrs.for Central Excise at B.No. 12, Seminary Hills, Nagpur Internal Water Supply, Sanitary Installation, Drainage and Internal Electrical Works involving an expenditure of Rs. 734.63 lakhs. | CBIC / CPWD | 7.35 | Proposal received and submitted to the Min. on 15.07.19 for approval. IFU returned the file with certain queries reg. justification of T-VI qtrs. and GH etc. and the same were conveyed to the Comm'te on 05.12.2019. Reply received and file is submitted to the Min. on 26.12.2019. Presently file is pending with US (IFU).
17 | CGST Udaipur/Jaipur/ 916/4/Const./Udaipur/HRD/19 | Construction of new office buildiing for Udaipur CGST Comm'te | CBIC/CPWD | 42.07 | File has been submitted to the Min. on 22.05.2019. File returned from the Ministry with certain observations reg. Space requirement, cost of const.hiring etc.and the same were conveyed to the Comm'te on 27.06.2019. Reply received and after scrutiny DGHRD's quereis were communicated. IFU query conveyed to comm'te on 04.11.19. Based on the reply received from the Comm'te file re-submitted to the Min. on 26.12.2019. Presently file is pending with US (IFU).
18 | Cus. Jamnagar (dwarka) Ahmedabad 916/17/Const./Ahmedabad/HRD/18 | Construction of office building at the site of shore guard, Dwarka, Jamnagar. | CBIC/CPWD | 1.24 | Fresh proposal received and file is submitted to Min. on 04.10.19. File returned from Min. with certain observations and the same were conveyed to comm'te on 22.11.19. Based on the reply received from the Comm'te, file submitted to the Min. 23.12.2019. Presently file is pending with US (IFU).
19 | CGST Goa/Pune 916/1/Const./Goa/HRD/2019 | Redevelopment of 52 nos. of staff quarters and community centre for CGST Goa Commissionerate, Goa at Alto-porvorim | CBIC/CPWD | 27.16 | Fresh proposal received and raised the queries by DGHRD letter sent on 24.09.19. File is submitted to the Min. on 08.01.2020. Presently file is pending with US (IFU).
20 | Customs (Airport) Bengaluru/Bengaluru 916/16/Const./Bengaluru/HRD/ 2019 | Construction of new customs House Building at bengaluru International Airport | CBIC/CPWD | 57.37 | Fresh proposal was received in October, 2019 and queries reg. calculation of office space, per sq.ft. Cost, cost benefit analysis etc. conveyed to the Comm'te on 14.10.19, followed by reminder on 16.12.2019. Reply received on 03.01.2020. Reply received and file is submitted to MIn. on 20.01.2020. Proposal for Geo Techinical and soil testing of the land purchase for construction of DRI Zonal Unit. Proposal submitted to Ministry for a/a & e/s on 17.01.2020. Presently file is pending with US (IFU).
21 | Jamnagar Cus./Ahmedabad 916/17/Const./Jamnagar (Res.)/HRD/19 | Construction of Staff quarters at Jamnagar | CBIC/CPWD | 18.86 | Proposal received on 09.09.19. Savings of HRA of the staff/officers has not informed accordingly query letter issued on 09.10.19. Reply recvd on 29.10.19, DGHRD sought some further clarification which were replied by the Comm'te on 06.12.19 & 06.01.2020. File submitted to the MIn. on 20.01.2020. Presently file is pending with US (IFU).
22 | CGST Manipur/ Guwahati 916/3/Const./Shillong/HRD/19 | Const. of office building and boundary wall at Lamphel at Imphal Shillong | CBIC/CPWD | 46.4 | Proposal was received on 16.09.2019. In the meantime, a reference was received from Sh. Bhabananda Singh, M.P. (Rajya Sabha) for allotting this work to MANIDCO. Matter was got clarified from the Comm'te and based on the report proposal was process for awarding the work to State PWD accordingly, the proposal was forwarded to Min. for a/a & e/s on 07.01.2020. Presently file is pending with US (IFU).
23 | 916/21/Const./DRI/Hyderabad/ HRD/19 | Construction of office building for DRI Hyderabad Zonal Unit at Jubilee Hills at Hyderabad (Geo Technical Investigation) | CBIC/CPWD | 0.08 | Proposal for Geo Techinical and soil testing of the land purchase for construction of DRI Zonal Unit. Proposal submitted to Ministry for a/a & e/s on 17.01.2020. Presently file is pending with US (IFU)