## Major Sanction & ongoing
Construction Proposal Sanctioned/Revalidated (Ongoing) as on 31.01.2020
S. No. | Commissionerate/ Zone / File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Present Status | Funds status
1 | NACIN Hyderabad / NACIN / 916/02/Const./ Hyderabad/ HRD/13 | Construction of RTI, NACIN, at Attapur, Hyderabad Total built up area- 11940 sqm. | CBIC/ NBCC | 46.71 | Project sanctioned on 30.12.2016. The project is being executed by NBCC. The construction work is in full swing. File is submitted to Min. for revalidation on 17.01.2020. Presently file is pending with US (IFU). | Rs. 7.00 Cr. were released in 2017-18 out of which 4.67 were utilized. Rs. 25.07 Cr. were released in 2018-19 out of which Rs. 15.07 cr. were utilized. Rs. 7.00 Cr. were released on 04.06.2019. Addl. Rs. 12.00 cr. allocated in RBE 2019-20
2 | Pr. Comm. Cus.(Gen.) / Mumbai Zone-I / 911/3/Custom Enclave/Mumbai/ HRD/16 | Construction of Office complex and residential quarters at Customs Enclave Plot, Wadala, Mumbai through CPWD at a cost of Rs. 495.5 Cr. for office complex and Rs. 480 cr. For residential complex Office space 30000 sqm. Total qtrs. -769 | CBIC/CPWD | 975.72 | Proposal Sanctioned on 11.11.2019. Letter for MPR issued on 10.12.2019. | Rs. 5.00 Cr. (Rs. 2.50 Cr. for office & Rs. 2.50 Cr. for residence) released on 11.11.2019.
3 | Cus. (Prev.), Jamnagar/ Ahmedabad / 916/8/Const./ Jamnagar/HRD/16 | Construction of office building at Jamnagar Total land- 10,250 sqm. Office space- 4131.34 sqm. | CBIC/ CPWD | 43.67 | Project sanctioned on 13.12.2017. File is submitted to Min. for revalidation on 14.01.2020. Presently file is pending with US (IFU). | Rs. 15.00 Cr. were released in 2018-19 out of which 4.00 were utilized. Rs. 7.00 Cr. were released in 2019-20 out of which 6.78 Cr. has been utilized till Nov, 2019. Addl. Rs. 7.00 cr. allocated in RBE 2019-20
4 | CGST Jalandhar/ Chandigarh/ 916/09/Const./ Jalandhar/ HRD/16 | Construction of office cum residential qtrs.and boundary wall at Jalandhar Total land - 06 acre Total qtrs.- 116 Type wise qtrs.- Type-II=19 Type-III=62 Type-IV =32 Type-V A=01 Type-V B=01 Type-VI=01 | CPWD/ CPWD | 67.57 | Project was sanctioned on 4.8.2017 and being executed through MoUD funds. During the visit to Chandigarh on 06.12.2019 JD (I&W) had reviewed the project status and found to be satisfactory.
5 | CGST, Delhi (North)/ Delhi/ 916/03/Const./ Dwarka/HRD/17 | Construction of residential qtrs. at Dwarka Total land- 17832 sqm. Total qtrs.-256 Type wise qtrs.- Type-IV=168 Type-V=52 Type-VI=36 | CBIC/ NPCC | 227 | Project sanctioned on 25.07.2018. File is submitted to Min. for revalidation on 16.01.2020. Presently file is pending with US (IFU). | Rs. 3.00 Cr. released on 27.07.2018 and Rs. 30.00 Cr. released on 26.02.2019 in F.Y. 2018-19. Further Rs. 26.50 Cr. released on 16.08.2019. Further, Rs. 12.00 Cr. have been allocated in RBE 2019-20
6 | Chennai Cus. (Gen.) VIII / Chennai / 916/03/Const./Chennai/RD/16 | Construction of residential qtrs. at Anna Nagar, Chennai. Total land- 1,06,086 sqm. Total qtrs.-726 Type wise qtrs.- Type-II=288 Type-III=288 Type-IV=150 | CBIC/ CPWD | 348.77 | Project sanctioned on 13.10.2017. Letter issued to EMC for release of addl. fund of Rs. 15.00 Cr sought under RBE 2019-20. | Rs. 30.00 cr. released in 2018-19 out of which Rs. 12.00 cr. utilized. Rs. 20.00 Cr. were released on 24.07.2019. LoA has been issued on 30.08.2019. Rs. 18.00 cr.is the expenditure as per PFMS till date. Addl. Rs. 15.00 cr. has been allocated in RBE 2019-20 as the construction work is in full swing.
7 | CGST, Raigad /Mumbai./ 911/4/Misc./Kharghar/HRD/15 | Construction of residential qtrs. at Kharghar by NBCC. Total land- 20,000.32 sqm. Total qtrs.-187 Type wise qtrs.- Type-II=42 Type-III=70 Type-IV=44 Type-IV (Spl)=20 Type-V=09 Type-VI=02 | CBIC/ NBCC | 110.11 | File sanctioned on 18.04.2019 | Rs 5.00 cr. were released on 23.04.2019 and further Rs. 6.011 Cr. released on 07.06.2019. Further, Rs. 10.00 Cr. released on 17.01.2020.
8 | CGST, Belgavi/ Bengaluru / 916/15/Const. /Belgaum/ HRD/12 | Construction of office cum residential qtrs. at Bagalkot Total land-01 acre Office space-1080 sqm. Residential space-465 sqm. Total qtrs.-02 Type wise qtrs.- Type-III=01 Type-IV=01 | CBIC/ CPWD | 2.19 | Project sanctioned on 10.01.2018. | Rs. 5.00 lakh released on 16.01.18 & Rs. 15.00 lakhs on 12.02.2018 but could not utilized. Rs. 20.00 lakh again released on 20.08.2018, Rs. 199.03 lakhs relaesed on 01.11.2018.
9 | Hyderabad Cus./Hyderabad CGST/ 916/14/Const./Hyderabad/HRD/16 | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | CBIC/ CPWD. | 1.3 | Proposal sanctioned on 07.03.19. | Rs. 10.00 lakhs were released in 2018-19 but could not be utilized Further, Rs. 50.00 lakhs has been released on 29.07.2019.
10 | CGST Tirupati/Visakhapatnam/ 916/55/Const./ Anantpur/HRD/ 06 | Construction of office building at Anantapur, Andhra Pradesh. Office space: 1292.70 sqm. | CBIC/ CPWD | 7.07 | Proposal sanctioned on 21.12.2018 | Rs. 1.00 Cr. were released in 2018-19 but could not be utilized Further, Rs. 4.06 has been released on 29.05.2019.
11 | Customs (General) JNCH/Mumbai-II Customs / 916/17/Const./ Raigad/HRD/16 | Construction of additional office building (G+7) at JNCH NHAVA SHEVA Dist. Raigad-Mumbai Available area - 14900 sqm. Office space - 8551.80 sqm. | CBIC/ CPWD | 90.26 | Proposal for enabling works (Rs 51 Lakh) was sanctioned in March, 2018. Proposal for office sanctioned on 14.02.2019. | Rs. 43 lakh for enabling works was released on 19.07.2019. Further due to pending approvals from local authorites Comm'te vide letter dated 10.10.19 has requested not to released in balance amount.
12 | Mangalore Custom/ Bengaluru / 202/7/2003 Ad. VIII (EC) | Providing Barbed wire fencing and Name Boards to properties belonging to Customs Department at Karwar, for Rs. 89,56,000. | CBIC/ CPWD | 0.89 | Project sanctioned on 15.09.2017. | Rs. 83,44,052/- were released in 2017-18, out of which RS. 6,11,948/- utilized in 2017-18 & Rs. 14,21,578/- utilized in 2018-19. Further, Rs. 75,34,422/- released on 12.07.2019 during 2019-20. LoA has not been issued till date as per PFMS.
13 | Udaipur/Jaipur / 916/11/Const./ Jaipur-II/HRD/11 | Construction of office building CGST division Bhilwara. Land area: 1858.06 sqm. Office space : 750.00sqm. | CBIC/ CPWD | 9.72 | Proposal sanctioned on 21.02.2019. | Rs 1.5 cr have been released on 26.02.2019 but could not utilized. During 2019-20 Rs. 50.00 lakhs has been released on 25.07.2019.
14 | CGST, Agartala/ Guwahati / 916/10/Const./ Shillong/HRD/15 | Construction of office building (Audit Circle, Custom division & CGST Division) at Agartala Total land- 3022 sqm. Office space-2793 sqm. Guest House-463 sqm. | CBIC/ CPWD | 28.04 | Proposal sanctioned on 18.02.2019. File is submitted to Min. for revalidation on 14.01.2020. Presently file is pending with US (IFU). | Rs 50 Lakh released on 26.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 1.00 Cr. released on 28.05.2019. Rs. 3.00 cr. has been allocated in RBE 2019-20.
15 | DRI Kolkata/ DRI 916/02/Const. /Kolkata/ HRD/2016 | Construction of DRI at Plot No. CBD-93, Action Area-II, New Town, Kolkata | CBIC/CPWD | 64.5 | Proposal sanctioned on 08.02.2019. | Rs 10 Lakh released on 18.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 2.00 Cr. released on 14.08.2019.
16 | CGST Pune-II/ Pune / 916/5/Const./ Pune/ HRD/2014 | Construction of office building and 02 nos. residential quarters for CGST Ranges office at Pandharpur, Distt. Solapur, Maharashtra. Total land : 2230.22 sqm. Office space :146.50 sqm. One quarter Type IV | CBIC/ CPWD | 2.02 | File sanctioned on 23.12.2019 | Rs. 20.00 lakh released on 30.12.2019.
17 | CGST Palghar/ Mumbai/ 916/5/Const./ Mumbai/HRD/ 16 | Construction of 3 Div. offices and 14 ranges offices on plot bearing NosP-34 at MIDC, Boisar-reg. | CBIC/ CPWD | 33.25 | Proposal sanctioned on 01.07.19. | Rs. 1.00 Cr. released on 19.07.19. LoA issued on 15.10.2019.
18 | Tuticorin/ Trichy Customs/ 916/19/ Const./ Tuticorin/HRD/14 | Construction of additional residential quarters (T-II, T-III & T-IV) at Port Area, Tuticorin. Total qtrs.- 06 Type wise qtrs.- Type-II=1 Type-III=2 Type-IV =3 | CBIC/ CPWD | 1.62 | Project sanctioned on 25.08.2017. | Rs. 1.47 Cr. were revalidated for F.Y. 2019-20 and released on 07.07.2019. LoA has been issued on 11.09.2019. No expenditure is being shown as per PFMS till date.
19 | Patna Cus. (Prev.)/ Patna Cus./ 916/16/Const./Patna (P)/HRD/2016 | Proposal for construction of Residential complex at Land Customs Station jogbani, a/ a & e/s of Rs.7,99,52,000/- Total qtrs.- 21 Type wise qtrs.- Type-II=7 Type-III=12 Type-IV =02 | CBIC/ CPWD | 7.99 | Project sanctioned on 11.06.2018. | Rs. 4.00 cr. have been released to the Comm'te. Comm'te surrendered Rs 3.5 crore. In F.Y. 2019-20 Rs. 3.99 cr. released on 12.07.19. MPR is awaited.
20 | Patna Cus. (Prev.)/Patna Cus./ 916/15/Const./Patna/HRD/14 | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul Total land- 2.74 acre Residential space-5,730 sqm. Total qtrs.-21 Type wise qtrs.- Type-III=06 Type-IV=14 Type-IV (Spl)=01 | CBIC/ CPWD | 11.85 | Project sanctioned on 22.09.2017. | Rs.9.5 cr. have been released to the Comm'te in this F.Y. 2018-19. Rs. 1.34 Cr. utilized in 2018-19. Comm'te had surrendered Rs 7.17 crore. In the current F.Y. 2019-20 Rs. 3.00 Cr. released on 14.08.2019.
21 | CGST Tirupati/ Visakhapatnam/ 916/4/Const./ Kurnool (A.P.)/HRD/2012 | Construction of 7 Nos. Type-IV Quarters and Guest House for Kurnool (Tirupati Comm’te), Andhra Pradesh-reg. Total Land :606.88 sqm. | CBIC/ CPWD | 3.96 | Proposal sanctioned on 10.09.2018. | Funds to the tune of Rs. 1.18 cr. released on 20.09.2018, out of which Rs. 44,18,857/- were used during F.Y. 2018-19. During F.Y. 2019-20, Rs. 73,82,000/- released on 20.08.19. Comm'te has surrendered Rs 98 Lakh. Further, IFU raised query regarding addl. amount sanction and same were conveyed to comm'te on 11.11.19. Addl. Rs. 50.00 lakhs released on 06.12.2019. | Mid Feb status funds utilization to be sought
22 | CGST Ahmedabad (North)/ Ahmedabad/ 916/8/Const./ Ahmedabad/HRD/17 | Construction of new building in the Custom House Compound, Ahmedabad. | CBIC/ CPWD | 31.87 | Project sanctioned on 11.06.2018. | Rs. 5.00 cr. was released in F.Y. 2018-19, Comm'te has surrendered Rs. 4.75 cr. During F.Y. 2019-20 Rs. 2.00 cr. released on 20.08.2019.
23 | CGST Ghaziabad & CGST (Audit), Noida/ Meerut/ 916/5/Const./ Meerut/HRD/17 | Construction of office building including boundary wall and culvert over Nala at allotted land measuring 2.21 acres (8894 sqm.) to CGST Ghaziabad, Audit-II, Ghaziabad, Noida | CBIC/ CPWD | 116.42 | Project sanctioned on 03.10.19. | Rs. 1.00 cr. released on 14.10.2019 in F.Y. 2019-20.
24 | Delhi (South)/CGST Delhi/ 916/62/Const./Nangal Raya/HW/06 | Construction of office building at Nangal Raya, New Delhi. | CBIC/NBCC | 32.83 | Proposal sanctioned on 13.06.2016. Complete amount has been released to the Comm'te. Comm'te has informed that civil work has almost completed
25 | CGST Agra/Lucknow 916/05/Const./Agra/HRD/2018 | Construction of conference hall in the building of CGST Comm'te Agra. | CBIC/CPWD | 0.12 | Project sanctioned on 13.08.19 | In F.Y. 2019-20 Rs. 11,97,143/- have been released on 28.08.2019.
26 | CGST Thane/Mumbai 916/15/Const./Thane/HRD/2018 | Proposal for payment of total station survey and GEO Technical Investigation (Soil Investigation) at Thane | CBIC / CPWD | 0.03 | Proposal sanctioned on 04.10.2019. | Fund amounting to Rs. 3,23,363/- released on 16.10.19.
27 | DRI (HQ), Delhi 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of boundary wall alongwith soil testing and digital survey of land in r/o plot of land purchased from the DDA for office building of DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 0.25 | Proposal sanctioned on 09.10.19. | Fund amounting to Rs. 25,56,450/- released vide S.O. No. 26/19 on 16.10.19.
28 | CGST Jodhpur/ Jaipur 916/19/Const./Jodhpur/HRD/18 | Comprehensive Consultancy Services for Master Planning of Campus & Design of Office cum Residential Campus for CGST at Jodhpur | CBIC/CPWD | 1.11 | Proposal for Master planning has been sanctioned on 25.09.2019. File is submitted to Ministry for revalidation on 24.01.2020. | In F.Y. 2019-20 Rs. 10.00 lakhs have been released on 01.10.2019.