## Major Sanction & ongoing
Major Sanctioned and Ongoing Infrastructure Projects as on 31.05.2020
S. No. | Commissionerate/ Zone / File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Project Status | Funds status | Present Status
1 | NACIN Hyderabad / NACIN / 916/02/Const./ Hyderabad/ HRD/13 | Construction of RTI, NACIN, at Attapur, Hyderabad Total built up area- 11940 sqm. | CBIC/ NBCC | 46.71 | Yes | Proposal sanctioned on 30.12.2016. | Original proposal received in Jan., 2013 . File submitted to Ministry on 26.02.2014, 10.11.2014, 04.09.2015,18.04.2016 & 23.11.2016. | Project sanctioned on 30.12.2016. The project is being executed by NBCC. The construction work is in full swing. | Rs. 7.00 Cr. were released in 2017-18 out of which 4.67 were utilized. Rs. 25.07 Cr. were released in 2018-19 out of which Rs. 15.07 cr. were utilized. Rs. 7.00 Cr. were released on 04.06.2019. Rs.12.00 Cr. released on 28.02.2020. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Based on the reply received from NACIN, file submitted to the Ministry for revalidation of Sanction Order.
2 | Pr. Comm. Cus.(Gen.) / Mumbai Zone-I / 911/3/Custom Enclave/Mumbai/ HRD/16 | Construction of Office complex and residential quarters at Customs Enclave Plot, Wadala, Mumbai through CPWD at a cost of Rs. 495.5 Cr. for office complex and Rs. 480 cr. For residential complex Office space 30000 sqm. Total qtrs. -769 | CBIC/CPWD | 975.72 | Yes | Project is being developed on self-sustaining basis. All the offices of GST Excise, DRI, DGCEI etc. will be relocated in the said project. | This land was given free of cost by the Salt Department 1980's. Due to the construction of roads we now have 46 acres encrochment free land where godowns exist. Initially it was thought that Govt. will pay for the construction which was to be done by CPWD. However, with the approval of Revenue Secretary it has been deceided to nominate NBCC to construct the office building and residential quarters without any cost to the Govt. The cost of construction only is likely to be Rs. 2700 crores. | Proposal Sanctioned on 11.11.2019. | Rs. 5.00 Cr. (Rs. 2.50 Cr. for office & Rs. 2.50 Cr. for residence) released on 11.11.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
3 | Cus. (Prev.), Jamnagar/ Ahmedabad / 916/8/Const./ Jamnagar/HRD/16 | Construction of office building at Jamnagar Total land- 10,250 sqm. Office space- 4131.34 sqm. | CBIC/ CPWD | 43.67 | Yes | Project in advanced stage |  | Project sanctioned on 13.12.2017. | Rs. 15.00 Cr. were released in 2018-19 out of which 4.00 were utilized. Rs. 7.00 Cr. were released in 2019-20 out of which 6.78 Cr. has been utilized till Nov, 2019. Addl. Rs. 5.00 Cr. revalidated from Min. and released on 17.02.2020. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Based on the reply received from the Commissionerate, file submitted to the Ministry for revalidation of Sanction Order. IFU approved the revaildation accordingly file submitted to the Ad-VIII for issuance to ssantion order so that funds can be released.
4 | CGST Jalandhar/ Chandigarh/ 916/09/Const./ Jalandhar/ HRD/16 | Construction of office cum residential qtrs.and boundary wall at Jalandhar Total land - 06 acre Total qtrs.- 116 Type wise qtrs.- Type-II=19 Type-III=62 Type-IV =32 Type-V A=01 Type-V B=01 Type-VI=01 | CPWD/ CPWD | 67.57 | Yes | Project approved by IFU. Non-construction fee will accrue if construction not started | Original proposal received on 06.09.2016. Query letter sent on 16.09.2016. Reply received on 17.11.2016.File submitted to the Ministry on 18.11.2016, 20.12.2016, 03.02.2017, 27.02.2017, 03.04.2017, 14.06.2017 & 28.07.2017. | Project was sanctioned on 4.8.2017 and being executed through MoUD funds. During the visit to Chandigarh on 06.12.2019 JD (I&W) had reviewed the project status and found to be satisfactory.
5 | CGST, Delhi (North)/ Delhi/ 916/03/Const./ Dwarka/HRD/17 | Construction of residential qtrs. at Dwarka Total land- 17832 sqm. Total qtrs.-256 Type wise qtrs.- Type-IV=168 Type-V=52 Type-VI=36 | CBIC/ NPCC | 227 | No | ____ | This is a very old proposal. Due to deficiencies in the bidding process Revenue Secretary advised for fresh bidding on 03.04.2017. Commissionerate invited tender along with RFP on 27.04.2017. Revised proposal received on 16.06.2017. | Project sanctioned on 25.07.2018. | Rs. 3.00 Cr. released on 27.07.2018 and Rs. 30.00 Cr. released on 26.02.2019 in F.Y. 2018-19. Further Rs. 26.50 Cr. released on 16.08.2019 and Rs. 12.00 Cr. released on 12.03.2020. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
6 | Chennai Cus. (Gen.) VIII / Chennai / 916/03/Const./Chennai/RD/16 | Construction of residential qtrs. at Anna Nagar, Chennai. Total land- 1,06,086 sqm. Total qtrs.-726 Type wise qtrs.- Type-II=288 Type-III=288 Type-IV=150 | CBIC/ CPWD | 348.77 | Yes | Project approved by IFU. Presentation to be made in front of the RS | Original proposal received in Feb. 2016. .File submitted to the Ministry on 29.04.2016, 21.11.2016, 03.01.2017, 26.04.2017 & 14.08.2017. | Project sanctioned on 13.10.2017. | Rs. 30.00 cr. released in 2018-19 out of which Rs. 12.00 cr. utilized. Rs. 20.00 Cr. were released on 24.07.2019. LoA has been issued on 30.08.2019. Rs. 18.00 cr.is the expenditure as per PFMS till date. Addl. amount of Rs. 15.00 cr. sought in RBE 2019-20 has been released on 27.01.2020. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Based on the reply received from the Commissionerate, file submitted to the Ministry on 29.4.2020 for revalidation of Sanction Order. IFU approved the revaildation accordingly file submitted to the Ad-VIII for issuance to ssantion order so that funds can be released.
7 | CGST, Raigad /Mumbai./ 911/4/Misc./Kharghar/HRD/15 | Construction of residential qtrs. at Kharghar by NBCC. Total land- 20,000.32 sqm. Total qtrs.-187 Type wise qtrs.- Type-II=42 Type-III=70 Type-IV=44 Type-IV (Spl)=20 Type-V=09 Type-VI=02 | CBIC/ NBCC | 110.11 | Yes | Project in advanced stage. |  | File sanctioned on 18.04.2019 | Rs 5.00 cr. were released on 23.04.2019 and further Rs. 6.011 Cr. released on 07.06.2019. Further, Rs. 10.00 Cr. released on 17.01.2020. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Based on the reply received fro the Commissionerate proposal for revaildation of sanction order submitted to the Ministry on 27.5.2020.
8 | CGST, Belgavi/ Bengaluru / 916/15/Const. /Belgaum/ HRD/12 | Construction of office cum residential qtrs. at Bagalkot Total land-01 acre Office space-1080 sqm. Residential space-465 sqm. Total qtrs.-02 Type wise qtrs.- Type-III=01 Type-IV=01 | CBIC/ CPWD | 2.19 | Yes | Project in advanced stage. Land worth Rs. 7-8 cr. which was provided free of cost will be taken back by Town Development Authority in case of non-construction.. |  | Project sanctioned on 10.01.2018. | Rs. 5.00 lakh released on 16.01.18 & Rs. 15.00 lakhs on 12.02.2018 but could not utilized. Rs. 20.00 lakh again released on 20.08.2018, Rs. 199.03 lakhs relaesed on 01.11.2018. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
9 | Hyderabad Cus./Hyderabad CGST/ 916/14/Const./Hyderabad/HRD/16 | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | CBIC/ CPWD. | 1.3 | No | ____ | Original proposal received on 24.10.2016. File submitted to the Ministry on 14.02.2017, 02.03.2017 & 04.07.2017. Ministry returned the file with observations on 23.02.2017, 10.04.2017 & 28.08.2017. | Proposal sanctioned on 07.03.19. | Rs. 10.00 lakhs were released in 2018-19 but could not be utilized Further, Rs. 50.00 lakhs has been released on 29.07.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
10 | CGST Tirupati/Visakhapatnam/ 916/55/Const./ Anantpur/HRD/ 06 | Construction of office building at Anantapur, Andhra Pradesh. Office space: 1292.70 sqm. | CBIC/ CPWD | 7.07 | No |  | Original proposal received on 06.07.2006.Revised PE received on 11.12.2015.Query letter sent on 28.11.2016, 11.04.2016, 29.07.2016, 14.12.2016 followed by reminders and DO letter dated 25.04.2017. | Proposal sanctioned on 21.12.2018 | Rs. 1.00 Cr. were released in 2018-19 but could not be utilized Further, Rs. 4.06 has been released on 29.05.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Fund requirement letter received , in which some clarification is required, so letter to Commissionearte issued on 21.5.2020
11 | Customs (General) JNCH/Mumbai-II Customs / 916/17/Const./ Raigad/HRD/16 | Construction of additional office building (G+7) at JNCH NHAVA SHEVA Dist. Raigad-Mumbai Available area - 14900 sqm. Office space - 8551.80 sqm. | CBIC/ CPWD | 90.26 | No | ___ | Original proposal received in nov. 2016. Query letter sent on 13.12.2016 followed by several reminders and DO letters. | Proposal for enabling works (Rs 51 Lakh) was sanctioned in March, 2018. Proposal for office sanctioned on 14.02.2019. | Rs. 43 lakh for enabling works was released on 19.07.2019. Further due to pending approvals from local authorites Comm'te vide letter dated 10.10.19 has requested not to released in balance amount. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
12 | Mangalore Custom/ Bengaluru / 202/7/2003 Ad. VIII (EC) | Providing Barbed wire fencing and Name Boards to properties belonging to Customs Department at Karwar, for Rs. 89,56,000. | CBIC/ CPWD | 0.89 | Yes | The said land is required to be protected from encroachment and this is a small project. | Original proposal received on 25.05.2016. File submitted to the Ministry on 10.11.2016, 18.01.2017 &12.05.2017. | Project sanctioned on 15.09.2017. | Rs. 83,44,052/- were released in 2017-18, out of which RS. 6,11,948/- utilized in 2017-18 & Rs. 14,21,578/- utilized in 2018-19. Further, Rs. 75,34,422/- released on 12.07.2019 during 2019-20. LoA has not been issued till date as per PFMS.
13 | Udaipur/Jaipur / 916/11/Const./ Jaipur-II/HRD/11 | Construction of office building CGST division Bhilwara. Land area: 1858.06 sqm. Office space : 750.00sqm. | CBIC/ CPWD | 9.72 | No | ___ | Original proposal recieved on 08.09.2014. Query letter sent on 31.10.2014, reply recieved on 15.04.2015. Query letter sent on 18.05.2015 followed by several reminders. | Proposal sanctioned on 21.02.2019. | Rs 1.5 cr have been released on 26.02.2019 but could not utilized. During 2019-20 Rs. 50.00 lakhs has been released on 25.07.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Fund requirement letter received , in which some clarification is required, so letter to Commissionearte issued on 21.5.2020
14 | CGST, Agartala/ Guwahati / 916/10/Const./ Shillong/HRD/15 | Construction of office building (Audit Circle, Custom division & CGST Division) at Agartala Total land- 3022 sqm. Office space-2793 sqm. Guest House-463 sqm. | CBIC/ CPWD | 28.04 | Yes | Project in advanced stage | Original proposal received on 16.09.2015. Deficiency letter sent on 14.10.2015, 23.03.2016 & 29.08.2016. Reply received on 23.02.2016, 12.08.2016 and 29.05.2017 subsequently. | Proposal sanctioned on 18.02.2019. | Rs 50 Lakh released on 26.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 1.00 Cr. released on 28.05.2019. Addl. Rs. 3.00 Cr. revalidated from Min. and released on 17.02.2020. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Based on the reply received from the Commissionerate, file submitted to the Ministry on 29.4.2020 for revalidation of Sanction Order. IFU approved the revaildation accordingly file submitted to the Ad-VIII for issuance to ssantion order so that funds can be released.
15 | DRI Kolkata/ DRI 916/02/Const. /Kolkata/ HRD/2016 | Construction of DRI at Plot No. CBD-93, Action Area-II, New Town, Kolkata | CBIC/CPWD | 64.5 | ___ |  | Not Sanctioned | Proposal sanctioned on 08.02.2019. | Rs 10 Lakh released on 18.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 2.00 Cr. released on 14.08.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21, Based on the reply received from the Commissionerate, file submitted to the Ministry on 18.5.2020 for revalidation of Sanction Order,
16 | CGST Pune-II/ Pune / 916/5/Const./ Pune/ HRD/2014 | Construction of office building and 02 nos. residential quarters for CGST Ranges office at Pandharpur, Distt. Solapur, Maharashtra. Total land : 2230.22 sqm. Office space :146.50 sqm. One quarter Type IV | CBIC/ CPWD | 2.02 | No | ___ | Original proposal received on 25.04.2014. Query letter sent on 27.07.2014, 29.08.2016 & 16.02.2017. followed by several reminders. Reply received on 11.12.2015, 08.02.2016 & 17.02.2017 respectively. | File sanctioned on 23.12.2019 | Rs. 20.00 lakh released on 30.12.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
17 | CGST Palghar/ Mumbai/ 916/5/Const./ Mumbai/HRD/ 16 | Construction of 3 Div. offices and 14 ranges offices on plot bearing NosP-34 at MIDC, Boisar-reg. | CBIC/ CPWD | 33.25 | No | ____ |  | Proposal sanctioned on 01.07.19. | Rs. 1.00 Cr. released on 19.07.19. LoA issued on 15.10.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
18 | Tuticorin/ Trichy Customs/ 916/19/ Const./ Tuticorin/HRD/14 | Construction of additional residential quarters (T-II, T-III & T-IV) at Port Area, Tuticorin. Total qtrs.- 06 Type wise qtrs.- Type-II=1 Type-III=2 Type-IV =3 | CBIC/ CPWD | 1.62 | Yes | Project in advanced stage. As this is a small project construction will be completed within 1 year. | Original proposal received on 09.11.2014. Query letter sent on 14.11.2014, 30.06.2015, 17.07.2015. File has been submitted to the Ministry on 01.09.2016. | Project sanctioned on 25.08.2017. | Rs. 1.47 Cr. were revalidated for F.Y. 2019-20 and released on 07.07.2019. LoA has been issued on 11.09.2019. No expenditure is being shown as per PFMS till date. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
19 | Patna Cus. (Prev.)/ Patna Cus./ 916/16/Const./Patna (P)/HRD/2016 | Proposal for construction of Residential complex at Land Customs Station jogbani, a/ a & e/s of Rs.7,99,52,000/- Total qtrs.- 21 Type wise qtrs.- Type-II=7 Type-III=12 Type-IV =02 | CBIC/ CPWD | 7.99 | No | ___ | Original proposal received on 21.11.2016. Query letter sent on 13.12.2016. Reply received, file submitted to the Ministry on 06.02.2017, IFU returned file with certain queries, file resubmitted to ministry after clarifying the queries on 10.08.2017. | Project sanctioned on 11.06.2018. | Rs. 4.00 cr. have been released to the Comm'te. Comm'te surrendered Rs 3.5 crore. In F.Y. 2019-20 Rs. 3.99 cr. released on 12.07.19. MPR is awaited. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
20 | Patna Cus. (Prev.)/Patna Cus./ 916/15/Const./Patna/HRD/14 | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul Total land- 2.74 acre Residential space-5,730 sqm. Total qtrs.-21 Type wise qtrs.- Type-III=06 Type-IV=14 Type-IV (Spl)=01 | CBIC/ CPWD | 11.85 | Yes | Sanctioned | Original proposal received in September 2014. Query letter sent on 17.11.2014, 25.06.2015, 20.07.2015. Reply received on 03.03.2015, 25.08.2015. File submitted to the Ministry on 08.11.2016 and 04.07.2017. | Project sanctioned on 22.09.2017. | Rs.9.5 cr. have been released to the Comm'te in this F.Y. 2018-19. Rs. 1.34 Cr. utilized in 2018-19. Comm'te had surrendered Rs 7.17 crore. In the current F.Y. 2019-20 Rs. 3.00 Cr. released on 14.08.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
21 | CGST Tirupati/ Visakhapatnam/ 916/4/Const./ Kurnool (A.P.)/HRD/2012 | Construction of 7 Nos. Type-IV Quarters and Guest House for Kurnool (Tirupati Comm’te), Andhra Pradesh-reg. Total Land :606.88 sqm. | CBIC/ CPWD | 3.96 | No | ____ |  | Proposal sanctioned on 10.09.2018. | Funds to the tune of Rs. 1.18 cr. released on 20.09.2018, out of which Rs. 44,18,857/- were used during F.Y. 2018-19. During F.Y. 2019-20, Rs. 73,82,000/- released on 20.08.19. Comm'te has surrendered Rs 98 Lakh. Further, IFU raised query regarding addl. amount sanction and same were conveyed to comm'te on 11.11.19. Addl. Rs. 50.00 lakhs released on 06.12.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. based on the fund requirement received,letter issued on 8.5.2020 to EMC seeking commitment from lumpsum grant
22 | CGST Ahmedabad (North)/ Ahmedabad/ 916/8/Const./ Ahmedabad/HRD/17 | Construction of new building in the Custom House Compound, Ahmedabad. | CBIC/ CPWD | 31.87 |  |  |  | Project sanctioned on 11.06.2018. | Rs. 5.00 cr. was released in F.Y. 2018-19, Comm'te has surrendered Rs. 4.75 cr. During F.Y. 2019-20 Rs. 2.00 cr. released on 20.08.2019. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Reminder issued on 27.5.2020.
23 | CGST Ghaziabad & CGST (Audit), Noida/ Meerut/ 916/5/Const./ Meerut/HRD/17 | Construction of office building including boundary wall and culvert over Nala at allotted land measuring 2.21 acres (8894 sqm.) to CGST Ghaziabad, Audit-II, Ghaziabad, Noida | CBIC/ CPWD | 116.42 |  |  |  | Project sanctioned on 03.10.19. | Rs. 1.00 cr. released on 14.10.2019 in F.Y. 2019-20. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Based on the reply received from the Commissionerate, file submitted to the Ministry for revalidation of Sanction Order. IFU approved the revaildation accordingly file submitted to the Ad-VIII for issuance to ssantion order so that funds can be released.
24 | Delhi (South)/CGST Delhi/ 916/62/Const./Nangal Raya/HW/06 | Construction of office building at Nangal Raya, New Delhi. | CBIC/NBCC | 32.83 |  |  |  | Proposal sanctioned on 13.06.2016. Complete amount has been released to the Comm'te. Comm'te has informed that civil work has almost completed
25 | CGST Agra/Lucknow 916/05/Const./Agra/HRD/2018 | Construction of conference hall in the building of CGST Comm'te Agra. | CBIC/CPWD | 0.12 |  | Proposal is under process at DGHRD |  | Project sanctioned on 13.08.19 | In F.Y. 2019-20 Rs. 11,97,143/- have been released on 28.08.2019.
26 | CGST Thane/Mumbai 916/15/Const./Thane/HRD/2018 | Proposal for payment of total station survey and GEO Technical Investigation (Soil Investigation) at Thane | CBIC / CPWD | 0.03 |  |  | Not Sanctioned | Proposal sanctioned on 04.10.2019. | Fund amounting to Rs. 3,23,363/- released on 16.10.19.
27 | DRI (HQ), Delhi 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of boundary wall alongwith soil testing and digital survey of land in r/o plot of land purchased from the DDA for office building of DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 0.25 |  |  |  | Proposal sanctioned on 09.10.19. | Fund amounting to Rs. 25,56,450/- released vide S.O. No. 26/19 on 16.10.19.
28 | CGST Jodhpur/ Jaipur 916/19/Const./Jodhpur/HRD/18 | Comprehensive Consultancy Services for Master Planning of Campus & Design of Office cum Residential Campus for CGST at Jodhpur | CBIC/CPWD | 1.11 |  |  | Not Sanctioned | Proposal for Master planning has been sanctioned on 25.09.2019. Proposal approved by the Ministry. | In F.Y. 2019-20 Rs. 10.00 lakhs have been released on 01.10.2019.
29 | CGST Udaipur/Jaipur/ 916/4/Const./Udaipur/HRD/19 | Construction of new office buildiing for Udaipur CGST Comm'te | CBIC/CPWD | 42.07 |  |  |  | Proposal sanctioned on 9.03.2020 | Rs. 10.00 lakh released on 18.03.2020 in F.Y. 2019-20. | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21. Based on the fund requirement received, from the commissionerate,file submitted to the Ministry on 8.5.2020 for revaildation of sanction order
30 | Cus. Jamnagar (dwarka) Ahmedabad 916/17/Const./Ahmedabad/HRD/18 | Construction of office building at the site of shore guard, Dwarka, Jamnagar. | CBIC/CPWD | 1.24 |  |  |  | Proposal Sanctioned | Fund to be released in BE 2020-21 | E-mail issued to the Commissionerate on 21.4.2020 to confirm the funds requirement in FY 2020-21, based on the fund requirement received,letter issued on 8.5.2020 to EMC seeking commitment from lumpsum grant
31 | 916/21/Const./DRI/Hyderabad/ HRD/19 | Construction of office building for DRI Hyderabad Zonal Unit at Jubilee Hills at Hyderabad (Geo Technical Investigation) | CBIC/CPWD | 0.08 |  |  |  | Proposal for Geo Technical Investigation sanctioned . | Funds amounting to Rs. 0.08 Cr.released on
32 | 916/7/Const./NACIN-Munnar/HRD/18 | Enabling works for construction of RTI NACIN, Munnar, Kerala | CBIC/CPWD | 0.03 |  |  |  | Revalidation of Sanction Order No. Const./19/Sanction/2018-19 dated 08.01.2019 for Enabling works for construction of RTI NACIN, Munnar, Kerala | funds to the tune of Rs. 2,75,000/- were release in FY 2019-20 but could not be utilized in the F.Y. 2019-20 | Based on the request letter of NACIN,Munnar, file is submitted to the Ministry on 8.5.2020 for revaildation of the sanction order
33 | 916/08/Const./Chennai/HRD/ 2018 | Construction of 36 residential quarters at Nungambakkam, Chennai | CBIC/CPWD | 49.02 |  |  |  | Revalidation of sanction Order No. Const./04/Sanction/ 2019-20/ dated 27.05.2019 |  | File submitted to the Ministry for revaildation of sanction Order, IFU approved the revaildation accordingly file submitted to the Ad-VIII for issuance to ssantion order so that funds can be released
22 | DRI Lucknow 916/3/Const./DRI-Lucknow/HRD/2020 | Construction of boundary wall by DRI Zonal Unit, Lucknow | CBIC/CPWD | 0.98 |  |  |  | Proposal for Sanctioned by the Ministry |  | As the project was sanctioned the last week of March 2020, funds were not released in 2019-20. Now after seeking commiement from EMC file submitted to the Ministry for revaildation of sanction order on 27.5.2020