## Ongoing projects
Major Ongoing Infrastructure Projects as on 31.05.2020
S. No. | Commissionerate/ Zone / File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | CGST Dibrugarh/Guwahati/ 916/4/Const./ Shillong/HRD/15 | Construction of office cum residential qtrs. at Dibrugarh. Total office space: 3562 sqm. Total quarters: 56 (Type-II 14, Type-III 28 & Type-IV 14) | CBIC/ CPWD | 60.37 | No | ____ | Original proposal received on 04.09.2015. Deficiency letter sent on 22.09.2015 followed by several reminders. Do letter to forward consolidated proposal sent on 22.03.2017. | The proposal was submitted to the Ministry on 21.05.2018. IFU had made some observations regarding budget head, cost index, carpet area and the same were conveyed to Comm'te on 12.09.19. Incomplete reply received Comm'te vide letter dated 14.01.2020 again requested to submit a proper reply. Reminder sent on 19.03.2020.
2 | CGST Kolhapur/Pune/ 916/21/Const. /Pune/HRD/14 | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur-reg. Land area: 12854.8 sqm. Office space : 9244.1 sqm. | CBIC/ CPWD | 43.79 | No | ____ | Original proposal received in March 2015. Query letter sent on 10.04.2015 followed by several reminders. | Proposal was received on 25.01.2019 and file was submitted to the Ministry. IFU vide note dt. 31.12.2019 has made some observations reg. FSI, plinth area, car parking space etc. which have been conveyed to the Comm'te on 14.01.2020. Reply received of IFU queries and file is submitted to the Min. on 13.02.2020 for a/a & e/s. Presently file is with US (IFU).
3 | CGST Hyderabad/ Secunderabad/ 916/13/Const./ Hyderabad/HRD/15 | Completion of 287 unfinished Dept. qtrs taken over from M/s Sri Durga Estate Pvt. Ltd. at Hyderabad | CBIC/ NBCC | 49.75 | Yes | MoU has been approved by Ministry. 287 Qtrs. in dilapidated condition will become habitable on the nominal cost of Rs. 21.3 Cr. (approx.) | Original proposal received on 02.11.2015.Miinistry gave concurrence to appoint NBCC as PMC on 24.12.2015. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Ministry had returned the file with certain observations reg. project status which was conveyed to comm'te on 21.05.19. Reply still awaited. A DO Letter has been written by DG,HRD to expedite the matter on 19.3.2020. Commissionerate vide letter dt. 28.2.2020 informed that they are in the process of revising the proposal and will submit a new proposal at the earliest. As the revised proposal is still awaited, a reminder is issued on 18.5.2020. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Funds released on 20.09.2018.
4 | CGST Raipur/ Bhopal/ 916/4/Const./Raipur/HRD/17 | Construction of office building and residential quarters at Rajnandgaon. | CBIC/ CPWD | 2.8 | Yes |  | Proposal for purchase of land sanctioned by competent authority on 17.04.2017. | Proposal received on 12.09.2017 and submitted to Min. for a/a & e/s on 17.07.2019. IFU returned the file with certain queries which were conveyed to Comm'te on 18.09.19. Pr. Commr., Raipur had visited in DGHRD on 16.12.2019 to discuss the project status. Reply awaited. Reminder sent on 19.03.2020.
5 | CGST Udaipur/Jaipur 916/1/Const./HRD/2018 | Proposal for repair/renovation and upgradation of staff houses at Udaipur. | CBIC / CPWD | 25.56 |  |  | Not Sanctioned | Fresh proposal was received on 08.04.2019 and submitted to Min. on 05.07.19. File returned by the IFU with certain queries reg. justification of proposal etc. the same were conveyed to the Comm'te on 24.12.2019. Reply receiived, file submitted to the Ministry for a/a & e/s.
6 | Cus. (P.), Vijaywada/Visakhapatnam 916/15/Const./Visakhapatnam/HRD/16 | Const. of buildings for newly formed Customs Comm'te (P.), Vijaywada-HQRS. Office Complex and Residential Quarters at Sy. No. 29/8 (3.84 acres) of Kesarpally Village of Gannavaram Mandal of Krishna Dist. Andhra Pradesh | CBIC / NBCC | 65.49 |  |  | Not Sanctioned | Revised proposal received on 01.03.2019, proposing to award this work to NBCC certain clarifications were sought by DGHRD whcih were conveyed to Comm'te after receiving the reply from the Comm'te on 22.05.2019, the proposal was submitted to Min. for a/a & e/s. But Member (Admn.) returned the file and asked to Comm'te to get in writing a letter from CPWD showing their inability before awarding this work to NBCC. Incomplete reply received accordingly again requested the commissionerate to submit point-wise reply. Commissionerate vide letter dt. 4.5.2020 informed that they have taken-up the matter with CPWD, and CPWD is willing to take the project, accordingly vide letter dated 8.5.2020 requested the Commissionerate to approch CPWD and get the PE
7 | CGST Agra/Lucknow /916/5/Const./Aligarh/HRD/19 | Const. of new office building for CGST Division at Aligarh. | CBIC/CPWD | 11.34 |  |  |  | File has been submitted to the Min. on 22.05.2019. File returned from the Ministry with certain observations reg. space requirement, cost of const. etc.and the same were conveyed to the Comm'te on 27.06.2019. Reply received and file is submitted to Min. on 05.09.19 for a/a & e/s. File returned with observations, based on the reply received, file submitted to the Ministry on 20.02.2020. file return back from the Ministry with certain observations, which are conveyed to the Commissionerate for n/a on 8.5.2020
8 | Chennai Customs/Chennai 916/12/Const/Jaffer Syarang-Chennai/HRD/19 | Construction of office accomodation building for Partner Govt. Agencies, Chennai Customs Audit and Import Comm'te at Jaffer Syarang Street, Chennai. | CBIC/CPWD | 86.75 |  |  |  | Proposal was received in July, 2019. IFU has raised observations reg. existing carpet area, shortage of space etc. and the same were conveyed to the comm'te on 30.10.19 Reply received and the file submitted to the Min. on 17.02.2020 for a/a & e/s. File received back from Ministry with certain observations, which have been conveyed to the Commissionerate for n/a. througt e-mail on 29.4.2020 and by letter on 4.5.2020
9 | CGST Jaipur/Jaipur 916/2/Const. Jaipur/HRD/19 | Dismantling and reconstruction of T-VI/3 Bunglow at C.Ex. Officers residence colony, JLN Marg, Jaipur | CBIC/CPWD | 2.07 |  |  |  | Proposal for const. of RCC wall sanctioned on 09.01.2020 (partly sanctioned). Acoordingly, Rs. 10.00 lakh released on 27.01.2020. Proposal for demolition of the existing flat also sanctioned. Further IFU made observations reg. demand survey of residential quarters, which are conveyed to the Comm'te on 19.03.2020.
10
11 | CGST Bhavnagar / Ahmedabad / 916/21-A/Const./Bhavnagar/HRD /11 | Construction of office building at Bhavnagar Total land- 7104 sqm. Office space-4807.50 sqm. | CPWD/ CPWD | 50.28 | Yes | Project in advanced stage and funds will be provided by CPWD. | Original proposal received on 16.01.2014. Query letter sent on 04.03.2014 & 22.12.2014. Reply received on 19.11.2014 & 17.10.2016. File submitted to the Ministry on 09.01.2017 & 12.05.2017. | Project sanctioned on 30.08.2017. But due to change in PAR 2019. A revised proposal has been forwarded by the Comm'te, which has been submitted to the Min. for a/a & e/s of the increase amount on 26.02.2020. File received back from FA, who had advised to keep the file pending for some time.
12 | Bhubaneswar/ Bhubaneswar / 916/12/Const. /Bhubaneswar/ HRD/14 | Const. of Retaining wall and Approach Road and from the main road to the office plot at Bagbrindaban Mauja of Balasore Town in state of Odisha. | CBIC/ CPWD | 1.57 | No | ____ | Original proposal received in September 2014. Query letter sent on 29.12.2014, 03.12.2015 & 23.08.2016. followed by several reminders. | CPWD has submitted a revised P.E for Rs 1.57 Cr. while examining the proposal DG, HRD has raised some queries, based on the reply/clarifications submitted by Comm'te proposal forwarded to the MInistry for a/a & e/s on 26.12.2019. File received back from the Min. with certain observations reg.ofice space, approach road etc. letter communicated to Comm'te on 14.02.2020. Last reminder issued on 16.3.2020
13 | Goa Cus./ Pune/ 916/10/Const./Goa/HRD/17 | Construction of addl. staff quarters for Customs Department at Customs Colony, Headland Sada, Marmagoa, Goa. | CBIC/CPWD | 37.28 |  |  |  | Proposal for demolition of dilapidated RCC overhead tank sanctioned on 16.01.2020. Acoordingly, Rs. 2,39,000/- released on 27.01.2020. Further IFU vide note dated 06.12.2019 raised certain queries reg. demand survey, justification of joggers park etc. and the same were communicated to the Comm'te on 12.12.2019. Reply awaited. Reminder issued on 24.02.2020.
14 | CGST Guntur/Visakhapatnam/ 916/11/Const./Guntur/HRD/18 | Construction of office building at Eluru (A.P.) | CBIC / CPWD | 6.95 |  |  | Not Sanctioned | File was submitted to the Ministry and IFU made observations regarding provision of funds, permissible FAR etc. which were conveyed to the Comm'te. File was re-submitted with replies. However, IFU made observations regarding plinth area, feasibility of construction for given sanctioned strength, etc., based on the reply received from Comm'te on 03.01.2020, file re-submitted to Min. on 14.01.2020. File returned back by the Min. with certain queries reg. per sq. ft. cost, layout plan etc. & also dropped the proposal which were conveyed to the Comm'te on 05.03.2020.
15 | Chennai Cus. (Gen.)/Chennai / 916/08/Const./Chennai/HRD/2018 | Construction of 36 residential quarters at Nungambakkam, Chennai | CBIC / CPWD | 65.42 |  |  | Sanctioned | Project sanctioned. Due to revision in PAR norms the cost has been increased accordingly, revised PE with a new cost of Rs. 65.00 Cr. was received in Nov, 2019. There is escalation of original cost by Rs. 16.39 Cr. On account of superior sanitary fitting, false sealing, mechaniced car parking. Rs. 10.00 Cr. cost has increased on account of mechaniced car parking only. Proposal submitted to MIn. on 17.01.2020. File returned back to the MIn. with certain observations reg. increase in cost etc. which were conveyed to the Comm'te on 11.03.2020. | Rs. 5.00 Cr. were revalidated for F.Y. 2019-20 and released on 31.05.2019. LoA has been issued on 11.09.2019. Rs. 20.00 lakh is the expenditure as per PFMS till date.
16 | CGST Tirupati/Visakhapatnam 916/06/Const./Tirupati/HRD/2015 | Construction of office building and staff quarters at Tirupati | CBIC / CPWD | 57.06 |  |  | Not Sanctioned | Revenue Secretary on 22.06.2017 made observations regarding PPP Model, Cost benefit analysis etc. Comm'te withdrew the proposal. Revised proposal has been received and after submission to Min. file returned by the IFU with ceratin queries which were conveyed to Comm'te on 18.09.19. Further, based on the reply received from the Comm'te file re-submitted to the Min. on 22.11.19. Revenue Secretary upon discussing the proposal with FA has disagreed the proposal. Conveyed to the Commissionerate
17 | CGST Nagpur-I/Nagpur 916/18/Const./Nagpur/HRD18 | Const. of 6 nos. of T-VI qtrs.for Central Excise at B.No. 12, Seminary Hills, Nagpur Internal Water Supply, Sanitary Installation, Drainage and Internal Electrical Works involving an expenditure of Rs. 734.63 lakhs. | CBIC / CPWD | 7.35 |  |  | Not Sanctioned | Proposal received and submitted to the Min. on 15.07.19 for approval. IFU returned the file with certain queries reg. justification of T-VI qtrs. and GH etc. and the same were conveyed to the Comm'te on 05.12.2019. Reply received and file is submitted to the Min. on 26.12.2019. AS & FA query reg. high cost of const. communicated to Comm'te on 18.02.2020. Justification to IFU query received and file submitted to the Ministry for a/a & e/s.
18 | CGST Goa/Pune 916/1/Const./Goa/HRD/2019 | Redevelopment of 52 nos. of staff quarters and community centre for CGST Goa Commissionerate, Goa at Alto-porvorim | CBIC/CPWD | 27.16 |  |  |  | Fresh proposal received and raised the queries by DGHRD letter sent on 24.09.19. File is submitted to the Min. on 08.01.2020. File receievd back from IFU with certain observations reg. GRIHA norms, cost of const. of per flat, cost index etc., which have been conveyed to the Comm'te on 28.02.2020
19 | Customs (Airport) Bengaluru/Bengaluru 916/16/Const./Bengaluru/HRD/ 2019 | Construction of new customs House Building at bengaluru International Airport | CBIC/CPWD | 57.37 |  |  |  | Fresh proposal was received in October, 2019 and queries reg. calculation of office space, per sq.ft. Cost, cost benefit analysis etc. conveyed to the Comm'te on 14.10.19, followed by reminder on 16.12.2019. Reply received on 03.01.2020, file submitted to MIn. on 20.01.2020. File returned back by the Min with certain observations reg. calculation of space, cost per sq. ft., cost benefit analysis etc. which where conveyed to the Comm'te on 11.03.2020.
20 | Jamnagar Cus./Ahmedabad 916/17/Const./Jamnagar (Res.)/HRD/19 | Construction of Staff quarters at Jamnagar | CBIC/CPWD | 18.86 |  |  |  | Proposal received on 09.09.19. Savings of HRA of the staff/officers has not informed accordingly query letter issued on 09.10.19. Reply recvd on 29.10.19, DGHRD sought some further clarification which were replied by the Comm'te on 06.12.19 & 06.01.2020. File submitted to the MIn. on 17.01.2020.File returned back by the Min. with certain observations reg.cost of const. per flat, area of quarters etc. communicated to the Comm'te on 05.03.2020.
21 | CGST Manipur/ Guwahati 916/3/Const./Shillong/HRD/19 | Const. of office building and boundary wall at Lamphel at Imphal Shillong | CBIC/CPWD | 46.4 |  |  |  | Proposal was received on 16.09.2019. In the meantime, a reference was received from Sh. Bhabananda Singh, M.P. (Rajya Sabha) for allotting this work to MANIDCO. Matter was got clarified from the Comm'te and based on the report proposal was process for awarding the work to State PWD accordingly, the proposal was forwarded to Min. for a/a & e/s on 07.01.2020. File returned back by the Min. with certain observations reg. revenue collection,cost benefit analysis, built up area, per sq.ft. cost of const. communicated to the Comm'te on 05.03.2020.
22 | Jammu 916/4/Const./Srinagar/HRD/2020 | Construction of boundary wall with concertina wire fencing around the land at Solina, Srinagar for construction of office and residential buildings of Customs & CGST Division, Srinagar | CBIC/CPWD | 4.14 |  |  |  | Proposal submitted to the Ministry for a/a & e/s
23 | DRI Chennai 916/2 /Const.DRI-Chennai/HRD/2020 | Construction of office Building for DRI CZU | CBIC/CPWD | 31.39 |  |  |  | Proposal submitted to the Ministry for a/a & e/s IFU vide note dated 6.5.2020 has turned down the proposal in view of existing guidelines for expenditure control and advised not to takeup this project during 2020-21. Conveyed to DRI on 21.5.2020
24 | NACIN Chennai 916/5/Const./ Chennai/ HRD/ 15 | Const. of NACIN Complex at Nolambur, Chennai-reg. | CBIC/ UPRNN | 80 | No | ___ | Land measuring 3.26 acre was acquired in 16.02.2015. Formal proposal awaited. | NACIN Chennai vide letter dated 21.05.2019 informed that UPRNN has been selected as PMC on the basis of lumpsum service charges and detailed proposal for awarding the project to M/s UPRNN at a total cost of Rs. 93.00 Cr. received on 20.12.2019. DGHRD observed some queries and the same were conveyed to DG NACIN on 06.01.2020. Reminder sent on 11.02.2020. Revised proposal received and submitted to the Ministry for a/a & e/s. IFU vide note dated 6.5.2020 has turned down the proposal in view of existing guidelines for expenditure control and advised to utilize the existing NACEN/RTI premise for training purpose. Conveyed to NACIN on 21.5.2020
25 | CGST Ahmedabad (Audit) 916/13/Const./Ahmedabad/HRD/2019 | Construction of office premises on land measuring 3972.22 sqm. of final plot No. 175 of TP No. 3 of the commissioner of CGST (Audit), Ahemedabad. | CBIC | 75 |  |  |  | Proposal was received on 15.07.19 alongwith two PEs (CPWD & NBCC). DGHRD raised certain queries reg. non.encumbrance certificate etc. and the same were conveyed to the Comm'te on 26.12.2019. Reply received and proposal submitted to the Ministry for a/a & e/s
26 | DRI (Hqrs) 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of office building of DRI (Hqrs) on the land measuring 6200 sq. mtrs at Plot No 11(B), Vasant Kunj, New Delhi. | CBIC | 86.47 |  |  |  | Proposal received on 23.3.2020, certain shortcomings were noticed, which were conveyed through e-mail on 7.4.2020, as offices are closed due to COVID-19. On the basis of reply received from DRI, proposal processed and submitted to the Ministry for a/a & e/s on 24.4.2020.