## Total list const. projects
Construction on going Projects (Yet to Sanction) as on 30.6.2020
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Jaipur CGST | CGST Udaipur 916/1/Const./HRD/2018 | Proposal for repair/renovation and upgradation of staff houses at Udaipur. | CBIC / CPWD | 25.56 |  |  | Not Sanctioned | Fresh proposal was received on 08.04.2019 and submitted to Min. on 05.07.19. File returned by the IFU with certain queries reg. justification of proposal etc. the same were conveyed to the Comm'te on 24.12.2019. Reminder sent on 24.01.2020. Reply received and file submitted to the Ministry on 27.04.2020. |  | With Ministry
2 | Nagpur CGST | CGST Nagpur-I 916/18/Const./Nagpur/HRD18 | Const. of 6 nos. of T-VI qtrs.for Central Excise at B.No. 12, Seminary Hills, Nagpur Internal Water Supply, Sanitary Installation, Drainage and Internal Electrical Works involving an expenditure of Rs. 734.63 lakhs. | CBIC / CPWD | 7.35 |  |  | Not Sanctioned | Proposal received and submitted to the Min. on 15.07.19 for approval. IFU returned the file with certain queries reg. justification of T-VI qtrs. and GH etc. and the same were conveyed to the Comm'te on 05.12.2019. Reply received and file is submitted to the Min. on 26.12.2019. AS & FA query reg. high cost of const. communicated to Comm'te on 18.02.2020. Reply received and file is submitted to the Ministry for a/a & e/s. |  | With Ministry
3 | Chandigarh CGST | Jammu 916/4/Const./Srinagar/HRD/2020 | Construction of boundary wall with concertina wire fencing around the land at Solina, Srinagar for construction of office and residential buildings of Customs & CGST Division, Srinagar | CBIC/CPWD | 4.14 |  |  |  | Proposal received and file submitted to to the Ministry for a/a & e/s. IFU has approved the proposal file submitted to Chairman, CBIC for approval on 08.06.2020. |  | With Ministry
4 | Ahmedabad CGST | CGST Bhavnagar / 916/21-A/Const./Bhavnagar/HRD /11 | Construction of office building at Bhavnagar Total land- 7104 sqm. Office space-4807.50 sqm. | CPWD/ CPWD | 40.61 | Yes | Project in advanced stage and funds will be provided by CPWD. | Original proposal received on 16.01.2014. Query letter sent on 04.03.2014 & 22.12.2014. Reply received on 19.11.2014 & 17.10.2016. File submitted to the Ministry on 09.01.2017 & 12.05.2017. | Project sanctioned on 30.08.2017. But due to change in PAR 2019. A revised proposal has been forwarded by the Comm'te, which has been submitted to the Min. for a/a & e/s of the increase amount on 26.02.2020. File received with FA on 02.06.2020. File re-submitted to DG,HRD on 18.06.2020. |  | IFU query
5 | Ahmedabad Cus. | Jamnagar Cus./ 916/17/Const./Jamnagar (Res.)/HRD/19 | Construction of Staff quarters at Jamnagar | CBIC/CPWD | 18.86 |  |  |  | Proposal received on 09.09.19. Savings of HRA of the staff/officers has not informed accordingly query letter issued on 09.10.19. Reply recvd on 29.10.19, DGHRD sought some further clarification which were replied by the Comm'te on 06.12.19 & 06.01.2020. File submitted to the Min. on 17.01.2020. File returned back to Min. with certain observations reg.cost of const. per flat, area of quarters etc. communicated to the Comm'te on 05.03.2020. Reminder sent on 11.06.2020. |  | IFU query
6 | Bengaluru Cus | Customs (Airport) Bengaluru/ 916/16/Const./ Bengaluru/HRD/ 2019 | Construction of new customs House Building at bengaluru International Airport | CBIC/CPWD | 57.37 |  |  |  | Fresh proposal was received in October, 2019 and queries reg. calculation of office space, per sq.ft. Cost, cost benefit analysis etc. conveyed to the Comm'te on 14.10.19, followed by reminder on 16.12.2019. Reply received on 03.01.2020, file is submitted to Min. on 20.01.2020. File returned back to the Min with certain observations reg. calculation of space, cost per sq. ft., cost benefit analysis etc. which where conveyed to the Comm'te on 11.03.2020. Reminder sent on 05.06.2020. |  | IFU query
7 | Bhopal CGST | CGST Raipur/ 916/4/Const./Raipur/HRD/17 | Construction of office building and residential quarters at Rajnandgaon. | CBIC/ CPWD | 2.8 | Yes |  | Proposal for purchase of land sanctioned by competent authority on 17.04.2017. | Proposal received on 12.09.2017 and submitted to Min. for a/a & e/s on 17.07.2019. IFU returned the file with certain queries which were conveyed to Comm'te on 18.09.19. Pr. Commr., Raipur had visited in DGHRD on 16.12.2019 to discuss the project status. Reminder sent on 15.06.2020. |  | IFU query
8 | Bhubaneshwar CGST | Bhubaneswar/ 916/12/Const. /Bhubaneswar/ HRD/14 | Const. of Retaining wall and Approach Road and from the main road to the office plot at Bagbrindaban Mauja of Balasore Town in state of Odisha. | CBIC/ CPWD | 1.57 | No | ____ | Original proposal received in September 2014. Query letter sent on 29.12.2014, 03.12.2015 & 23.08.2016. followed by several reminders. | CPWD has submitted a revised P.E for Rs 1.57 Cr. while examining the proposal DG, HRD has raised some queries, based on the reply/clarifications submitted by Comm'te proposal forwarded to the MInistry for a/a & e/s on 26.12.2019. File received back from the Min. with certain observations reg.ofice space, approach road etc. letter communicated to Comm'te on 14.02.2020. Reminder sent on 11.06.2020. |  | IFU query
9 | Chennai Cus. | Chennai Customs/ 916/12/Const/Jaffer Syarang-Chennai/HRD/19 | Construction of office accomodation building for Partner Govt. Agencies, Chennai Customs Audit and Import Comm'te at Jaffer Syarang Street, Chennai. | CBIC/ CPWD | 86.75 |  |  |  | Proposal was received in July, 2019. IFU has raised observations reg. existing carpet area, shortage of space etc. and the same were conveyed to the comm'te on 30.10.19 Reply received and the file submitted to the Min. and IFU returned the file with certain observations and the same were communicated to the Commissionerate on 04.05.2020. File is submitted to Ministry 24.06.2020. |  | IFU query
10 | Guwahati CGST | CGST Dibrugarh 916/4/Const./ Shillong/HRD/15 | Construction of office cum residential qtrs. at Dibrugarh. Total office space: 3562 sqm. Total quarters: 56 (Type-II 14, Type-III 28 & Type-IV 14) | CBIC/ CPWD | 60.37 | No | ____ | Original proposal received on 04.09.2015. Deficiency letter sent on 22.09.2015 followed by several reminders. Do letter to forward consolidated proposal sent on 22.03.2017. | The proposal was submitted to the Ministry on 21.05.2018. IFU had made some observations regarding budget head, cost index, carpet area and the same were conveyed to Comm'te on 12.09.19. Incomplete reply received Comm'te vide letter dated 14.01.2020 again requested to submit a proper reply. Reminder sent on 11.06.2020. |  | IFU query
11 | Guwahati CGST | CGST Imphal 916/3/Const./Shillong/HRD/19 | Const. of office building and boundary wall at Lamphel at Imphal Shillong | CBIC/CPWD | 46.4 |  |  |  | Proposal was received on 16.09.2019. In the meantime, a reference was received from Sh. Bhabananda Singh, M.P. (Rajya Sabha) for allotting this work to MANIDCO. Matter was got clarified from the Comm'te and based on the report proposal was process for awarding the work to State PWD accordingly, the proposal was forwarded to Min. for a/a & e/s on 07.01.2020. File returned back to the Min. with certain observations reg. revenue collection,cost benefit analysis, built up area, per sq.ft. cost of const. communicated to the Comm'te on 05.03.2020. Reminder sent on 05.06.2020. |  | IFU query
12 | Hyderabad CGST | Secunderabad/ 916/13/Const./ Hyderabad/HRD/15 | Completion of 287 unfinished Dept. qtrs taken over from M/s Sri Durga Estate Pvt. Ltd. at Hyderabad | CBIC/ NBCC | 49.75 | Yes | MoU has been approved by Ministry. 287 Qtrs. in dilapidated condition will become habitable on the nominal cost of Rs. 21.3 Cr. (approx.) | Original proposal received on 02.11.2015.Miinistry gave concurrence to appoint NBCC as PMC on 24.12.2015. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Ministry had returned the file with certain observations reg. project status which was conveyed to comm'te on 21.05.19. D.O. letter from DG,HRD issued on 13.03.20 follwed by reminder dated 18.05.20 & 29.06.20. Reply awaited. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Funds released on 20.09.2018. | IFU query
13 | Jaipur CGST | CGST Jaipur 916/2/Const. Jaipur/HRD/19 | Dismantling and reconstruction of T-VI/3 Bunglow at C.Ex. Officers residence colony, JLN Marg, Jaipur | CBIC/ CPWD | 2.07 |  |  |  | Proposal for const. of RCC wall sanctioned on 09.01.2020 (partly sanctioned). Acoordingly, Rs. 10.00 lakh released on 27.01.2020. Proposal for demolition of the existing flat sanctioned on 19.05.2020 (partly sanctioned). Further IFU made observations reg. demand survey of residential quarters, which are conveyed to the Comm'te on 19.03.2020. |  | IFU query
14 | Lucknow CGST | CGST Agra/Lucknow /916/5/Const./Aligarh/HRD/19 | Const. of new office building for CGST Division at Aligarh. | CBIC/CPWD | 11.34 |  |  |  | File has been submitted to the Min. on 22.05.2019. File returned from the Ministry with certain observations reg. space requirement, cost of const. etc.and the same were conveyed to the Comm'te on 27.06.2019. File submitted to the Ministry on 20.02.2020 and observations made by IFU were communicated to comm'te on 11.05.2020 |  | IFU query
15 | Pune CGST | CGST Goa/ 916/1/Const./Goa/HRD/2019 | Redevelopment of 52 nos. of staff quarters and community centre for CGST Goa Commissionerate, Goa at Alto-porvorim | CBIC /CPWD | 27.16 |  |  |  | Fresh proposal received and raised the queries by DGHRD letter sent on 24.09.19. File is submitted to the Min. on 08.01.2020. File receievd back from IFU with certain observations reg. GRIHA norms, cost of const. of per flat, cost index etc., which have been conveyed to the Comm'te on 28.02.2020. Reminder sent on 05.06.2020. |  | IFU query
16 | Pune CGST | CGST Kolhapur/ 916/21/Const. /Pune/HRD/14 | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur-reg. Land area: 12854.8 sqm. Office space : 9244.1 sqm. | CBIC/ CPWD | 42.44 | No | ____ | Original proposal received in March 2015. Query letter sent on 10.04.2015 followed by several reminders. | Proposal was received on 25.01.2019 and file was submitted to the Ministry. IFU vide note dt. 31.12.2019 has made some observations reg. FSI, plinth area, car parking space etc. which have been conveyed to the Comm'te on 14.01.2020. Reply received of IFU queries and file is submitted to the Min. on 13.02.2020 for a/a & e/s. |  | IFU query
17 | Visakhapatnam CGST | CGST Guntur/ 916/11/Const./Guntur/HRD/18 | Construction of office building at Eluru (A.P.) | CBIC / CPWD | 6.95 |  |  | Not Sanctioned | File was submitted to the Ministry and IFU made observations regarding provision of funds, permissible FAR etc. which were conveyed to the Comm'te. File was re-submitted with replies. However, IFU made observations regarding plinth area, feasibility of construction for given sanctioned strength, etc., based on the reply received from Comm'te on 03.01.2020, file re-submitted to Min. on 14.01.2020. File returned to the Min. with certain queries reg. per sq. ft. cost, layout plan etc. & also dropped the proposal which were conveyed to the Comm'te on 05.03.2020. Reminder sent on 05.06.2020. |  | IFU query
18 | Visakhapatnam CGST | Cus. (P.), Vijaywada 916/15/Const./Visakhapatnam/HRD/16 | Const. of buildings for newly formed Customs Comm'te (P.), Vijaywada-HQRS. Office Complex and Residential Quarters at Sy. No. 29/8 (3.84 acres) of Kesarpally Village of Gannavaram Mandal of Krishna Dist. Andhra Pradesh | CBIC / NBCC | 65.49 |  |  | Not Sanctioned | Revised proposal received on 01.03.2019, proposing to award this work to NBCC certain clarifications were sought by DGHRD whcih were conveyed to Comm'te after receiving the reply from the Comm'te on 22.05.2019, the proposal was submitted to Min. for a/a & e/s. But Member (Admn.) returned the file and asked to Comm'te to get in writing a letter from CPWD showing their inability before awarding this work to NBCC. Reminder sent on 31.01.2020. Comm'te had informed that CPWD is willing to under take the work accordingly, it was advise on 08.05.2020 to get it fresh PE from CPWD. Reminder sent on 29.06.2020. |  | IFU query
19 | DRI Delhi | DRI (HQ), 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of office building for DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 88.46 |  |  |  | Proposal received on 23.03.2020. File submitted to the Ministry for approval on 24.04.2020. File received back to Min. with certain queries and the same were conveyed to Comm'te on 29.06.2020. |  | IFU query
20 | Ahmedabad CGST | CGST Ahmedabad (Audit) 916/13/Const./Ahmedabad/HRD/2019 | Construction of office premises on land measuring 3972.22 sqm. of final plot No. 175 of TP No. 3 of the commissioner of CGST (Audit), Ahemedabad. | CBIC | 75 |  |  |  | Proposal was received on 15.07.19 alongwith two PEs (CPWD & NBCC). DGHRD raised certain queries reg. non.encumbrance certificate etc. and the same were conveyed to the Comm'te on 26.12.2019. Reply received and file submitted to the Min. 01.05.2020. File returned to the MInistry with certain observations and the same were conveyed to the Comm'te on 03.06.2020. |  | IFU has turned down the proposal
21 | Bengaluru CGST | Belgavi / 916/8/Const./Belgaum/ HRD/13 | Construction of office building and staff quarters at Belgaum (Gulbarga Division)-reg. Office space: 191.16 sqm. Total Quarters =04 Type II=01 Type III=02 Type IV= 01 | CBIC/ CPWD | 3.36 | No | ____ | Original proposal received on 11.02.2013. Deficiency letter sent on 05.04.2013 followed by several reminders. Revised proposal received on 27.12.2016. Query letter sent on 10.03.2017. | Revised proposal received on 28.01.2019. While examining the proposal DGHRD has sought some clarifications which were conveyed to the Comm'te 19.09.2019. Reply received, file submitted to the Ministry on 19.03.2020. IFU returned the file with certain observation which were conveyed to the Comm'te on 03.06.2020. |  | IFU has turned down the proposal
22 | DRI | DRI Chennai 916/02/Const./DRI Chennai/HRD/2020 | Construction of office building of DRI Zonal Unit at Trustpuram Kodambakkam, Chennai | CBIC/ CPWD | 31.38 |  |  |  | Proposal received on 05.02.2020. File was submitted to the Ministry for approval on 16.03.2020. IFU has returned the file on 13.05.2020 advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to DRI Chennai letter dated 26.05.2020. |  | IFU has turned down the proposal
23 | NACIN | NACIN Chennai 916/5/Const./ Chennai/ HRD/ 15 | Const. of NACIN Complex at Nolambur, Chennai-reg. | CBIC/ UPRNN | 79.8 | No | ___ | Land measuring 3.26 acre was acquired in 16.02.2015. Formal proposal awaited. | File was submitted to the Ministry for approval on 04.03.2020. IFU has returned the file on 06.05.2020 advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. Further, it has advised to utilize the existing NACIN/RTI premises for training purposes. |  | IFU has turned down the proposal
24 | Pune CGST | Goa Cus. 916/10/Const./Goa/HRD/17 | Construction of addl. staff quarters for Customs Department at Customs Colony, Headland Sada, Marmagoa, Goa. | CBIC/ CPWD | 37.28 |  |  |  | Proposal for demolition of dilapidated RCC overhead tank sanctioned on 16.01.2020. Acoordingly, Rs. 2,39,000/- released on 27.01.2020. Further IFU vide note dated 06.12.2019 raised certain queries reg. demand survey, justification of joggers park etc. and the same were communicated to the Comm'te on 12.12.2019. Based on the reply received from teh Comm'te file is submitted to the Min. on 27.04.2020. In view of limited fund availability IFU has turned down the proposal. Conveyed to Comm'te on 08.06.2020. |  | IFU has turned down the proposal
25 | Visakhapatnam CGST | CGST Tirupati/ 916/06/Const./Tirupati/HRD/2015 | Construction of office building and staff quarters at Tirupati | CBIC / CPWD | 57.06 |  |  | Not Sanctioned | Revenue Secretary on 22.06.2017 made observations regarding PPP Model, Cost benefit analysis etc. Comm'te withdrew the proposal. Revised proposal has been received and after submission to Min. file returned by the IFU with ceratin queries which were conveyed to Comm'te on 18.09.19. Further, based on the reply received from the Comm'te file re-submitted to the Min. on 22.11.19. Revenue Secretary upon discussing the proposal with FA has disagreed the proposal. The same were conveyed to the Comm'te on 16.03.2020. |  | RS has turned down the proposal