## Updated const. list
Total Construction Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad CGST | CGST Ahmedabad (Audit) 916/13/Const./Ahmedabad/HRD/2019 | Construction of office premises on land measuring 3972.22 sqm. of final plot No. 175 of TP No. 3 of the commissioner of CGST (Audit), Ahemedabad. | CBIC | 75 |  |  |  | Proposal was received on 15.07.19 alongwith two PEs (CPWD & NBCC). DGHRD raised certain queries reg. non.encumbrance certificate etc. and the same were conveyed to the Comm'te on 26.12.2019. Reply received and file submitted to the Min. 01.05.2020. IFU has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te on 03.06.2020. |  | IFU has turned down the proposal
2 | Ahmedabad CGST | CGST Bhavnagar / 916/21-A/Const./Bhavnagar/HRD /11 | Construction of office building at Bhavnagar Total land- 7104 sqm. Office space-4807.50 sqm. | CPWD/ CPWD | 40.61 | Yes | Project in advanced stage and funds will be provided by CPWD. | Original proposal received on 16.01.2014. Query letter sent on 04.03.2014 & 22.12.2014. Reply received on 19.11.2014 & 17.10.2016. File submitted to the Ministry on 09.01.2017 & 12.05.2017. | Project sanctioned on 30.08.2017. But due to change in PAR 2019. A revised proposal has been forwarded by the Comm'te, which has been submitted to the Min. for a/a & e/s of the increase amount on 26.02.2020. FA upon consulation with RS has advised to keep the proposal in abeyance for the time being. |  | IFU query
3 | Ahmedabad Cus. | Jamnagar Cus./ 916/17/Const./Jamnagar (Res.)/HRD/19 | Construction of Staff quarters at Jamnagar | CBIC/CPWD | 18.86 |  |  |  | Proposal received on 09.09.19. Savings of HRA of the staff/officers has not informed accordingly query letter issued on 09.10.19. Reply recvd on 29.10.19, DGHRD sought some further clarification which were replied by the Comm'te on 06.12.19 & 06.01.2020. File submitted to the Min. on 17.01.2020. File returned back to Min. with certain observations reg.cost of const. per flat, area of quarters etc. communicated to the Comm'te on 05.03.2020. Reminder sent on 11.06.2020, 13.07.2020. |  | IFU query
4 | Bengaluru CGST | Belgavi / 916/8/Const./Belgaum/ HRD/13 | Construction of office building and staff quarters at Belgaum (Gulbarga Division)-reg. Office space: 191.16 sqm. Total Quarters =04 Type II=01 Type III=02 Type IV= 01 | CBIC/ CPWD | 3.36 | No | ____ | Original proposal received on 11.02.2013. Deficiency letter sent on 05.04.2013 followed by several reminders. Revised proposal received on 27.12.2016. Query letter sent on 10.03.2017. | Revised proposal received on 28.01.2019. File submitted to the Ministry on 19.03.2020. IFU has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te on 03.06.2020. |  | IFU has turned down the proposal
5 | Bengaluru Cus | Customs (Airport) Bengaluru/ 916/16/Const./ Bengaluru/HRD/ 2019 | Construction of new customs House Building at bengaluru International Airport | CBIC/CPWD | 57.37 |  |  |  | Fresh proposal was received in October, 2019 and queries reg. calculation of office space, per sq.ft. Cost, cost benefit analysis etc. conveyed to the Comm'te on 14.10.19. After clarifications, file was submitted to Min. on 20.01.2020. File returned back by the Min. with certain observations reg. calculation of space, cost per sq. ft., cost benefit analysis etc. which where conveyed to the Comm'te on 11.03.2020. Followed by reminders on 05.06.2020, 09.07.2020. Reply received and file sent to Ministry on 13.08.2020 for approval. |  | With Ministry
6 | Bhopal CGST | CGST Raipur/ 916/4/Const./Raipur/HRD/17 | Construction of office building and residential quarters at Rajnandgaon. | CBIC/ CPWD | 2.8 | Yes |  | Proposal for purchase of land sanctioned by competent authority on 17.04.2017. | Proposal received on 12.09.2017 and submitted to Min. for a/a & e/s on 17.07.2019. IFU returned the file with certain queries which were conveyed to Comm'te on 18.09.19. Pr. Commr., Raipur had visited in DGHRD on 16.12.2019 to discuss the project status. Reminder sent on 15.06.2020, 13.07.2020. |  | IFU query
7 | Bhubaneshwar CGST | Bhubaneswar/ 916/12/Const. /Bhubaneswar/ HRD/14 | Const. of Retaining wall and Approach Road and from the main road to the office plot at Bagbrindaban Mauja of Balasore Town in state of Odisha. | CBIC/ CPWD | 1.57 | No | ____ | Original proposal received in September 2014. Query letter sent on 29.12.2014, 03.12.2015 & 23.08.2016. followed by several reminders. | CPWD has submitted a revised P.E for Rs 1.57 Cr. while examining the proposal DG, HRD has raised some queries, based on the reply/clarifications submitted by Comm'te proposal forwarded to the MInistry for a/a & e/s on 26.12.2019. File received back from the Min. with certain observations reg.ofice space, approach road etc. letter communicated to Comm'te on 14.02.2020. Reminder sent on 11.06.2020, 13.07.2020. |  | IFU query
8 | Chennai Cus. | Chennai Customs/ 916/12/Const/Jaffer Syarang-Chennai/HRD/19 | Construction of office accomodation building for Partner Govt. Agencies, Chennai Customs Audit and Import Comm'te at Jaffer Syarang Street, Chennai. | CBIC/ CPWD | 86.75 |  |  |  | Proposal was received in July, 2019. After three rounds of observations by IFU. The file re-submitted to the Ministry on 24.06.2020. IFU has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te, Cus. Chennai on 21.07.2020. |  | IFU query
9 | DRI | DRI Chennai 916/02/Const./DRI Chennai/HRD/2020 | Construction of office building of DRI Zonal Unit at Trustpuram Kodambakkam, Chennai | CBIC/ CPWD | 31.38 |  |  |  | Proposal received on 05.02.2020. File was submitted to the Ministry for approval on 16.03.2020. IFU has returned the file on 13.05.2020 advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to DRI Chennai letter dated 26.05.2020. |  | IFU has turned down the proposal
10 | DRI Delhi | DRI (HQ), 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of office building for DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 88.46 |  |  |  | Proposal received on 23.03.2020. File submitted to the Ministry for approval on 24.04.2020. File received back from the Min. with certain queries and the same were conveyed to Comm'te on 29.06.2020. Reminder sent on 27.07.2020. Reply received on 10.08.2020 and file submitted to Ministry on 25.08.2020. |  | With Ministry
11 | Guwahati CGST | CGST Dibrugarh 916/4/Const./ Shillong/HRD/15 | Construction of office cum residential qtrs. at Dibrugarh. Total office space: 3562 sqm. Total quarters: 56 (Type-II 14, Type-III 28 & Type-IV 14) | CBIC/ CPWD | 60.37 | No | ____ | Original proposal received on 04.09.2015. Deficiency letter sent on 22.09.2015 followed by several reminders. Do letter to forward consolidated proposal sent on 22.03.2017. | The proposal was submitted to the Ministry on 21.05.2018. IFU had made some observations regarding budget head, cost index, carpet area and the same were conveyed to Comm'te on 12.09.19. Incomplete reply received Comm'te vide letter dated 14.01.2020 again requested to submit a proper reply. Reminder sent on 16.07.2020. Revised proposal is awaited from the Comm'te. |  | IFU query
12 | Guwahati CGST | CGST Imphal 916/3/Const./Shillong/HRD/19 | Const. of office building and boundary wall at Lamphel at Imphal Shillong | CBIC/CPWD | 46.4 |  |  |  | Proposal was received on 16.09.2019. In the meantime, a reference was received from Sh. Bhabananda Singh, M.P. (Rajya Sabha) for allotting this work to MANIDCO. Matter was got clarified from the Comm'te and based on the report proposal was process for awarding the work to State PWD accordingly, the proposal was forwarded to Min. for a/a & e/s on 07.01.2020. File returned back to the Min. with certain observations reg. revenue collection,cost benefit analysis, built up area, per sq.ft. cost of const. communicated to the Comm'te on 05.03.2020. Last reminder sent on 09.07.2020 |  | IFU query
13 | Hyderabad CGST | Secunderabad/ 916/13/Const./ Hyderabad/HRD/15 | Completion of 287 unfinished Dept. qtrs taken over from M/s Sri Durga Estate Pvt. Ltd. at Hyderabad | CBIC/ NBCC | 49.75 | Yes | MoU has been approved by Ministry. 287 Qtrs. in dilapidated condition will become habitable on the nominal cost of Rs. 21.3 Cr. (approx.) | Original proposal received on 02.11.2015.Miinistry gave concurrence to appoint NBCC as PMC on 24.12.2015. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Ministry had returned the file with certain observations reg. project status which was conveyed to comm'te on 21.05.19. D.O. letter from DG,HRD issued on 13.03.20 follwed by reminders dated 18.05.20, 29.06.20 & 23.07.2020. Reply awaited. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Funds released on 20.09.2018. | IFU query
14 | Jaipur CGST | CGST Udaipur 916/1/Const./HRD/2018 | Proposal for repair/renovation and upgradation of staff houses at Udaipur. | CBIC / CPWD | 25.56 |  |  | Not Sanctioned | Fresh proposal was received on 08.04.2019 IFU has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te, Udaipur letter dated 06.07.2020. |  | IFU turned down the proposal
15 | Jaipur CGST | CGST Jaipur 916/2/Const. Jaipur/HRD/19 | Dismantling and reconstruction of T-VI/3 Bunglow at C.Ex. Officers residence colony, JLN Marg, Jaipur | CBIC/ CPWD | 2.07 |  |  |  | Proposal for const. of RCC wall sanctioned on 09.01.2020 (partly sanctioned). Revalidation sought on 17.08.2020. Proposal for demolition of the existing flat sanctioned on 19.05.2020 (partly sanctioned). Comprehensive reply to IFU observations pertaining to reconstruction is awaited, letter sent to Comm'te for same on 31.07.2020. |  | With Ministry
16 | Lucknow CGST | CGST Agra/Lucknow /916/5/Const./Aligarh/HRD/19 | Const. of new office building for CGST Division at Aligarh. | CBIC/CPWD | 11.34 |  |  |  | File has been submitted to the Min. on 22.05.2019. File submitted to the Ministry on 20.02.2020 and observations made by IFU were communicated to comm'te on 11.05.2020. Reminder sent on 20.08.2020. |  | IFU query
17 | NACIN | NACIN Chennai 916/5/Const./ Chennai/ HRD/ 15 | Const. of NACIN Complex at Nolambur, Chennai-reg. | CBIC/ UPRNN | 79.8 | No | ___ | Land measuring 3.26 acre was acquired in 16.02.2015. Formal proposal awaited. | File was submitted to the Ministry for approval on 04.03.2020. IFU has returned the file on 06.05.2020 advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. Further, it has advised to utilize the existing NACIN/RTI premises for training purposes. |  | IFU has turned down the proposal
18 | Nagpur CGST | CGST Nagpur-I 916/18/Const./Nagpur/HRD18 | Const. of 6 nos. of T-VI qtrs.for Central Excise at B.No. 12, Seminary Hills, Nagpur Internal Water Supply, Sanitary Installation, Drainage and Internal Electrical Works involving an expenditure of Rs. 734.63 lakhs. | CBIC / CPWD | 7.35 |  |  | Not Sanctioned | Proposal received and submitted to the Min. on 15.07.19 for approval. IFU has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to CC Nagpur letter dated 06.07.2020. |  | IFU has turned down the proposal
19 | Pune CGST | CGST Goa/ 916/1/Const./Goa/HRD/2019 | Redevelopment of 52 nos. of staff quarters and community centre for CGST Goa Commissionerate, Goa at Alto-porvorim | CBIC /CPWD | 27.16 |  |  |  | File was submitted to the Min. on 08.01.2020. File receievd back from IFU with certain observations reg. GRIHA norms, cost of const. of per flat, cost index etc., which were conveyed to the Comm'te on 28.02.2020. Last reminder sent on 09.07.2020. |  | IFU query
20 | Pune CGST | Goa Cus. 916/10/Const./Goa/HRD/17 | Construction of addl. staff quarters for Customs Department at Customs Colony, Headland Sada, Marmagoa, Goa. | CBIC/ CPWD | 37.28 |  |  |  | Proposal for demolition of dilapidated RCC overhead tank sanctioned on 16.01.2020. Acoordingly, Rs. 2,39,000/- released on 27.01.2020. In view of limited fund availability due to COVID-19 pandemic IFU has turned down the main construction proposal. Conveyed to Comm'te on 08.06.2020. Revalidation of Rs. 2,39,000/-, approved on 20.08.2020. | Rs. 2,39,000/- released on 27.08.2020. | IFU has turned down the proposal
21 | Visakhapatnam CGST | CGST Guntur/ 916/11/Const./Guntur/HRD/18 | Construction of office building at Eluru (A.P.) | CBIC / CPWD | 6.95 |  |  | Not Sanctioned | File was submitted to Min. for approval on 14.01.2020. File returned by the Min. with certain queries reg. per sq. ft. cost, layout plan etc. & has also dropped the proposal due to very less rental outgo at present which were conveyed to the Comm'te on 05.03.2020. Reminder sent on 05.06.2020. |  | IFU has turned down the proposal
22 | Visakhapatnam CGST | CGST Tirupati/ 916/06/Const./Tirupati/HRD/2015 | Construction of office building and staff quarters at Tirupati | CBIC / CPWD | 57.06 |  |  | Not Sanctioned | Earlier, Revenue Secretary on 22.06.2017 made observations regarding PPP Model, Cost benefit analysis etc. Comm'te withdrew the proposal. Revised proposal was submitted to the Ministry and Revenue Secretary upon discussing the proposal with FA has disagreed the proposal. The same were conveyed to the Comm'te on 16.03.2020. Tirupati Comm'te vide letter dated July, 2020 stated that to protect the land from encrochment & returning of land to State Govt. urgent need of const. of boundary wall is felt. Letter sent to Comm'te on 06.07.2020 requesting to submit seprate PE for boundary wall at the earliest. |  | RS has turned down the proposal
23 | Visakhapatnam CGST | Cus. (P.), Vijaywada 916/15/Const./Visakhapatnam/HRD/16 | Const. of buildings for newly formed Customs Comm'te (P.), Vijaywada-HQRS. Office Complex and Residential Quarters at Sy. No. 29/8 (3.84 acres) of Kesarpally Village of Gannavaram Mandal of Krishna Dist. Andhra Pradesh | CBIC / NBCC | 65.49 |  |  | Not Sanctioned | Revised proposal received on 01.03.2019, proposing to award this work to NBCC the proposal was submitted to Min. for a/a & e/s. While perusing Member (Admn.) returned the file and asked to Comm'te to get in writing a letter from CPWD showing their inability before awarding this work to NBCC. Comm'te had informed that CPWD is willing to under take the work accordingly, it was advised on 08.05.2020 to get it fresh PE from CPWD. Last reminder sent on 21.07.2020. |  | IFU query