## Sanctioned projects (hidden)
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad CGST | CGST Ahmedabad (North)/ 916/8/Const./ Ahmedabad/HRD/17 | Construction of new building in the Custom House Compound, Ahmedabad. | CBIC/ CPWD | 31.87 |  |  |  | Project sanctioned on 11.06.2018. File submitted to Ministry for revalidation on 25.08.2020. IFU returned the file with certain observations, the same communicated to the Comm'te on 17.09.2020. | Rs. 5.00 cr. was released in F.Y. 2018-19, Comm'te has surrendered Rs. 4.75 cr. During F.Y. 2019-20 Rs. 2.00 cr. released on 20.08.2019. | Sanctioned
2 | Ahmedabad Cus. | Cus. (Prev.), Jamnagar/ / 916/8/Const./ Jamnagar/HRD/16 | Construction of office building at Jamnagar Total land- 10,250 sqm. Office space- 4131.34 sqm. | CBIC/ CPWD | 43.67 | Yes | Project in advanced stage |  | Project sanctioned on 13.12.2017. Revalidation approved on 03.06.2020 | Rs. 15.00 Cr. were released in 2018-19 out of which 4.00 were utilized. Rs. 7.00 Cr. were released in 2019-20 out of which 6.78 Cr. has been utilized till Nov, 2019. Addl. Rs. 5.00 Cr. revalidated from Min. and released on 17.02.2020. Rs. 12.74 Cr.released on 16.06.2020 in F.Y. 20-21. | Sanctioned
3 | Ahmedabad Cus. | Cus. Jamnagar (dwarka) 916/17/Const./Ahmedabad/HRD/18 | Construction of office building at the site of shore guard, Dwarka, Jamnagar. | CBIC/CPWD | 1.24 |  |  |  | File sanctioned on 04.03.2020. Revalidation approved on 12.06.2020. | Rs. 50.00 lakh released on 06.07.2020 in F.Y. 2020-21 | Sanctioned
4 | Bengaluru CGST | CGST, Belgavi/ Bengaluru / 916/15/Const. /Belgaum/ HRD/12 | Construction of office building and staff quarters for Bagalkot Range and Range D of Vijaypura Division under Belagavi CGST Comm'te Total land-01 acre Office space-1080 sqm. Residential space-465 sqm. Total qtrs.-02 Type wise qtrs.- Type-III=01 Type-IV=01 | CBIC/ CPWD | 2.19 | Yes | Project in advanced stage. Land worth Rs. 7-8 cr. which was provided free of cost will be taken back by Town Development Authority in case of non-construction.. |  | Project sanctioned on 10.01.2018. Revalidation approved by IFU on 18.09.2020 . | Rs. 5.00 lakh released on 16.01.18 & Rs. 15.00 lakhs on 12.02.2018 but could not utilized. Rs. 20.00 lakh again released on 20.08.2018, Rs. 199.03 lakhs released on 01.11.2018. Rs. 1.03 released on 31.5.2019 | Sanctioned
5 | Bengaluru Cus | Mangalore Custom/ 202/7/2003 Ad. VIII (EC) | Providing Barbed wire fencing and Name Boards to properties belonging to Customs Department at Karwar, for Rs. 89,56,000. | CBIC/ CPWD | 0.89 | Yes | The said land is required to be protected from encroachment and this is a small project. | Original proposal received on 25.05.2016. File submitted to the Ministry on 10.11.2016, 18.01.2017 &12.05.2017. | Project sanctioned on 15.09.2017. Reasons for delay in the project sought from the Comm'te vide DG,HRD D.O. letter dated 09.09.2020. In the meanwhile , file submitted to Ministry for revalidation on 21.09.2020. | Rs. 83,44,052/- were released in 2017-18, out of which Rs. 6,11,948/- utilized in 2017-18 & Rs. 14,21,578/- utilized in 2018-19. Further, Rs. 75,34,422/- released on 12.07.2019 | With Ministry
6 | Chandigarh CGST | CGST Jalandhar/ 916/09/Const./ Jalandhar/ HRD/16 | Construction of office cum residential qtrs.and boundary wall at Jalandhar Total land - 06 acre Total qtrs.- 116 Type wise qtrs.- Type-II=19 Type-III=62 Type-IV =32 Type-V A=01 Type-V B=01 Type-VI=01 | CPWD/ CPWD | 67.57 | Yes | Project approved by IFU. Non-construction fee will accrue if construction not started | Original proposal received on 06.09.2016. Query letter sent on 16.09.2016. Reply received on 17.11.2016.File submitted to the Ministry on 18.11.2016, 20.12.2016, 03.02.2017, 27.02.2017, 03.04.2017, 14.06.2017 & 28.07.2017. | Project was sanctioned on 4.8.2017 and being executed through MoUD funds. During the visit to Chandigarh on 06.12.2019 JD (I&W) had reviewed the project status and found to be satisfactory. |  | Sanctioned
7 | Chandigarh CGST | Jammu 916/4/Const./Srinagar/HRD/2020 | Construction of boundary wall with concertina wire fencing around the land at Solina, Srinagar for construction of office and residential buildings of Customs & CGST Division, Srinagar | CBIC/CPWD | 4.14 |  |  |  | Proposal sanctioned on 31.07.2020. File sent to Ministry for concurrence to release funds on 17.08.2020. IFU returned the file seeking certain information, same communicated to the Comm'te on 31.08.2020. |  | Sanctioned
8 | Chennai Cus. | Chennai Cus. (Gen.) VIII / 916/03/Const./Chennai/RD/ 16 | Construction of residential qtrs. at Anna Nagar, Chennai. Total land- 1,06,086 sqm. Total qtrs.-726 Type wise qtrs.- Type-II=288 Type-III=288 Type-IV=150 | CBIC/ CPWD | 348.77 | Yes | Project approved by IFU. Presentation to be made in front of the RS | Original proposal received in Feb. 2016. .File submitted to the Ministry on 29.04.2016, 21.11.2016, 03.01.2017, 26.04.2017 & 14.08.2017. | Project sanctioned on 13.10.2017. Revalidation approved on 03.06.2020. | Rs. 30.00 cr. released in 2018-19 out of which Rs. 12.00 cr. utilized. Rs. 20.00 Cr. were released on 24.07.2019. Addl. amount of Rs. 15.00 cr. sought in RBE 2019-20 has been released on 27.01.2020. Rs. 67.00 Cr. released on 16.06.2020 in F.Y. 20-21. | Sanctioned
9 | Chennai Cus. | Chennai Cus. (Gen.)/ 916/08/Const./Chennai/HRD/2018 | Construction of 36 residential quarters at Nungambakkam, Chennai | CBIC / CPWD | 65.42 |  |  | Sanctioned | Project sanctioned. Revised proposal submitted to Min. on 17.01.2020. Revalidation approved on 03.06.2020. | Rs. 5.00 Cr. were revalidated for F.Y. 2019-20 and released on 31.05.2019. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21 | Sanctioned | AS & FA
10 | Delhi CGST | CGST, Delhi (North)/ 916/03/Const./ Dwarka/HRD/17 | Construction of residential qtrs. at Dwarka Total land- 17832 sqm. Total qtrs.-256 Type wise qtrs.- Type-IV=168 Type-V=52 Type-VI=36 | CBIC/ NPCC | 227 | No | ____ | This is a very old proposal. Due to deficiencies in the bidding process Revenue Secretary advised for fresh bidding on 03.04.2017. Commissionerate invited tender along with RFP on 27.04.2017. Revised proposal received on 16.06.2017. | Project sanctioned on 25.07.2018. . File is submitted to the Ministry on 06.07.20 for revalidation. IFU raised an observation reg. non-utilization of funds by NPCC in F.Y. 2019-20, same conveyed to the Comm'te on 21.07.2020. Revalidation approved by IFU, file submitted to Commr. (Coord.) on 21.09.2020 for issuance of S.O. | Rs. 3.00 Cr. released on 27.07.2018 and Rs. 30.00 Cr. released on 26.02.2019 in F.Y. 2018-19. Further Rs. 26.50 Cr. released on 16.08.2019. | With Ministry | AS & FA
11 | Delhi CGST | Delhi (South)/ 916/62/Const./Nangal Raya/HW/06 | Construction of office building at Nangal Raya, New Delhi. | CBIC/ NBCC | 32.83 |  |  |  | Proposal sanctioned on 13.06.2016. Complete amount has been released to the Comm'te. Comm'te has informed that civil work has almost completed |  | Sanctioned
12 | DRI | DRI Kolkata/ 916/02/Const. /Kolkata/ HRD/2016 | Construction of DRI at Plot No. CBD-93, Action Area-II, New Town, Kolkata | CBIC/ CPWD | 64.5 | ___ |  | Not Sanctioned | Proposal sanctioned on 08.02.2019. Revalidation request for an amount of Rs. 20.00 Cr. approved on 12.06.2020. | Rs.1.49 Cr. have been utilized till F.Y. 2019-20. Rs. 10.00 Cr. released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
13 | DRI | DRI Hyderabad 916/21/Const./DRI/ Hyderabad/ HRD/19 | Construction of office building for DRI Hyderabad Zonal Unit at Jubilee Hills at Hyderabad (Geo Technical Investigation) | CBIC/ CPWD | 0.08 |  |  |  | Proposal sanctioned on 13.03.2020. Comm'te vide letter dated 27.07.2020 has stated that Geo Technical Investigation work will be included in the main construction proposal to be sent shortly. | Rs. 0.08 lakh released on 17.03.2020. | Sanctioned
14 | DRI | DRI Lucknow 916/3/Const./DRI-Lucknow/HRD/2020 | Construction of boundary wall by DRI Zonal Unit, Lucknow | CBIC/CPWD | 0.98 |  |  |  | Proposal sanctioned by the Ministry on 23.03.2020. Revalidation approved on 25.06.2020. | Rs. 98.00 lakh released by EMC on 06.07.2020 in F.Y. 2020-21 | Sanctioned
15 | DRI Delhi | DRI (HQ), 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of boundary wall for DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 0.25 |  |  |  | Proposal sanctioned on 09.10.2019. |  | Sanctioned
16 | Guwahati CGST | CGST, Agartala/ 916/10/Const./ Shillong/HRD/15 | Construction of office building (Audit Circle, Custom division & CGST Division) at Agartala Total land- 3022 sqm. Office space-2793 sqm. Guest House-463 sqm. | CBIC/ CPWD | 28.04 | Yes | Project in advanced stage | Original proposal received on 16.09.2015. Deficiency letter sent on 14.10.2015, 23.03.2016 & 29.08.2016. Reply received on 23.02.2016, 12.08.2016 and 29.05.2017 subsequently. | Proposal sanctioned on 18.02.2019. Revalidation approved on 03.06.2020. | Rs 50 Lakh released on 26.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 1.00 Cr. released on 28.05.2019. Addl. Rs. 3.00 Cr. revalidated from Min. and released on 17.02.2020. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. | Sanctioned
17 | Hyderabad CGST | Hyderabad Cus. 916/14/Const./Hyderabad/HRD/16 | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | CBIC/ CPWD. | 1.3 | No | ____ | Original proposal received on 24.10.2016. File submitted to the Ministry on 14.02.2017, 02.03.2017 & 04.07.2017. Ministry returned the file with observations on 23.02.2017, 10.04.2017 & 28.08.2017. | Proposal sanctioned on 07.03.19. Comm'te vide letter dated 30.07.2020 has stated that demarcation of land is pending and no funds are required till demarcation is completed. | Rs. 10.00 lakhs were released in 2018-19 but could not be utilized Further, Rs. 50.00 lakhs has been released on 29.07.2019. | Sanctioned
18 | Jaipur CGST | Udaipur/ 916/11/Const./ Jaipur-II/HRD/11 | Construction of office building CGST division Bhilwara. Land area: 1858.06 sqm. Office space : 750.00sqm. | CBIC/ CPWD | 9.72 | No | ___ | Original proposal recieved on 08.09.2014. Query letter sent on 31.10.2014, reply recieved on 15.04.2015. Query letter sent on 18.05.2015 followed by several reminders. | Proposal sanctioned on 21.02.2019. Certain discrepencies vis-a-vis the tender cost have been found. Revalidation approved on 25.08.2020. | Rs 1.5 cr have been released on 26.02.2019 but could not be utilized. During 2019-20 Rs. 50.00 lakhs has been released on 25.07.2019. Rs. 3.00 Cr released on 31.08.2020. | Sanctioned | AD VIII
19 | Jaipur CGST | CGST Jodhpur/ 916/19/Const./Jodhpur/HRD/18 | Comprehensive Consultancy Services for Master Planning of Campus & Design of Office cum Residential Campus for CGST at Jodhpur | CBIC/ CPWD | 1.11 |  |  | Not Sanctioned | Proposal for Master planning has been sanctioned on 25.09.2019. Comm'te vide letter dated 27.07.2020 has stated that revalidation/funds is not required for the project for F.Y. 2020-21, till MoU is signed with Income Tax. | In F.Y. 2019-20 Rs. 10.00 lakhs have been released on 01.10.2019. | Sanctioned
20 | Jaipur CGST | CGST Udaipur 916/4/Const./Udaipur/HRD/19 | Construction of new office building for Udaipur CGST Comm'te | CBIC/ CPWD | 42.07 |  |  |  | File sanctioned on 09.03.2020. Revalidation approved on 25.06.2020. | Rs. 10.00 lakh released on 18.03.2020 in F.Y. 2019-20. Rs. 50.00 lakh released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
21 | Lucknow CGST | CGST Agra/ 916/05/Const./Agra/HRD/2018 | Construction of conference hall in the building of CGST Comm'te Agra. | CBIC/ CPWD | 0.12 |  | Proposal is under process at DGHRD |  | Project sanctioned on 13.08.19. Revalidation approved by IFU on 18.09.2020. | In F.Y. 2019-20 Rs. 11,97,143/- have been released on 28.08.2019. | Sanctioned
22 | Meerut CGST | CGST Ghaziabad & 916/5/Const./ Meerut/HRD/17 | Construction of office building including boundary wall and culvert over Nala at allotted land measuring 2.21 acres (8894 sqm.) to CGST Ghaziabad, Audit-II, Ghaziabad, Noida | CBIC/ CPWD | 116.42 |  |  |  | Project sanctioned on 03.10.19. Revalidation approved on 03.06.2020. | Rs. 1.00 cr. released on 14.10.2019 in F.Y. 2019-20. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. | Sanctioned
23 | Mumbai CGST | CGST, Raigad 911/4/Misc./Kharghar/HRD/15 | Construction of residential qtrs. at Kharghar by NBCC. Total land- 20,000.32 sqm. Total qtrs.-187 Type wise qtrs.- Type-II=42 Type-III=70 Type-IV=44 Type-IV (Spl)=20 Type-V=09 Type-VI=02 | CBIC/ NBCC | 110.11 | Yes | Project in advanced stage. |  | File sanctioned on 18.04.2019. Revalidation for an amount of Rs. 22.00 Cr. approved by the Min. on 25.06.2020, subject to condition that utilization certificate for amount released in F.Y. 2019-20 may be taken from NBCC before releasing of any amount in F.Y. 2020-21, same communicated to Comm'te on 06.07.2020 | Rs 5.00 cr. were released on 23.04.2019 and further Rs. 6.011 Cr. released on 07.06.2019. Further, Rs. 10.00 Cr. sought in RBE 2019-20 released on 17.01.2020.Rs 22.00 cr. were released on 27.08.2020. | Sanctioned
24 | Mumbai CGST | CGST Palghar/916/5/Const./ Mumbai/HRD/ 16 | Construction of 3 Div. offices and 14 ranges offices on plot bearing NosP-34 at MIDC, Boisar-reg. | CBIC/ CPWD | 33.25 | No | ____ |  | Proposal sanctioned on 01.07.19. Revalidation approved on 25.06.2020. | Rs. 1.00 Cr. released on 19.07.19. Rs. 5.00 Cr. released on 19.08.2020 in F.Y. 2020-21. | Sanctioned
25 | Mumbai CGST | CGST Thane/ 916/15/Const./Thane/HRD/2018 | Proposal for payment of total station survey and GEO Technical Investigation (Soil Investigation) at Thane | CBIC / CPWD | 0.03 |  |  | Not Sanctioned | Proposal sanctioned on 04.10.2019. Revalidation request awaited from the Comm'te, reminder sent on 13.07.2020. | Fund amounting to Rs. 3,23,363/- released on 16.10.19. | Sanctioned | AS & FA
26 | Mumbai Zone-I | Pr. Comm. Cus.(Gen.) 911/3/Custom Enclave/Mumbai/ HRD/16 | Construction of Office complex and residential quarters at Customs Enclave Plot, Wadala, Mumbai through CPWD at a cost of Rs. 495.5 Cr. for office complex and Rs. 480 cr. For residential complex Office space 30000sqm. Total qtrs. -769 | CBIC/CPWD | 975.72 | Yes | Project is being developed on self-sustaining basis. All the offices of GST Excise, DRI, DGCEI etc. will be relocated in the said project. | This land was given free of cost by the Salt Department 1980's. Due to the construction of roads we now have 46 acres encrochment free land where godowns exist. Initially it was thought that Govt. will pay for the construction which was to be done by CPWD. However, with the approval of Revenue Secretary it has been deceided to nominate NBCC to construct the office building and residential quarters without any cost to the Govt. The cost of construction only is likely to be Rs. 2700 crores. | Proposal Sanctioned on 11.11.2019. Revalidation approved by IFU on 31.07.2020. | Rs. 5.00 Cr. (Rs. 2.50 Cr. for office & Rs. 2.50 Cr. for residence) released on 11.11.2019. Rs. 30.00 Cr. released on 13.08.2020 (Rs.15 Cr. for 4059 & Rs.15 Cr. for 4216). | Sanctioned
27 | Mumbai-II Cus. | Customs (General) JNCH/ 916/17/Const./ Raigad/HRD/16 | Construction of additional office building (G+7) at JNCH NHAVA SHEVA Dist. Raigad-Mumbai Available area - 14900 sqm. Office space - 8551.80 sqm. | CBIC/ CPWD | 90.26 | No | ___ | Original proposal received in nov. 2016. Query letter sent on 13.12.2016 followed by several reminders and DO letters. | Proposal for enabling works (Rs 51 Lakh) was sanctioned in March, 2018. Proposal for office sanctioned on 14.02.2019. Revalidation request awaited from the Comm'te, reminder sent on 13.07.2020. | Rs. 43 lakh for enabling works was released on 19.07.2019. Further due to pending approvals from local authorites Comm'te vide letter dated 10.10.19 has requested not to released in balance amount. | Sanctioned
28 | NACIN | Hyderabad NACIN 916/02/Const./ Hyderabad/ HRD/13 | Construction of RTI, NACIN, at Attapur, Hyderabad Total built up area- 11940 sqm. | CBIC/ NBCC | 46.71 | Yes | Proposal sanctioned on 30.12.2016. | Original proposal received in Jan., 2013 . File submitted to Ministry on 26.02.2014, 10.11.2014, 04.09.2015,18.04.2016 & 23.11.2016. | Project sanctioned on 30.12.2016. The project is being executed by NBCC. The construction work is in full swing. Revalidation request for an amount of Rs. 8.85 Cr. approved on 12.06.2020. | Rs. 37.85 Cr. have been released/utilized till F.Y. 2019-20. Rs. 5.00 Cr. released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
29 | NACIN | RTI Hindupur/ 916/8/Const./ Hindupur/HRD/15 | Construction of New Academy of NACIN at Palasamudram (V), (Hindupur) Ananthpur Dist., Andhra Pradesh-Requirement of funds for construction of compound wall road along the boundary etc. Total land- 500 acre | CBIC/ CPWD | 15.14 | No | ___ |  | Proposal for boundary wall & gate complex involving Rs. 15.14 Cr. was sanctioned on 20.11.18 and proposal for consultancy services involving Rs. 1.15 Cr. was sanctioned on 16.10.19. Revalidation approved on 28.07.2020 for an amount of Rs. 4.85 Cr. for boundary wall. Revised proposal for consultancy services at a cost of Rs. 2.00 cr. submitted to Ministry for approval on 17.08.2020. IFU has returned the file advising to keep the consultancy work in suspension for F.Y. 2020-21, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. | Rs. 7.45 Cr. have been utilized till F.Y. 2019-20. | IFU query
30 | NACIN | NACIN Cochin 916/7/Const./RTI NACIN Munnar/HRD/18 | Const. of RTI NACIN Munnar, Kerala | CBIC / CPWD | 0.03 (Enabling works) 0.93 (For boundary wall) |  |  | Not Sanctioned | Proposal for enabling works sanctioned on 08.01.2019. Revalidation approved on 12.06.2020 | Rs. 2.75 lakh released in F.Y.2019-20 has not been utilized in F.Y. 2019-20. Rs. 2.75 lakhs released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
31 | Patna Cus. | Patna Cus. (Prev.)/ / 916/16/Const./Patna (P)/HRD/2016 | Proposal for construction of Residential complex at Land Customs Station jogbani, a/ a & e/s of Rs.7,99,52,000/- Total qtrs.- 21 Type wise qtrs.- Type-II=7 Type-III=12 Type-IV =02 | CBIC/ CPWD | 7.99 | No | ___ | Original proposal received on 21.11.2016. Query letter sent on 13.12.2016. Reply received, file submitted to the Ministry on 06.02.2017, IFU returned file with certain queries, file resubmitted to ministry after clarifying the queries on 10.08.2017. | Project sanctioned on 11.06.2018. File sent for revalidation on 06.08.2020. IFU returned the file with some queries and the same were conveyed to Comm'te on 27.08.2020. After clarifications, file submitted to Ministry for revalidation on 21.09.2020. | Rs. 4.00 cr. have been released to the Comm'te. Comm'te surrendered Rs 3.5 crore. In F.Y. 2019-20 Rs. 3.99 cr. released on 12.07.19. | With Ministry
32 | Patna Cus. | Patna Cus. (Prev.)/ 916/15/Const./Patna/HRD/14 | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul Total land- 2.74 acre Residential space-5,730 sqm. Total qtrs.-21 Type wise qtrs.- Type-III=06 Type-IV=14 Type-IV (Spl)=01 | CBIC/ CPWD | 11.85 | Yes | Sanctioned | Original proposal received in September 2014. Query letter sent on 17.11.2014, 25.06.2015, 20.07.2015. Reply received on 03.03.2015, 25.08.2015. File submitted to the Ministry on 08.11.2016 and 04.07.2017. | Project sanctioned on 22.09.2017. Revalidation approved on 25.08.2020. | Rs.9.5 cr. have been released to the Comm'te in this F.Y. 2018-19. Rs. 1.34 Cr. utilized in 2018-19. Comm'te had surrendered Rs 7.17 crore. In the current F.Y. 2019-20 Rs. 3.00 Cr. released on 14.08.2019. Rs. 4.00 Cr. released on 31.08.2020. | Sanctioned
33 | Pune CGST | CGST Pune-II/ 916/5/Const./ Pune/ HRD/2014 | Construction of office building and 02 nos. residential quarters for CGST Ranges office at Pandharpur, Distt. Solapur, Maharashtra. Total land : 2230.22 sqm. Office space :146.50 sqm. One quarter Type IV | CBIC/ CPWD | 2.05 | No | ___ | Original proposal received on 25.04.2014. Query letter sent on 27.07.2014, 29.08.2016 & 16.02.2017. followed by several reminders. Reply received on 11.12.2015, 08.02.2016 & 17.02.2017 respectively. | File sanctioned on 23.12.2019. Revalidation approved on 25.06.2020. | Rs. 20.00 lakhs released on 30.12.2019. Rs. 1.31 Cr. released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
34 | Pune CGST | CGST Kolhapur/ 916/21/Const. /Pune/HRD/14 | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur-reg. Land area: 12854.8 sqm. Office space : 9244.1 sqm. | CBIC/ CPWD | 42.44 | No | ____ | Original proposal received in March 2015. Query letter sent on 10.04.2015 followed by several reminders. | Proposal sanctioned on 25.06.2020. File submitted to Ministry on 17.08.2020 for concurrence to release Rs. 3.00 Cr. for enabling works. IFU returned the file seeking certain information, same communicated to the Comm'te on 31.08.2020. |  | Sanctioned
35 | Trichy Cus. | Tuticorin/ 916/19/ Const./ Tuticorin/HRD/14 | Construction of additional residential quarters (T-II, T-III & T-IV) at Port Area, Tuticorin. Total qtrs.- 06 Type wise qtrs.- Type-II=1 Type-III=2 Type-IV =3 | CBIC/ CPWD | 1.62 | Yes | Project in advanced stage. As this is a small project construction will be completed within 1 year. | Original proposal received on 09.11.2014. Query letter sent on 14.11.2014, 30.06.2015, 17.07.2015. File has been submitted to the Ministry on 01.09.2016. | Project sanctioned on 25.08.2017. Revalidation approved on 20.08.2020. Rs. 0.96Cr. Released on 27.08.2020. | F.Y. 2019-20 Released = Rs. 1.47 Cr.Utilized = Rs. 0.52 Cr. Rs. 95.00 lakh were released on 27.08.2020. | Sanctioned
36 | Visakhapatnam CGST | CGST Tirupati/Visakhapatnam/ 916/55/Const./ Anantpur/HRD/ 06 | Construction of office building at Anantapur, Andhra Pradesh. Office space: 1292.70 sqm. | CBIC/ CPWD | 7.07 | No |  | Original proposal received on 06.07.2006.Revised PE received on 11.12.2015.Query letter sent on 28.11.2016, 11.04.2016, 29.07.2016, 14.12.2016 followed by reminders and DO letter dated 25.04.2017. | Proposal sanctioned on 21.12.2018. Revalidation approved by IFU, file submitted to Commr. (Coord.) on 21.09.2020 for issuance of S.O. | F.Y. 2018-19 Released = Rs. 1.00 Cr. F.Y. 2019-20 Released = Rs. 4.06 Cr. | Sanctioned
37 | Visakhapatnam CGST | CGST Tirupati/ 916/4/Const./ Kurnool (A.P.)/HRD/2012 | Construction of 7 Nos. Type-IV Quarters and Guest House for Kurnool (Tirupati Comm’te), Andhra Pradesh-reg. Total Land :606.88 sqm. | CBIC/ CPWD | 3.96 | No | ____ |  | Proposal sanctioned on 10.09.2018. Revalidation approved on 25.06.2020. | F.Y. 2018-19 Released = Rs. 1.18 Cr., Utilized Rs. 20 lakhs. F.Y. 2019-20 Released = Rs. 50.00 lakhs. IFU raised observations on addl. sanction sought, conveyed to the Comm'te F.Y. 2020-21 Released = Rs. 1.97 Cr. (06.07.2020) | Sanctioned | AD VIII

## Ahmedabad CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad CGST | CGST Ahmedabad (North)/ 916/8/Const./ Ahmedabad/HRD/17 | Construction of new building in the Custom House Compound, Ahmedabad. | CBIC/ CPWD | 31.87 |  |  |  | Project sanctioned on 11.06.2018. File submitted to Ministry for revalidation on 25.08.2020. IFU returned the file with certain observations, the same communicated to the Comm'te on 17.09.2020. | Rs. 5.00 cr. was released in F.Y. 2018-19, Comm'te has surrendered Rs. 4.75 cr. During F.Y. 2019-20 Rs. 2.00 cr. released on 20.08.2019. | Sanctioned

## Ahmedabad Custom
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad Cus. | Cus. (Prev.), Jamnagar/ / 916/8/Const./ Jamnagar/HRD/16 | Construction of office building at Jamnagar Total land- 10,250 sqm. Office space- 4131.34 sqm. | CBIC/ CPWD | 43.67 | Yes | Project in advanced stage |  | Project sanctioned on 13.12.2017. Revalidation approved on 03.06.2020 | Rs. 15.00 Cr. were released in 2018-19 out of which 4.00 were utilized. Rs. 7.00 Cr. were released in 2019-20 out of which 6.78 Cr. has been utilized till Nov, 2019. Addl. Rs. 5.00 Cr. revalidated from Min. and released on 17.02.2020. Rs. 12.74 Cr.released on 16.06.2020 in F.Y. 20-21. | Sanctioned
2 | Ahmedabad Cus. | Cus. Jamnagar (dwarka) 916/17/Const./Ahmedabad/HRD/18 | Construction of office building at the site of shore guard, Dwarka, Jamnagar. | CBIC/CPWD | 1.24 |  |  |  | File sanctioned on 04.03.2020. Revalidation approved on 12.06.2020. | Rs. 50.00 lakh released on 06.07.2020 in F.Y. 2020-21 | Sanctioned

## Bengaluru CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
3 | Bengaluru CGST | CGST, Belgavi/ Bengaluru / 916/15/Const. /Belgaum/ HRD/12 | Construction of office building and staff quarters for Bagalkot Range and Range D of Vijaypura Division under Belagavi CGST Comm'te Total land-01 acre Office space-1080 sqm. Residential space-465 sqm. Total qtrs.-02 Type wise qtrs.- Type-III=01 Type-IV=01 | CBIC/ CPWD | 2.19 | Yes | Project in advanced stage. Land worth Rs. 7-8 cr. which was provided free of cost will be taken back by Town Development Authority in case of non-construction.. |  | Project sanctioned on 10.01.2018. Revalidation approved by IFU on 18.09.2020 . | Rs. 5.00 lakh released on 16.01.18 & Rs. 15.00 lakhs on 12.02.2018 but could not utilized. Rs. 20.00 lakh again released on 20.08.2018, Rs. 199.03 lakhs released on 01.11.2018. Rs. 1.03 released on 31.5.2019 | Sanctioned

## Bengaluru Custom
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bengaluru Cus | Mangalore Custom/ 202/7/2003 Ad. VIII (EC) | Providing Barbed wire fencing and Name Boards to properties belonging to Customs Department at Karwar, for Rs. 89,56,000. | CBIC/ CPWD | 0.89 | Yes | The said land is required to be protected from encroachment and this is a small project. | Original proposal received on 25.05.2016. File submitted to the Ministry on 10.11.2016, 18.01.2017 &12.05.2017. | Project sanctioned on 15.09.2017. Reasons for delay in the project sought from the Comm'te vide DG,HRD D.O. letter dated 09.09.2020. In the meanwhile , file submitted to Ministry for revalidation on 21.09.2020. | Rs. 83,44,052/- were released in 2017-18, out of which Rs. 6,11,948/- utilized in 2017-18 & Rs. 14,21,578/- utilized in 2018-19. Further, Rs. 75,34,422/- released on 12.07.2019 | With Ministry

## Chandigarh CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Chandigarh CGST | CGST Jalandhar/ 916/09/Const./ Jalandhar/ HRD/16 | Construction of office cum residential qtrs.and boundary wall at Jalandhar Total land - 06 acre Total qtrs.- 116 Type wise qtrs.- Type-II=19 Type-III=62 Type-IV =32 Type-V A=01 Type-V B=01 Type-VI=01 | CPWD/ CPWD | 67.57 | Yes | Project approved by IFU. Non-construction fee will accrue if construction not started | Original proposal received on 06.09.2016. Query letter sent on 16.09.2016. Reply received on 17.11.2016.File submitted to the Ministry on 18.11.2016, 20.12.2016, 03.02.2017, 27.02.2017, 03.04.2017, 14.06.2017 & 28.07.2017. | Project was sanctioned on 4.8.2017 and being executed through MoUD funds. During the visit to Chandigarh on 06.12.2019 JD (I&W) had reviewed the project status and found to be satisfactory. |  | Sanctioned
2 | Chandigarh CGST | Jammu 916/4/Const./Srinagar/HRD/2020 | Construction of boundary wall with concertina wire fencing around the land at Solina, Srinagar for construction of office and residential buildings of Customs & CGST Division, Srinagar | CBIC/CPWD | 4.14 |  |  |  | Proposal sanctioned on 31.07.2020. File sent to Ministry for concurrence to release funds on 17.08.2020. IFU returned the file seeking certain information, same communicated to the Comm'te on 31.08.2020. |  | Sanctioned

## Chennai Custom
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Chennai Cus. | Chennai Cus. (Gen.) VIII / 916/03/Const./Chennai/RD/ 16 | Construction of residential qtrs. at Anna Nagar, Chennai. Total land- 1,06,086 sqm. Total qtrs.-726 Type wise qtrs.- Type-II=288 Type-III=288 Type-IV=150 | CBIC/ CPWD | 348.77 | Yes | Project approved by IFU. Presentation to be made in front of the RS | Original proposal received in Feb. 2016. .File submitted to the Ministry on 29.04.2016, 21.11.2016, 03.01.2017, 26.04.2017 & 14.08.2017. | Project sanctioned on 13.10.2017. Revalidation approved on 03.06.2020. | Rs. 30.00 cr. released in 2018-19 out of which Rs. 12.00 cr. utilized. Rs. 20.00 Cr. were released on 24.07.2019. Addl. amount of Rs. 15.00 cr. sought in RBE 2019-20 has been released on 27.01.2020. Rs. 67.00 Cr. released on 16.06.2020 in F.Y. 20-21. | Sanctioned
2 | Chennai Cus. | Chennai Cus. (Gen.)/ 916/08/Const./Chennai/HRD/2018 | Construction of 36 residential quarters at Nungambakkam, Chennai | CBIC / CPWD | 65.42 |  |  | Sanctioned | Project sanctioned. Revised proposal submitted to Min. on 17.01.2020. Revalidation approved on 03.06.2020. | Rs. 5.00 Cr. were revalidated for F.Y. 2019-20 and released on 31.05.2019. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21 | Sanctioned | AS & FA

## Delhi CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Delhi CGST | CGST, Delhi (North)/ 916/03/Const./ Dwarka/HRD/17 | Construction of residential qtrs. at Dwarka Total land- 17832 sqm. Total qtrs.-256 Type wise qtrs.- Type-IV=168 Type-V=52 Type-VI=36 | CBIC/ NPCC | 227 | No | ____ | This is a very old proposal. Due to deficiencies in the bidding process Revenue Secretary advised for fresh bidding on 03.04.2017. Commissionerate invited tender along with RFP on 27.04.2017. Revised proposal received on 16.06.2017. | Project sanctioned on 25.07.2018. . File is submitted to the Ministry on 06.07.20 for revalidation. IFU raised an observation reg. non-utilization of funds by NPCC in F.Y. 2019-20, same conveyed to the Comm'te on 21.07.2020. Revalidation approved by IFU, file submitted to Commr. (Coord.) on 21.09.2020 for issuance of S.O. | Rs. 3.00 Cr. released on 27.07.2018 and Rs. 30.00 Cr. released on 26.02.2019 in F.Y. 2018-19. Further Rs. 26.50 Cr. released on 16.08.2019. | With Ministry | AS & FA
2 | Delhi CGST | Delhi (South)/ 916/62/Const./Nangal Raya/HW/06 | Construction of office building at Nangal Raya, New Delhi. | CBIC/ NBCC | 32.83 |  |  |  | Proposal sanctioned on 13.06.2016. Complete amount has been released to the Comm'te. Comm'te has informed that civil work has almost completed |  | Sanctioned

## DRI
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | DRI | DRI Kolkata/ 916/02/Const. /Kolkata/ HRD/2016 | Construction of DRI at Plot No. CBD-93, Action Area-II, New Town, Kolkata | CBIC/ CPWD | 64.5 | ___ |  | Not Sanctioned | Proposal sanctioned on 08.02.2019. Revalidation request for an amount of Rs. 20.00 Cr. approved on 12.06.2020. | Rs.1.49 Cr. have been utilized till F.Y. 2019-20. Rs. 10.00 Cr. released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
2 | DRI | DRI Hyderabad 916/21/Const./DRI/ Hyderabad/ HRD/19 | Construction of office building for DRI Hyderabad Zonal Unit at Jubilee Hills at Hyderabad (Geo Technical Investigation) | CBIC/ CPWD | 0.08 |  |  |  | Proposal sanctioned on 13.03.2020. Comm'te vide letter dated 27.07.2020 has stated that Geo Technical Investigation work will be included in the main construction proposal to be sent shortly. | Rs. 0.08 lakh released on 17.03.2020. | Sanctioned
3 | DRI | DRI Lucknow 916/3/Const./DRI-Lucknow/HRD/2020 | Construction of boundary wall by DRI Zonal Unit, Lucknow | CBIC/CPWD | 0.98 |  |  |  | Proposal sanctioned by the Ministry on 23.03.2020. Revalidation approved on 25.06.2020. | Rs. 98.00 lakh released by EMC on 06.07.2020 in F.Y. 2020-21 | Sanctioned
4 | DRI Delhi | DRI (HQ), 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of boundary wall for DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 0.25 |  |  |  | Proposal sanctioned on 09.10.2019. |  | Sanctioned

## Guwahati CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Guwahati CGST | CGST, Agartala/ 916/10/Const./ Shillong/HRD/15 | Construction of office building (Audit Circle, Custom division & CGST Division) at Agartala Total land- 3022 sqm. Office space-2793 sqm. Guest House-463 sqm. | CBIC/ CPWD | 28.04 | Yes | Project in advanced stage | Original proposal received on 16.09.2015. Deficiency letter sent on 14.10.2015, 23.03.2016 & 29.08.2016. Reply received on 23.02.2016, 12.08.2016 and 29.05.2017 subsequently. | Proposal sanctioned on 18.02.2019. Revalidation approved on 03.06.2020. | Rs 50 Lakh released on 26.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 1.00 Cr. released on 28.05.2019. Addl. Rs. 3.00 Cr. revalidated from Min. and released on 17.02.2020. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. | Sanctioned

## Hyderabad CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Hyderabad CGST | Hyderabad Cus. 916/14/Const./Hyderabad/HRD/16 | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | CBIC/ CPWD. | 1.3 | No | ____ | Original proposal received on 24.10.2016. File submitted to the Ministry on 14.02.2017, 02.03.2017 & 04.07.2017. Ministry returned the file with observations on 23.02.2017, 10.04.2017 & 28.08.2017. | Proposal sanctioned on 07.03.19. Comm'te vide letter dated 30.07.2020 has stated that demarcation of land is pending and no funds are required till demarcation is completed. | Rs. 10.00 lakhs were released in 2018-19 but could not be utilized Further, Rs. 50.00 lakhs has been released on 29.07.2019. | Sanctioned

## Jaipur CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Jaipur CGST | Udaipur/ 916/11/Const./ Jaipur-II/HRD/11 | Construction of office building CGST division Bhilwara. Land area: 1858.06 sqm. Office space : 750.00sqm. | CBIC/ CPWD | 9.72 | No | ___ | Original proposal recieved on 08.09.2014. Query letter sent on 31.10.2014, reply recieved on 15.04.2015. Query letter sent on 18.05.2015 followed by several reminders. | Proposal sanctioned on 21.02.2019. Certain discrepencies vis-a-vis the tender cost have been found. Revalidation approved on 25.08.2020. | Rs 1.5 cr have been released on 26.02.2019 but could not be utilized. During 2019-20 Rs. 50.00 lakhs has been released on 25.07.2019. Rs. 3.00 Cr released on 31.08.2020. | Sanctioned | AD VIII
2 | Jaipur CGST | CGST Jodhpur/ 916/19/Const./Jodhpur/HRD/18 | Comprehensive Consultancy Services for Master Planning of Campus & Design of Office cum Residential Campus for CGST at Jodhpur | CBIC/ CPWD | 1.11 |  |  | Not Sanctioned | Proposal for Master planning has been sanctioned on 25.09.2019. Comm'te vide letter dated 27.07.2020 has stated that revalidation/funds is not required for the project for F.Y. 2020-21, till MoU is signed with Income Tax. | In F.Y. 2019-20 Rs. 10.00 lakhs have been released on 01.10.2019. | Sanctioned
3 | Jaipur CGST | CGST Udaipur 916/4/Const./Udaipur/HRD/19 | Construction of new office building for Udaipur CGST Comm'te | CBIC/ CPWD | 42.07 |  |  |  | File sanctioned on 09.03.2020. Revalidation approved on 25.06.2020. | Rs. 10.00 lakh released on 18.03.2020 in F.Y. 2019-20. Rs. 50.00 lakh released on 06.07.2020 in F.Y. 2020-21. | Sanctioned

## Lucknow CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Lucknow CGST | CGST Agra/ 916/05/Const./Agra/HRD/2018 | Construction of conference hall in the building of CGST Comm'te Agra. | CBIC/ CPWD | 0.12 |  | Proposal is under process at DGHRD |  | Project sanctioned on 13.08.19. Revalidation approved by IFU on 18.09.2020. | In F.Y. 2019-20 Rs. 11,97,143/- have been released on 28.08.2019. | Sanctioned

## Meerut CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Meerut CGST | CGST Ghaziabad & 916/5/Const./ Meerut/HRD/17 | Construction of office building including boundary wall and culvert over Nala at allotted land measuring 2.21 acres (8894 sqm.) to CGST Ghaziabad, Audit-II, Ghaziabad, Noida | CBIC/ CPWD | 116.42 |  |  |  | Project sanctioned on 03.10.19. Revalidation approved on 03.06.2020. | Rs. 1.00 cr. released on 14.10.2019 in F.Y. 2019-20. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. | Sanctioned

## Mumbai CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai CGST | CGST, Raigad 911/4/Misc./Kharghar/HRD/15 | Construction of residential qtrs. at Kharghar by NBCC. Total land- 20,000.32 sqm. Total qtrs.-187 Type wise qtrs.- Type-II=42 Type-III=70 Type-IV=44 Type-IV (Spl)=20 Type-V=09 Type-VI=02 | CBIC/ NBCC | 110.11 | Yes | Project in advanced stage. |  | File sanctioned on 18.04.2019. Revalidation for an amount of Rs. 22.00 Cr. approved by the Min. on 25.06.2020, subject to condition that utilization certificate for amount released in F.Y. 2019-20 may be taken from NBCC before releasing of any amount in F.Y. 2020-21, same communicated to Comm'te on 06.07.2020 | Rs 5.00 cr. were released on 23.04.2019 and further Rs. 6.011 Cr. released on 07.06.2019. Further, Rs. 10.00 Cr. sought in RBE 2019-20 released on 17.01.2020.Rs 22.00 cr. were released on 27.08.2020. | Sanctioned
2 | Mumbai CGST | CGST Palghar/916/5/Const./ Mumbai/HRD/ 16 | Construction of 3 Div. offices and 14 ranges offices on plot bearing NosP-34 at MIDC, Boisar-reg. | CBIC/ CPWD | 33.25 | No | ____ |  | Proposal sanctioned on 01.07.19. Revalidation approved on 25.06.2020. | Rs. 1.00 Cr. released on 19.07.19. Rs. 5.00 Cr. released on 19.08.2020 in F.Y. 2020-21. | Sanctioned
3 | Mumbai CGST | CGST Thane/ 916/15/Const./Thane/HRD/2018 | Proposal for payment of total station survey and GEO Technical Investigation (Soil Investigation) at Thane | CBIC / CPWD | 0.03 |  |  | Not Sanctioned | Proposal sanctioned on 04.10.2019. Revalidation request awaited from the Comm'te, reminder sent on 13.07.2020. | Fund amounting to Rs. 3,23,363/- released on 16.10.19. | Sanctioned | AS & FA

## Mumbai Custom
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai Zone-I | Pr. Comm. Cus.(Gen.) 911/3/Custom Enclave/Mumbai/ HRD/16 | Construction of Office complex and residential quarters at Customs Enclave Plot, Wadala, Mumbai through CPWD at a cost of Rs. 495.5 Cr. for office complex and Rs. 480 cr. For residential complex Office space 30000sqm. Total qtrs. -769 | CBIC/CPWD | 975.72 | Yes | Project is being developed on self-sustaining basis. All the offices of GST Excise, DRI, DGCEI etc. will be relocated in the said project. | This land was given free of cost by the Salt Department 1980's. Due to the construction of roads we now have 46 acres encrochment free land where godowns exist. Initially it was thought that Govt. will pay for the construction which was to be done by CPWD. However, with the approval of Revenue Secretary it has been deceided to nominate NBCC to construct the office building and residential quarters without any cost to the Govt. The cost of construction only is likely to be Rs. 2700 crores. | Proposal Sanctioned on 11.11.2019. Revalidation approved by IFU on 31.07.2020. | Rs. 5.00 Cr. (Rs. 2.50 Cr. for office & Rs. 2.50 Cr. for residence) released on 11.11.2019. Rs. 30.00 Cr. released on 13.08.2020 (Rs.15 Cr. for 4059 & Rs.15 Cr. for 4216). | Sanctioned
2 | Mumbai-II Cus. | Customs (General) JNCH/ 916/17/Const./ Raigad/HRD/16 | Construction of additional office building (G+7) at JNCH NHAVA SHEVA Dist. Raigad-Mumbai Available area - 14900 sqm. Office space - 8551.80 sqm. | CBIC/ CPWD | 90.26 | No | ___ | Original proposal received in nov. 2016. Query letter sent on 13.12.2016 followed by several reminders and DO letters. | Proposal for enabling works (Rs 51 Lakh) was sanctioned in March, 2018. Proposal for office sanctioned on 14.02.2019. Revalidation request awaited from the Comm'te, reminder sent on 13.07.2020. | Rs. 43 lakh for enabling works was released on 19.07.2019. Further due to pending approvals from local authorites Comm'te vide letter dated 10.10.19 has requested not to released in balance amount. | Sanctioned

## NACIN
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | NACIN | Hyderabad NACIN 916/02/Const./ Hyderabad/ HRD/13 | Construction of RTI, NACIN, at Attapur, Hyderabad Total built up area- 11940 sqm. | CBIC/ NBCC | 46.71 | Yes | Proposal sanctioned on 30.12.2016. | Original proposal received in Jan., 2013 . File submitted to Ministry on 26.02.2014, 10.11.2014, 04.09.2015,18.04.2016 & 23.11.2016. | Project sanctioned on 30.12.2016. The project is being executed by NBCC. The construction work is in full swing. Revalidation request for an amount of Rs. 8.85 Cr. approved on 12.06.2020. | Rs. 37.85 Cr. have been released/utilized till F.Y. 2019-20. Rs. 5.00 Cr. released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
2 | NACIN | RTI Hindupur/ 916/8/Const./ Hindupur/HRD/15 | Construction of New Academy of NACIN at Palasamudram (V), (Hindupur) Ananthpur Dist., Andhra Pradesh-Requirement of funds for construction of compound wall road along the boundary etc. Total land- 500 acre | CBIC/ CPWD | 15.14 | No | ___ |  | Proposal for boundary wall & gate complex involving Rs. 15.14 Cr. was sanctioned on 20.11.18 and proposal for consultancy services involving Rs. 1.15 Cr. was sanctioned on 16.10.19. Revalidation approved on 28.07.2020 for an amount of Rs. 4.85 Cr. for boundary wall. Revised proposal for consultancy services at a cost of Rs. 2.00 cr. submitted to Ministry for approval on 17.08.2020. IFU has returned the file advising to keep the consultancy work in suspension for F.Y. 2020-21, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. | Rs. 7.45 Cr. have been utilized till F.Y. 2019-20. | IFU query
3 | NACIN | NACIN Cochin 916/7/Const./RTI NACIN Munnar/HRD/18 | Const. of RTI NACIN Munnar, Kerala | CBIC / CPWD | 0.03 (Enabling works) 0.93 (For boundary wall) |  |  | Not Sanctioned | Proposal for enabling works sanctioned on 08.01.2019. Revalidation approved on 12.06.2020 | Rs. 2.75 lakh released in F.Y.2019-20 has not been utilized in F.Y. 2019-20. Rs. 2.75 lakhs released on 06.07.2020 in F.Y. 2020-21. | Sanctioned

## Patna Custom
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Patna Cus. | Patna Cus. (Prev.)/ / 916/16/Const./Patna (P)/HRD/2016 | Proposal for construction of Residential complex at Land Customs Station jogbani, a/ a & e/s of Rs.7,99,52,000/- Total qtrs.- 21 Type wise qtrs.- Type-II=7 Type-III=12 Type-IV =02 | CBIC/ CPWD | 7.99 | No | ___ | Original proposal received on 21.11.2016. Query letter sent on 13.12.2016. Reply received, file submitted to the Ministry on 06.02.2017, IFU returned file with certain queries, file resubmitted to ministry after clarifying the queries on 10.08.2017. | Project sanctioned on 11.06.2018. File sent for revalidation on 06.08.2020. IFU returned the file with some queries and the same were conveyed to Comm'te on 27.08.2020. After clarifications, file submitted to Ministry for revalidation on 21.09.2020. | Rs. 4.00 cr. have been released to the Comm'te. Comm'te surrendered Rs 3.5 crore. In F.Y. 2019-20 Rs. 3.99 cr. released on 12.07.19. | With Ministry
2 | Patna Cus. | Patna Cus. (Prev.)/ 916/15/Const./Patna/HRD/14 | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul Total land- 2.74 acre Residential space-5,730 sqm. Total qtrs.-21 Type wise qtrs.- Type-III=06 Type-IV=14 Type-IV (Spl)=01 | CBIC/ CPWD | 11.85 | Yes | Sanctioned | Original proposal received in September 2014. Query letter sent on 17.11.2014, 25.06.2015, 20.07.2015. Reply received on 03.03.2015, 25.08.2015. File submitted to the Ministry on 08.11.2016 and 04.07.2017. | Project sanctioned on 22.09.2017. Revalidation approved on 25.08.2020. | Rs.9.5 cr. have been released to the Comm'te in this F.Y. 2018-19. Rs. 1.34 Cr. utilized in 2018-19. Comm'te had surrendered Rs 7.17 crore. In the current F.Y. 2019-20 Rs. 3.00 Cr. released on 14.08.2019. Rs. 4.00 Cr. released on 31.08.2020. | Sanctioned

## Pune CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Pune CGST | CGST Pune-II/ 916/5/Const./ Pune/ HRD/2014 | Construction of office building and 02 nos. residential quarters for CGST Ranges office at Pandharpur, Distt. Solapur, Maharashtra. Total land : 2230.22 sqm. Office space :146.50 sqm. One quarter Type IV | CBIC/ CPWD | 2.05 | No | ___ | Original proposal received on 25.04.2014. Query letter sent on 27.07.2014, 29.08.2016 & 16.02.2017. followed by several reminders. Reply received on 11.12.2015, 08.02.2016 & 17.02.2017 respectively. | File sanctioned on 23.12.2019. Revalidation approved on 25.06.2020. | Rs. 20.00 lakhs released on 30.12.2019. Rs. 1.31 Cr. released on 06.07.2020 in F.Y. 2020-21. | Sanctioned
2 | Pune CGST | CGST Kolhapur/ 916/21/Const. /Pune/HRD/14 | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur-reg. Land area: 12854.8 sqm. Office space : 9244.1 sqm. | CBIC/ CPWD | 42.44 | No | ____ | Original proposal received in March 2015. Query letter sent on 10.04.2015 followed by several reminders. | Proposal sanctioned on 25.06.2020. File submitted to Ministry on 17.08.2020 for concurrence to release Rs. 3.00 Cr. for enabling works. IFU returned the file seeking certain information, same communicated to the Comm'te on 31.08.2020. |  | Sanctioned

## Trichy Custom
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Trichy Cus. | Tuticorin/ 916/19/ Const./ Tuticorin/HRD/14 | Construction of additional residential quarters (T-II, T-III & T-IV) at Port Area, Tuticorin. Total qtrs.- 06 Type wise qtrs.- Type-II=1 Type-III=2 Type-IV =3 | CBIC/ CPWD | 1.62 | Yes | Project in advanced stage. As this is a small project construction will be completed within 1 year. | Original proposal received on 09.11.2014. Query letter sent on 14.11.2014, 30.06.2015, 17.07.2015. File has been submitted to the Ministry on 01.09.2016. | Project sanctioned on 25.08.2017. Revalidation approved on 20.08.2020. Rs. 0.96Cr. Released on 27.08.2020. | F.Y. 2019-20 Released = Rs. 1.47 Cr.Utilized = Rs. 0.52 Cr. Rs. 95.00 lakh were released on 27.08.2020. | Sanctioned

## Visakhapatnam CGST
Construction Sanctioned Projects
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Visakhapatnam CGST | CGST Tirupati/Visakhapatnam/ 916/55/Const./ Anantpur/HRD/ 06 | Construction of office building at Anantapur, Andhra Pradesh. Office space: 1292.70 sqm. | CBIC/ CPWD | 7.07 | No |  | Original proposal received on 06.07.2006.Revised PE received on 11.12.2015.Query letter sent on 28.11.2016, 11.04.2016, 29.07.2016, 14.12.2016 followed by reminders and DO letter dated 25.04.2017. | Proposal sanctioned on 21.12.2018. Revalidation approved by IFU, file submitted to Commr. (Coord.) on 21.09.2020 for issuance of S.O. | F.Y. 2018-19 Released = Rs. 1.00 Cr. F.Y. 2019-20 Released = Rs. 4.06 Cr. | Sanctioned
2 | Visakhapatnam CGST | CGST Tirupati/ 916/4/Const./ Kurnool (A.P.)/HRD/2012 | Construction of 7 Nos. Type-IV Quarters and Guest House for Kurnool (Tirupati Comm’te), Andhra Pradesh-reg. Total Land :606.88 sqm. | CBIC/ CPWD | 3.96 | No | ____ |  | Proposal sanctioned on 10.09.2018. Revalidation approved on 25.06.2020. | F.Y. 2018-19 Released = Rs. 1.18 Cr., Utilized Rs. 20 lakhs. F.Y. 2019-20 Released = Rs. 50.00 lakhs. IFU raised observations on addl. sanction sought, conveyed to the Comm'te F.Y. 2020-21 Released = Rs. 1.97 Cr. (06.07.2020) | Sanctioned | AD VIII