## Ahmedabad CGST
Ahmedabad CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad CGST | Ahmedabad (North)/ 916/8/Const./ Ahmedabad/HRD/17 | Construction of new building in the Custom House Compound for CGST North Commissionerate at Ahmedabad. | CBIC/ CPWD | 31.87 |  |  |  | Project sanctioned on 11.06.2018. File submitted to Ministry for revalidation on 25.08.2020. IFU returned the file with observations regarding fund utilization and requested to reconcile the fund utlization vis-a-vis funds released. Further as the approval of building plan is pending & tender process is not yet finalized, IFU has advised to seek (i) revaildation after finalization of building plan & Tender process and (ii) to ascertain funds requirment for the current FY from CPWD. IFU's observations have been communicated to the Comm'te on 17.09.2020. Comm'te vide status report dt. 23.11.2020 has intimated that the project is stuck pending approvals of local authorities as CPWD has not factored in the parking requirements as specified by Ahmedabad Municipal Corporation. Their alternatives are not viable as the main building is almost 5 decades old. AMC has asked the Commissionerate to come up with fresh and long term viable proposal after consulting CPWD. | Rs. 5.00 cr. was released in F.Y. 2018-19, Comm'te surrendered Rs. 4.75 cr. During F.Y. 2019-20 Rs. 2.00 cr. released out of which only Rs.11.00 lakh was utilized | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Ahmedabad Cus.
Ahmedabad Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad Cus. | Jamnagar (P.) 916/8/Const./ Jamnagar/HRD/16 | Construction of office building for Customs (Preventive) Commissionerate, Jamnagar; Custom Division, Jamnagar; Custom House, Jamnagar; Custom House, Vadinar, and CGST Sub Commissionerate at Jamnagar Total land- 10,250 sqm. Office space- 4131.34 sqm. | CBIC/ CPWD | 43.67 | Yes | Project in advanced stage |  | Project sanctioned on 13.12.2017. Commencement of construction 23.10.2018. Revalidation approved on 03.06.2020 | Rs. 15.97 Cr. have been utilized till FY 2019-20. Rs. 12.74 Cr.was sought during FY 2021-21 which was released on 16.06.2020. Addl. Funds of Rs. 3.00 Cr. sought in FY 2020-21 and Rs. 4.00 cr. in FY 2021-22 on 6.10.2020 85% of construction work has been completed (As on 31.10.2020). | Sanctioned | Sanctioned
2 | Ahmedabad Cus. | Jamnagar (dwarka) 916/17/Const./Ahmedabad/HRD/18 | Construction of office building at the site of shore guard, Dwarka, Jamnagar. | CBIC/CPWD | 1.24 |  |  |  | File sanctioned on 04.03.2020. Revalidation approved on 12.06.2020. | Rs. 50.00 lakh released on 06.07.2020 in F.Y. 2020-21 RCC works going on as reported in Nov., 2020 | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Bengaluru CGST
Bengaluru CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bengaluru CGST | Belgavi 916/15/Const. /Belgaum/ HRD/12 | Construction of office building and staff quarters for Bagalkot Range and Range D of Vijaypura Division under Belagavi CGST Comm'te Total land-01 acre Office space-1080 sqm. Residential space-465 sqm. Total qtrs.-02 Type wise qtrs.- Type-III=01 Type-IV=01 | CBIC/ CPWD | 2.19 | Yes | Project in advanced stage. Land worth Rs. 7-8 cr. which was provided free of cost will be taken back by Town Development Authority in case of non-construction.. |  | Project sanctioned on 10.01.2018. Revalidation approved by IFU on 18.09.2020. Letter written on 29.01.2021 seeking completion details of project and booking of expenditure. | Rs. 1.6 Cr. utilized till F.Y. 2019-20. For F.Y. 2020-21 remaining Rs. 50.00 lakh released on 24.09.2020. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Bengaluru Cus.
Bengaluru Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bengaluru Cus | Mangalore 202/7/2003 Ad. VIII (EC) | Providing Barbed wire fencing and Name Boards to properties belonging to Customs Department at Karwar, for Rs. 89,56,000. | CBIC/ CPWD | 0.89 | Yes | The said land is required to be protected from encroachment and this is a small project. | Original proposal received on 25.05.2016. File submitted to the Ministry on 10.11.2016, 18.01.2017 &12.05.2017. | Project sanctioned on 15.09.2017. CPWD vide letter dated 20.11.2020 informed Commissionerate that out of total 39 properties, fencing work is completed in 18 properties and work is yet to be started 4 properties. In rest of properties fencing work has not started due to disputed land title, land being claimed by salt department etc. The purpose of fencing at present is to save the land from any encroachment. Revalidation approved by IFU on 23.11.2020. | Rs. 83,44,052/- were released in 2017-18, out of which Rs. 6,11,948/- utilized in 2017-18 Rs. 14,21,578/- utilized till 2018-19. Rs. 75,34,422/- released on 12.07.2019. Rs. 45,67,778/- released on 09.12.2020. | Sanctioned | yet to sanction
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
39.14

## Chandigarh CGST
Chandigarh CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Chandigarh CGST | Jalandhar/ 916/09/Const./ Jalandhar/ HRD/16 | Construction of office cum residential qtrs.and boundary wall at Jalandhar for CGST Jalandhar Commissionerate Total land - 06 acre Total qtrs.- 116 Type wise qtrs.- Type-II=19 Type-III=62 Type-IV =32 Type-V A=01 Type-V B=01 Type-VI=01 | CPWD/ CPWD | 67.57 | Yes | Project approved by IFU. Non-construction fee will accrue if construction not started | Original proposal received on 06.09.2016. Query letter sent on 16.09.2016. Reply received on 17.11.2016.File submitted to the Ministry on 18.11.2016, 20.12.2016, 03.02.2017, 27.02.2017, 03.04.2017, 14.06.2017 & 28.07.2017. | Project was sanctioned on 4.8.2017 and being executed through MoUD funds. |  | Sanctioned | yet to sanction
2 | Chandigarh CGST | Jammu 916/4/Const./Srinagar/HRD/2020 | Construction of boundary wall with concertina wire fencing around the land at Solina, Srinagar for construction of office and residential buildings of Customs & CGST Division, Srinagar | CBIC/CPWD | 4.14 |  |  |  | Proposal sanctioned on 31.07.2020. File sent to Ministry for concurrence to release funds on 17.08.2020. IFU has given concurrence to release Rs. 10.00 lakh on 18.11.2020. | Rs. 10.00 lakhs released on 09.12.2020 in F.Y. 2020-21 | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Chennai Cus.
Chennai Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Chennai Cus. | Chennai Cus. (Gen.) VIII / 916/03/Const./Chennai/RD/ 16 | Construction of residential qtrs. at Anna Nagar, Chennai. Total land- 1,06,086 sqm. Total qtrs.-726 Type wise qtrs.- Type-II=288 Type-III=288 Type-IV=150 | CBIC/ CPWD | 348.77 | Yes | Project approved by IFU. Presentation to be made in front of the RS | Original proposal received in Feb. 2016. .File submitted to the Ministry on 29.04.2016, 21.11.2016, 03.01.2017, 26.04.2017 & 14.08.2017. | Project sanctioned on 13.10.2017. Revalidation approved on 03.06.2020. Pile work of all towers of type II,III & IV are completed. Comm'te vide letter dt. 18.1.2021 has stated that addl. Rs. 52.00 Cr.are required for the project in F.Y.2020-21. | Comm'te vide letter dt. 20.11.2020 has stated that Rs. 114 Cores have been released till date, out of which as on 20.11.2020 CPWD had booked Rs. 80.14 Cr and utilization certificate has been issued for Rs. 47.00 Crores. | Sanctioned | Sanctioned
2 | Chennai Cus. | Chennai Cus. (Gen.)/ 916/08/Const./Chennai/HRD/2018 | Construction of 36 residential quarters (18 Type-V and 18 Type-VI) at Nungambakkam, Chennai. (Total 36 quarters) | CBIC / CPWD | 65.42 |  |  | Sanctioned | Project sanctioned 24.12.2018. Revalidation approved on 03.06.2020. Comm'te vid letter dt. 1.10.2020 has intimated that soil investigation & structural design completed. | Rs. 5.00 Cr. were revalidated for F.Y. 2019-20. Rs. 2.25 cr. utilised. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21 | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Delhi CGST
Delhi CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Delhi CGST | Delhi (North)/ 916/03/Const./ Dwarka/HRD/17 | Construction of residential qtrs. at Dwarka Total land- 17832 sqm. Total qtrs.-256 Type wise qtrs.- Type-IV=168 Type-V=52 Type-VI=36 | CBIC/ NPCC | 227 | No | ____ | This is a very old proposal. Due to deficiencies in the bidding process Revenue Secretary advised for fresh bidding on 03.04.2017. Commissionerate invited tender along with RFP on 27.04.2017. Revised proposal received on 16.06.2017. | Project sanctioned on 25.07.2018. Date of commencement of construction is 1.11.2018. Revalidation approved by IFU on 30.09.2020. | Rs. 71.50 Cr. have been released upto FY 2019-20 which was fully utilized till 23.9.2020. Rs. 36.00 Cr. have been released during FY 2020-21. Rs. 94.51 Cr. have been booked upto December, 2020 Addl. funds sought in FY 20-21 -- Rs. 44.00 Cr. | Sanctioned | yet to sanction
2 | Delhi CGST | Delhi (South)/ 916/62/Const./ Nangal Raya/HW/06 | Construction of office building at Nangal Raya, New Delhi. | CBIC/ NBCC | 32.83 |  |  |  | Proposal sanctioned on 13.06.2016. Complete amount has been released to the Comm'te. Comm'te vide letter dt. 06.02.2019 has intimated that civil work is almost completed. Further, Comm'te vide letter dt. 21.08.2020 has sought funds amounting to Rs. 3.97 Cr. for providing new load of 1408KW, justification for which was sought on 2.9.2020, as work of electric connection was already included in the final preliminary estimate approved by the Competent Authority. Reminders issued on 26.10.2020 & 12.11.2020 (alongwith status of project). Reply awaited. |  | Sanctioned | Sanctioned | 33
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## DRI
DG: DRI
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | DRI | Kolkata/ 916/02/Const. /Kolkata/ HRD/2016 | Construction of DRI at Plot No. CBD-93, Action Area-II, New Town, Kolkata | CBIC/ CPWD | 64.5 | ___ |  | Not Sanctioned | Proposal sanctioned on 08.02.2019. Revalidation request for an amount of Rs. 10.00 Cr. approved on 12.06.2020. Pile foundation work & sheet piling work completed | Rs.1.49 Cr. have been utilized till F.Y. 2019-20. Rs. 10.00 Cr. released on 06.07.2020 in F.Y. 2020-21. Rs. 8.00 Cr. to be utilized in F.Y. 2020-21. | Sanctioned | Sanctioned
2 | DRI | Hyderabad 916/21/Const./DRI/ Hyderabad/ HRD/19 | Construction of office building for DRI Hyderabad Zonal Unit at Jubilee Hills at Hyderabad (Geo Technical Investigation) | CBIC/ CPWD | 0.08 |  |  |  | Proposal sanctioned on 13.03.2020. Comm'te vide letter dated 27.07.2020 has stated that Geo Technical Investigation work will be included in the main construction proposal to be sent shortly. | Rs. 0.08 lakh released on 17.03.2020. | Sanctioned | Sanctioned
3 | DRI | Lucknow 916/3/Const./DRI-Lucknow/HRD/2020 | Construction of boundary wall by DRI Zonal Unit, Lucknow | CBIC/CPWD | 0.98 |  |  |  | Proposal sanctioned on 23.03.2020. Revalidation approved on 25.06.2020. | Rs. 98.00 lakh released by EMC on 06.07.2020 in F.Y. 2020-21 | Sanctioned | Sanctioned
4 | DRI Delhi | DRI (HQ), 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of boundary wall for DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 0.25 |  |  |  | Proposal sanctioned on 09.10.2019. |  | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Guwahati CGST
Guwahati CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Guwahati CGST | Agartala 916/10/Const./ Shillong/HRD/15 | Construction of office building (Audit Circle, Custom division & CGST Division) at Agartala Total land- 3022 sqm. Office space-2793 sqm. Guest House-463 sqm. | CBIC/ CPWD | 28.04 | Yes | Project in advanced stage | Original proposal received on 16.09.2015. Deficiency letter sent on 14.10.2015, 23.03.2016 & 29.08.2016. Reply received on 23.02.2016, 12.08.2016 and 29.05.2017 subsequently. | Proposal sanctioned on 18.02.2019. Revalidation approved on 03.06.2020. | Rs 50 Lakh released on 26.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 4.00 Cr. released in FY 2019-20 and fully utilized. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. Addl. funds sought in FY 20-21 -- Rs. 7.00 Cr. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Hyderabad CGST
Hyderabad CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Hyderabad CGST | Hyderabad 916/14/Const./Hyderabad/HRD/16 | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | CBIC/ CPWD. | 1.3 | No | ____ | Original proposal received on 24.10.2016. File submitted to the Ministry on 14.02.2017, 02.03.2017 & 04.07.2017. Ministry returned the file with observations on 23.02.2017, 10.04.2017 & 28.08.2017. | Proposal sanctioned on 07.03.19. Comm'te vide letter dated 30.07.2020 has stated that demarcation of land is pending and no funds are required till demarcation is completed. | Rs. 10.00 lakhs were released in 2018-19 but could not be utilized Rs. 50.00 lakhs has been released on 29.07.2019. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Jaipur CGST
Jaipur CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Jaipur CGST | Udaipur/ 916/11/Const./ Jaipur-II/HRD/11 | Construction of office building CGST division Bhilwara. Land area: 1858.06 sqm. Office space : 750.00sqm. | CBIC/ CPWD | 9.72 | No | ___ | Original proposal recieved on 08.09.2014. Query letter sent on 31.10.2014, reply recieved on 15.04.2015. Query letter sent on 18.05.2015 followed by several reminders. | Proposal sanctioned on 21.02.2019. Revalidation approved on 25.08.2020. Construction started on 07.10.2019. | Rs 1.5 cr have been released on 26.02.2019 but could not be utilized. During 2019-20 Rs. 50.00 lakhs has been released on 25.07.2019. Rs. 3.00 Cr released on 31.08.2020. Addl. funds required in F.Y. 2021-22 = Rs. 4.00 Cr. | Sanctioned | Sanctioned
2 | Jaipur CGST | Jodhpur/ 916/19/Const./Jodhpur/HRD/18 | Comprehensive Consultancy Services for Master Planning of Campus & Design of Office cum Residential Campus for CGST at Jodhpur | CBIC/ CPWD | 1.11 |  |  | Not Sanctioned | Proposal for Master planning has been sanctioned on 25.09.2019. Comm'te vide letter dated 27.07.2020 has stated that revalidation/funds is not required for the project for F.Y. 2020-21, till MoU is signed with Income Tax. | In F.Y. 2019-20 Rs. 10.00 lakhs have been released on 01.10.2019. | Sanctioned | yet to sanction
3 | Jaipur CGST | CGST Udaipur 916/4/Const./Udaipur/HRD/19 | Construction of new office building for Udaipur CGST Comm'te | CBIC/ CPWD | 42.07 |  |  |  | File sanctioned on 09.03.2020. Revalidation approved on 25.06.2020. Period of completion of the project is for 18 months. Construction started on 26.08.2020. | Rs. 10.00 lakh released in F.Y. 2019-20. Rs. 50.00 lakh released in F.Y. 2020-21. Addl. funds sought in FY 20-21 -- Rs. 7.50 Cr. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Lucknow CGST
Lucknow CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Lucknow CGST | Agra/ 916/05/Const./Agra/HRD/2018 | Construction of conference hall in the building of CGST Comm'te Agra. | CBIC/ CPWD | 0.12 |  | Proposal is under process at DGHRD |  | Project sanctioned on 13.08.19. Revalidation approved by IFU on 18.09.2020. | In F.Y. 2019-20 Rs. 12 lakh released, they could not be utilized. Rs.12 lakh released on 24.09.2020. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Meerut CGST
Meerut CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Meerut CGST | CGST Ghaziabad & 916/5/Const./ Meerut/HRD/17 | Construction of office building including boundary wall and culvert over Nala at allotted land measuring 2.21 acres (8894 sqm.) to CGST Ghaziabad, Audit-II, Ghaziabad, Noida | CBIC/ CPWD | 116.42 |  |  |  | Project sanctioned on 03.10.19. Revalidation approved on 03.06.2020. As per status report submitted by the Comm'te vide letter dt. 12.11.2020 work related to construction of boundary wall is almost completed and as reagrds culvert over nala, work is held up as permission is required from forest department for cutting of green trees. Letter written to Comm'te on 15.01.2021 for immidiate surrender of funds. | Rs. 1.00 cr. released on 14.10.2019 in F.Y. 2019-20. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Mumbai CGST
Mumbai CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai CGST | Raigad 911/4/Misc./Kharghar/HRD/15 | Construction of residential qtrs. at Kharghar by NBCC. Total land- 20,000.32 sqm. Total qtrs.-187 Type wise qtrs.- Type-II=42 Type-III=70 Type-IV=44 Type-IV (Spl)=20 Type-V=09 Type-VI=02 | CBIC/ NBCC | 110.11 | Yes | Project in advanced stage. |  | Proposal sanctioned on 18.04.2019. Revalidation for Rs. 22.00 Cr. approved on 25.06.2020, Construction work is in full swing and completed upto plinth beam level as reported by the Comm'te. | Rs 11.01 cr. released in FY 2019-20. Rs 22.00 cr. were released on 27.08.2020. Addl. funds sought in FY 20-21 -- Rs. 25.11 Cr. | Sanctioned
2 | Mumbai CGST | Palghar 916/5/Const./ Mumbai/HRD/ 16 | Construction of 3 Div. offices and 14 ranges offices on plot bearing Nos P-34 at MIDC, Boisar-reg. | CBIC/ CPWD | 33.25 | No | ____ |  | Proposal sanctioned on 01.07.19. Date of commencement of construction is 14.07.2020. Revalidation approved on 25.06.2020. Comm'te vide letter dt. 28.9.2020 has intimated that the tender process has been completed and tender has been awarded. CPWD has been requested to get the plan approved. | Rs. 1.00 Cr. released on 19.07.19. Rs. 5.00 Cr. released on 19.08.2020 in F.Y. 2020-21. Rs. 3.00 Cr. have been surrendered in PFMS. | Sanctioned | Sanctioned
3 | Mumbai CGST | Thane 916/15/Const./Thane/HRD/2018 | Proposal for payment of total station survey and GEO Technical Investigation (Soil Investigation) at Thane | CBIC / CPWD | 0.03 |  |  | Not Sanctioned | Proposal sanctioned on 04.10.2019. Revalidation request/ status of project awaited from the Comm'te, reminder sent on 13.07.2020. | Fund amounting to Rs. 3,23,363/- released on 16.10.19. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Mumbai-I Cus.
Mumbai-I Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai Zone-I Customs | Mumbai (Gen.) 911/3/Custom Enclave/Mumbai/ HRD/16 | Construction of Office complex and residential quarters at Customs Enclave Plot, Wadala, Mumbai through CPWD at a cost of Rs. 495.5 Cr. for office complex and Rs. 480 cr. For residential complex Office space 30000sqm. Total qtrs. -769 | CBIC/ CPWD | 975.72 | Yes | Project is being developed on self-sustaining basis. All the offices of GST Excise, DRI, DGCEI etc. will be relocated in the said project. | This land was given free of cost by the Salt Department 1980's. Due to the construction of roads we now have 46 acres encrochment free land where godowns exist. Initially it was thought that Govt. will pay for the construction which was to be done by CPWD. However, with the approval of Revenue Secretary it has been deceided to nominate NBCC to construct the office building and residential quarters without any cost to the Govt. The cost of construction only is likely to be Rs. 2700 crores. | Proposal Sanctioned on 11.11.2019. Revalidation approved by IFU on 31.07.2020. Commissionerate vide letter dated 15.01.2021 has informed that the presentation by bidders for evaluation of techinical bid stage - II is schdeuled for 28/29.01.2021 | Rs. 5.00 Cr. (Rs. 2.50 Cr. for office & Rs. 2.50 Cr. for residence) released on 11.11.2019. Rs. 30.00 Cr. released on 13.08.2020 (Rs.15 Cr. for 4059 & Rs.15 Cr. for 4216). | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Mumbai-II Cus.
Mumbai-II Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai-II Cus. | Nhava Sheva (Gen.) 916/17/Const./ Raigad/HRD/16 | Construction of additional office building (G+7) (To provide more space to officers of Mumbai Zone-II) at JNCH NHAVA SHEVA Dist. Raigad-Mumbai Available area - 14900 sqm. Office space - 8551.80 sqm. | CBIC/ CPWD | 90.26 | No | ___ | Original proposal received in nov. 2016. Query letter sent on 13.12.2016 followed by several reminders and DO letters. | Proposal for enabling works (Rs 51 Lakh) was sanctioned in March, 2018. Proposal for office sanctioned on 14.02.2019. Comm'te vide letter dt. 29.12.2020 has intimated that pre-construction activities like soil investigation, digital survey, tree survey has been completed. The structrual design work are under process. CPWD is in the process for obtaining permission for tree cutting/transplantation for which has been identified by the CPWD on which work for clearance has been initiated, after which proposal for permission for tree cutting will be submitted to the CIDCO. Construction work is likely to start in April, 2021. | Rs. 43 lakh for enabling works was released on 19.07.2019. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## NACIN
NACIN
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | NACIN | Hyderabad NACIN 916/02/Const./ Hyderabad/ HRD/13 | Construction of RTI, NACIN, at Attapur, Hyderabad Total built up area- 11940 sqm. | CBIC/ NBCC | 46.71 | Yes | Proposal sanctioned on 30.12.2016. | Original proposal received in Jan., 2013 . File submitted to Ministry on 26.02.2014, 10.11.2014, 04.09.2015,18.04.2016 & 23.11.2016. | Project sanctioned on 30.12.2016. Commencement of construction 01.06.2018. The project is being executed by NBCC. The construction work is in full swing. Revalidation request for an amount of Rs. 5.00 Cr. and funds have been released on 6.7.2020. File submitted to Ministry through E-office on 23.12.2020 for approval of the additional works in the auditorium at a cost of Rs. 2.76 Cr. within the original sanctioned total project cost of Rs. 46.71 Cr. IFU has certain observations which have been conveyed to NACIN. | Rs. 37.85 Cr. have been released/utilized till F.Y. 2019-20. Rs. 5.00 Cr. released on 06.07.2020 in F.Y. 2020-21. FY 2021-22, Rs. 3.50 Cr. sought. | Sanctioned
2 | NACIN | NACIN Cochin 916/7/Const./RTI NACIN Munnar/HRD/18 | Const. of RTI NACIN Munnar, Kerala | CBIC / CPWD | 0.03 (Enabling works) 0.93 (For boundary wall) |  |  | Not Sanctioned | Proposal for enabling works sanctioned on 08.01.2019. Revalidation approved on 12.06.2020. Main building proposal awaited. | Rs. 2.75 lakh released in F.Y.2019-20 has not been utilized in F.Y. 2019-20. Rs. 2.75 lakhs released on 06.07.2020 in F.Y. 2020-21. F.Y. 2020-21: Rs. 47 lakh (Savings taken in RBE) F.Y. 2021-22: Rs. 1.00 Cr. (Sought for line opening) | Sanctioned | yet to sanction
3 | NACIN | RTI Hindupur/ 916/8/Const./ Hindupur/HRD/15 | Construction of New Academy of NACIN at Palasamudram (V), (Hindupur) Ananthpur Dist., Andhra Pradesh-Requirement of funds for construction of compound wall road along the boundary etc. Total land- 500 acre | CBIC/ CPWD | 15.14 | No | ___ |  | Proposal for boundary wall & gate complex involving Rs. 15.14 Cr. was sanctioned on 20.11.18. Out of total 8.4 km boundary wall 4.6 km is completed and balance is under dispute with neighbours. Required re-allignment. Proposal for consultancy services involving Rs. 1.15 Cr. was sanctioned on 16.10.19. Revalidation approved on 28.07.2020 for an amount of Rs. 4.85 Cr. for boundary wall. Revised proposal for consultancy services at a cost of Rs. 2.00 cr. submitted to Ministry for approval on 17.08.2020. Approved by Ministry on 29.01.2021. | Rs. 7.45 Cr. have been utilized till F.Y. 2019-20. Rs. 4.85 Cr. released during current FY on 07.08.2020 for construction of boundary wall. F.Y. 2020-21: Rs. 2.00 Cr .(Remaining for Consultancy work) F.Y. 2020-21: Rs. 3.00 Cr. (Savings taken in RBE) F.Y. 2021-22: Rs. 5.00 Cr. (Sought )
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Pune CGST
Pune CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Pune CGST | Pune-II/ 916/5/Const./ Pune/ HRD/2014 | Construction of office building and 02 nos. residential quarters for CGST Ranges office at Pandharpur, Distt. Solapur, Maharashtra. Total land : 2230.22 sqm. Office space :146.50 sqm. One quarter Type IV | CBIC/ CPWD | 2.05 | No | ___ | Original proposal received on 25.04.2014. Query letter sent on 27.07.2014, 29.08.2016 & 16.02.2017. followed by several reminders. Reply received on 11.12.2015, 08.02.2016 & 17.02.2017 respectively. | File sanctioned on 23.12.2019. Revalidation approved on 25.06.2020.Commisionerate vide mail dated 01.12.2020 informed that Soil testing work has been completed, demoliton work will start from 01.12.2020 and process of Local body approval is in progress. | Rs. 20.00 lakhs released on 30.12.2019. Rs. 1.31 Cr. released on 06.07.2020 in F.Y. 2020-21. | Sanctioned | Sanctioned
2 | Pune CGST | Kolhapur/ 916/21/Const. /Pune/HRD/14 | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur-reg. Land area: 12854.8 sqm. Office space : 9244.1 sqm. | CBIC/ CPWD | 42.44 | No | ____ | Original proposal received in March 2015. Query letter sent on 10.04.2015 followed by several reminders. | Proposal sanctioned on 25.06.2020. Ministry approved the release of Rs. 1.00 cr for enabling works. Rs. 1.00 cr released on 23.10.2020.Commisionerate vide mail dated 01.12.2020 informed that the work of desiging of project and floating of tender would be undertaken in january 2021. | Rs. 1.00 cr. released on 23.10.2020 | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Patna Cus.
Patna Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Patna Cus. | Patna Cus. (Prev.) 916/16/Const./Patna (P)/HRD/2016 | Proposal for construction of Residential complex at Land Customs Station jogbani, a/ a & e/s of Rs.7,99,52,000/- Total qtrs.- 21 Type wise qtrs.- Type-II=7 Type-III=12 Type-IV =02 | CBIC/ CPWD | 7.99 | No | ___ | Original proposal received on 21.11.2016. Query letter sent on 13.12.2016. Reply received, file submitted to the Ministry on 06.02.2017, IFU returned file with certain queries, file resubmitted to ministry after clarifying the queries on 10.08.2017. | Project sanctioned on 11.06.2018. Revalidiation approved on 15.10.2020. | Rs. 2.59 Cr. utilized till F.Y. 2019-20. For F.Y. 2020-21, Rs. 4.00 Cr. released on 02.11.2020. | Sanctioned | yet to sanction
2 | Patna Cus. | Patna Cus. (Prev.)/ 916/15/Const./Patna/HRD/14 | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul Total land- 2.74 acre Residential space-5,730 sqm. Total qtrs.-21 Type wise qtrs.- Type-III=06 Type-IV=14 Type-IV (Spl)=01 | CBIC/ CPWD | 11.85 | Yes | Sanctioned | Original proposal received in September 2014. Query letter sent on 17.11.2014, 25.06.2015, 20.07.2015. Reply received on 03.03.2015, 25.08.2015. File submitted to the Ministry on 08.11.2016 and 04.07.2017. | Project sanctioned on 22.09.2017. Revalidation approved on 25.08.2020. | Rs. 3.14 Cr. utilized till F.Y. 2019-20. For F.Y. 2020-21, Rs. 4.00 Cr. released on 31.08.2020. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Visakhaptnam CGST
Visakhapatnam CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Visakhapatnam CGST | Tirupati 916/55/Const./ Anantpur/HRD/ 06 | Construction of office building at Anantapur, Andhra Pradesh. Office space: 1292.70 sqm. | CBIC/ CPWD | 7.07 | No |  | Original proposal received on 06.07.2006.Revised PE received on 11.12.2015.Query letter sent on 28.11.2016, 11.04.2016, 29.07.2016, 14.12.2016 followed by reminders and DO letter dated 25.04.2017. | Proposal sanctioned on 21.12.2018. Revalidation approved by IFU on 28.09.2020. | Rs. 3.39 Cr. utilized till F.Y. 2019-20. F.Y. 2020-21 Released = Rs. 2.00 Cr. (08.10.2020) | Sanctioned | yet to sanction
2 | Visakhapatnam CGST | CGST Tirupati/ 916/4/Const./ Kurnool (A.P.)/HRD/2012 | Construction of 7 Nos. Type-IV Quarters and Guest House for Kurnool (Tirupati Comm’te), Andhra Pradesh-reg. Total Land :606.88 sqm. | CBIC/ CPWD | 3.96 | No | ____ |  | Proposal sanctioned on 10.09.2018. Revalidation approved on 25.06.2020. | F.Y. 2018-19 Released = Rs. 1.18 Cr., Utilized Rs. 20 lakhs. F.Y. 2019-20 Released = Rs. 50.00 lakhs. utilized Rs. 50 lakh F.Y. 2020-21 Released = Rs. 1.97 Cr. (06.07.2020) | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Trichy Cus.
Trichy Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Trichy Cus. | Tuticorin 916/19/ Const./ Tuticorin/HRD/14 | Construction of additional residential quarters (T-II, T-III & T-IV) at Port Area, Tuticorin. Total qtrs.- 06 Type wise qtrs.- Type-II=1 Type-III=2 Type-IV =3 | CBIC/ CPWD | 1.62 | Yes | Project in advanced stage. As this is a small project construction will be completed within 1 year. | Original proposal received on 09.11.2014. Query letter sent on 14.11.2014, 30.06.2015, 17.07.2015. File has been submitted to the Ministry on 01.09.2016. | Project sanctioned on 25.08.2017. Revalidation approved on 20.08.2020. Rs. 0.96 Cr. Two Type-III qtrs & one Type-II qtr are completed. Three Type-IV are yet to be completed as reported by the Comm'te on 20.11.2020 | F.Y. 2018-19 Released = Rs. 1.47 Cr. Utilized = Nil F.Y. 2019-20 Released = Rs. 1.47 Cr. Utilized = Rs. 0.52 Cr. F.Y. 2020-21 Released Rs. 96.00 lakh on 27.08.2020. | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14