## Ahmedabad CGST
Ahmedabad CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad CGST | Ahmedabad (North)/ 916/8/Const./ Ahmedabad/HRD/17 | Construction of new building in the Custom House Compound for CGST North Commissionerate at Ahmedabad. | CBIC/ CPWD | 31.87 |  |  |  | Project sanctioned on 11.06.2018. File submitted to Ministry for revalidation on 25.08.2020. IFU returned the file with observations regarding fund utilization and requested to reconcile the fund utlization vis-a-vis funds released. Further as the approval of building plan is pending & tender process is not yet finalized, IFU has advised to seek (i) revaildation after finalization of building plan & Tender process and (ii) to ascertain funds requirment for the current FY from CPWD. IFU's observations have been communicated to the Comm'te on 17.09.2020. Comm'te vide status report dt. 23.11.2020 has intimated that the project is stuck pending approvals of local authorities as CPWD has not factored in the parking requirements as specified by Ahmedabad Municipal Corporation. Their alternatives are not viable as the main building is almost 5 decades old. AMC has asked the Commissionerate to come up with fresh and long term viable proposal after consulting CPWD. Letter issued on 18.02.2021 to ascertain the latest updates in this matter. Reply awaited. | Rs. 5.00 cr. was released in F.Y. 2018-19, Comm'te surrendered Rs. 4.75 cr. During F.Y. 2019-20 Rs. 2.00 cr. released out of which only Rs.11.00 lakh was utilized. Rs. 50.00 lakh sought in BE 2021-22. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Ahmedabad Cus.
Ahmedabad Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad Cus. | Jamnagar (P.) 916/8/Const./ Jamnagar/HRD/16 | Construction of office building for Customs (Preventive) Commissionerate, Jamnagar; Custom Division, Jamnagar; Custom House, Jamnagar; Custom House, Vadinar, and CGST Sub Commissionerate at Jamnagar Total land- 10,250 sqm. Office space- 4131.34 sqm. | CBIC/ CPWD | 43.67 | Yes | Project in advanced stage |  | Project sanctioned on 13.12.2017. Commencement of construction 23.10.2018. A letter has been issued on 09.02.2021 to ascertain the actual tender cost of the project & fund requirement in F.Y. 2020-21 & 2021-22. Reply awaited. File submitted to the Ministry on 26.02.2021 through e-office for revalidation of sanction order for Rs. 26.00 lakh to be released in F.Y. 2020-21 | Rs. 15.97 Cr. have been utilized till FY 2019-20. Rs. 12.74 Cr.was sought during FY 2021-21 which was released on 16.06.2020. (Expenditure of Rs. 11.57 Cr. booked during current F.Y. against release of Rs. 12.74 Cr.). Expenditure till date Rs. 27.53 Cr. Addl. Funds of Rs. 6.00 Cr. sought in FY 2020-21 and Rs. 5.00 cr. in FY 2021-22. 85% of construction work has been completed. Rs. 10.00 Cr. sought in BE 2021-22. Further addl. funds of Rs. 3.00 Cr. has been sought vide letter dated 26.02.2021 over & above funds allocated in RBE 2020-21 | Sanctioned | Sanctioned
2 | Ahmedabad Cus. | Jamnagar (dwarka) 916/17/Const./Ahmedabad/HRD/18 | Construction of office building at the site of shore guard, Dwarka, Jamnagar. | CBIC/CPWD | 1.24 |  |  |  | Proposal sanctioned on 04.03.2020. Revalidated on 12.06.2020. | Rs. 50.00 lakh released on 06.07.2020 in F.Y. 2020-21. Rs. 10.00 lakh surrender under PFMS on 09.02.2021. Out of Rs. 40.00 lakhs Rs. 29.87 lakhs has been booked in PFMS as on 08.02.21. RCC works going on as reported in Nov., 2020 | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Bengaluru CGST
Bengaluru CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bengaluru CGST | Belgavi 916/15/Const. /Belgaum/ HRD/12 | Construction of office building and staff quarters for Bagalkot Range and Range D of Vijaypura Division under Belagavi CGST Comm'te Total land-01 acre Office space-1080 sqm. Residential space-465 sqm. Total qtrs.-02 Type wise qtrs.- Type-III=01 Type-IV=01 | CBIC/ CPWD | 2.19 | Yes | Project in advanced stage. Land worth Rs. 7-8 cr. which was provided free of cost will be taken back by Town Development Authority in case of non-construction.. |  | Project sanctioned on 10.01.2018. Revalidated on 18.09.2020. Date of completion of the project and status of booking of funds sought vide letter dated 29.01.2021. Telephonically status of the project was sought on 26.02.2021 is learnt that the CPWD has completed & shall be handing over shortly | Rs. 1.6 Cr. utilized till F.Y. 2019-20. For F.Y. 2020-21 remaining Rs. 50.00 lakh released on 24.09.2020. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Bengaluru Cus.
Bengaluru Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bengaluru Cus | Mangalore 202/7/2003 Ad. VIII (EC) | Providing Barbed wire fencing and Name Boards to properties belonging to Customs Department at Karwar, for Rs. 89,56,000. | CBIC/ CPWD | 0.89 | Yes | The said land is required to be protected from encroachment and this is a small project. | Original proposal received on 25.05.2016. File submitted to the Ministry on 10.11.2016, 18.01.2017 &12.05.2017. | Project sanctioned on 15.09.2017. Out of total 39 properties, fencing work has not started in 17 properties due to disputed land title, land being claimed by salt department etc. The purpose of fencing at present is to save the land from any encroachment. Fencing work is completed in 18 properties. Revalidated on 23.11.2020. | Rs. 83,44,052/- were released in 2017-18, out of which Rs. 6,11,948/- utilized in 2017-18 Rs. 14,21,578/- utilized till 2018-19. Rs. 75,34,422/- released on 12.07.2019. Rs. 45,67,778/- released on 09.12.2020. | Sanctioned | yet to sanction
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
39.14

## Chandigarh CGST
Chandigarh CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Chandigarh CGST | Jalandhar/ 916/09/Const./ Jalandhar/ HRD/16 | Construction of office cum residential qtrs.and boundary wall at Jalandhar for CGST Jalandhar Commissionerate Total land - 06 acre Total qtrs.- 116 Type wise qtrs.- Type-II=19 Type-III=62 Type-IV =32 Type-V A=01 Type-V B=01 Type-VI=01 | CPWD/ CPWD | 67.57 | Yes | Project approved by IFU. Non-construction fee will accrue if construction not started | Original proposal received on 06.09.2016. Query letter sent on 16.09.2016. Reply received on 17.11.2016.File submitted to the Ministry on 18.11.2016, 20.12.2016, 03.02.2017, 27.02.2017, 03.04.2017, 14.06.2017 & 28.07.2017. | Project was sanctioned on 4.8.2017 and being executed through MoUD funds. | Fund requirement during current F.Y. Rs. 18.00 Cr. Funds allocated & utilized during current F.Y. Rs. 5.21 Cr. | Sanctioned | yet to sanction
2 | Chandigarh CGST | Jammu 916/4/Const./Srinagar/HRD/2020 | Construction of boundary wall with concertina wire fencing around the land at Solina, Srinagar for construction of office and residential buildings of Customs & CGST Division, Srinagar | CBIC/CPWD | 4.14 |  |  |  | Proposal sanctioned on 31.07.2020. | Rs. 10.00 lakhs sought for current F.Y., released on 09.12.2020. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Chennai Cus.
Chennai Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Chennai Cus. | Chennai Cus. (Gen.) VIII / 916/03/Const./Chennai/RD/ 16 | Construction of residential qtrs. at Anna Nagar, Chennai. Total land- 1,06,086 sqm. Total qtrs.-726 Type wise qtrs.- Type-II=288 Type-III=288 Type-IV=150 | CBIC/ CPWD | 348.77 | Yes | Project approved by IFU. Presentation to be made in front of the RS | Original proposal received in Feb. 2016. .File submitted to the Ministry on 29.04.2016, 21.11.2016, 03.01.2017, 26.04.2017 & 14.08.2017. | Project sanctioned on 13.10.2017. Revalidated on 03.06.2020. Pile work of all towers of type II,III & IV are completed. Comm'te vide letter dt. 18.1.2021 has stated that addl. Rs. 52.00 Cr.are required for the project in F.Y.2020-21. | Expenditure upto F.Y. 2019-20 was Rs. 47.00 Cr. Rs. 67.00 Cr. released on 16.06.2020 out of which Rs. 66.99 Cr. has been utilized till date. Rs. 10.00 Cr. sought in supplementary grant in 2020-21 and Rs. 80.00 Cr. sought in BE 2021-22. Addl. funds of Rs. 52.00 Cr. sought by the Comm'te for F.Y. 2020-21. Accordingly, addl. funds of Rs. 42.00 Cr. has been sought vide letter dated 17.02.2021 over & above funds allocated in RBE 2020-21 which was letter on reduced to Rs. 14.40 Cr. vide letter dated 26.02.2021. | Sanctioned | Sanctioned
2 | Chennai Cus. | Chennai Cus. (Gen.)/ 916/08/Const./Chennai/HRD/2018 | Construction of 36 residential quarters (18 Type-V and 18 Type-VI) at Nungambakkam, Chennai. (Total 36 quarters) | CBIC / CPWD | 65.42 |  |  | Sanctioned | Project sanctioned 24.12.2018. Revalidated on 03.06.2020. Comm'te vid letter dt. 01.10.2020 has intimated that soil investigation & structural design completed. Date of start of completion - 27.10.2020 as reported on 08.12.2021. | Rs. 5.00 Cr. were revalidated for F.Y. 2019-20. Rs. 2.25 cr. utilized. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. Comm'te vide letter dt. 09.02.2021 has intimated that till 31.01.2021 Rs. 28.26 lakhs have been utilized during current F.Y. Comm'te has also intimated that CPWD has assured to utilize the allotted funds of Rs. 5.00 Cr. by March, 2021. Rs. 10.00 Cr. sought in BE 2021-22. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Delhi CGST
Delhi CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Delhi CGST | Delhi (North)/ 916/03/Const./ Dwarka/HRD/17 | Construction of residential qtrs. at Dwarka Total land- 17832 sqm. Total qtrs.-256 Type wise qtrs.- Type-IV=168 Type-V=52 Type-VI=36 | CBIC/ NPCC | 227 | No | ____ | This is a very old proposal. Due to deficiencies in the bidding process Revenue Secretary advised for fresh bidding on 03.04.2017. Commissionerate invited tender along with RFP on 27.04.2017. Revised proposal received on 16.06.2017. | Project sanctioned on 25.07.2018. Date of commencement of construction is 1.11.2018. Revalidated on 30.09.2020. | Rs. 71.50 Cr. have been released upto FY 2019-20 which was fully utilized till 23.9.2020. Rs. 36.00 Cr. have been released during FY 20-21. Rs. 23.01 Cr. have been booked upto Dec,20 as reported vide letter dt. 08.01.21. Total released amount till date Rs. 107.50 Cr. total utilized Rs. 94.91 Cr. upto Dec,20. Rs. 40.00 Cr. sought in BE 2021-22. | Sanctioned | yet to sanction
2 | Delhi CGST | Delhi (South)/ 916/62/Const./ Nangal Raya/HW/06 | Construction of office building at Nangal Raya, New Delhi. | CBIC/ NBCC | 32.83 |  |  |  | Proposal sanctioned on 13.06.2016. Complete amount has been released to the Comm'te. Comm'te vide letter dt. 06.02.2019 has intimated that civil work is almost completed. Further, Comm'te vide letter dt. 21.08.2020 has sought funds amounting to Rs. 3.97 Cr. for providing new load of 1408KW, justification for which was sought on 2.9.2020, as work of electric connection was already included in the final preliminary estimate approved by the Competent Authority. Reminders issued on 26.10.2020, 12.11.2020, 15.12.2020, 20.01.2021 & 23.02.2021. Reply awaited. |  | Sanctioned | Sanctioned | 33
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## DRI
DG: DRI
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | DRI | Kolkata/ 916/02/Const. /Kolkata/ HRD/2016 | Construction of DRI at Plot No. CBD-93, Action Area-II, New Town, Kolkata | CBIC/ CPWD | 64.5 | ___ |  | Not Sanctioned | Proposal sanctioned on 08.02.2019. Revalidated for Rs. 10.00 Cr. on 12.06.2020. Pile foundation work & sheet piling work completed for basement as intimated vide letter dt. 24.12.20. | Rs.1.56 Cr. have been utilized till F.Y. 2019-20. Rs. 10.00 Cr. released on 06.07.2020 in F.Y. 2020-21. Out of which Rs. 2.00 has been surrendered in PFMS Out of remaining Rs. 8.00 Cr. Rs. 3.08 Cr. has been utilized as per PFMS dt. 08.02.2021. Fund required for F.Y. 2020-21 is Rs. 20.00 Cr. Rs. 10.00 Cr. sought in BE 2021-22. | Sanctioned | Sanctioned
2 | DRI | Hyderabad 916/21/Const./DRI/ Hyderabad/ HRD/19 | Construction of office building for DRI Hyderabad Zonal Unit at Jubilee Hills at Hyderabad (Geo Technical Investigation) | CBIC/ CPWD | 0.08 |  |  |  | Proposal sanctioned on 13.03.2020. Comm'te vide letter dated 27.07.2020 has stated that Geo Technical Investigation work will be included in the main construction proposal to be sent shortly. | Rs. 0.08 lakh released on 17.03.2020. | Sanctioned | Sanctioned
3 | DRI | Lucknow 916/3/Const./DRI-Lucknow/HRD/2020 | Construction of boundary wall by DRI Zonal Unit, Lucknow | CBIC/CPWD | 0.98 |  |  |  | Proposal sanctioned on 23.03.2020. Revalidation approved on 25.06.2020. | Rs. 98.00 lakh released in F.Y. 2020-21. Out of which Rs. 58 lakhs has been surrendered in PFMS Out of remaining Rs. 40.00 lakhs Rs. 20.40 lakhs has been utilized as per PFMS dt. 08.02.2021. | Sanctioned | Sanctioned
4 | DRI Delhi | DRI (HQ), 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of boundary wall for DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 0.25 |  |  |  | Proposal sanctioned on 09.10.2019. |  | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Guwahati CGST
Guwahati CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Guwahati CGST | Agartala 916/10/Const./ Shillong/HRD/15 | Construction of office building (Audit Circle, Custom division & CGST Division) at Agartala Total land- 3022 sqm. Office space-2793 sqm. Guest House-463 sqm. | CBIC/ CPWD | 28.04 | Yes | Project in advanced stage | Original proposal received on 16.09.2015. Deficiency letter sent on 14.10.2015, 23.03.2016 & 29.08.2016. Reply received on 23.02.2016, 12.08.2016 and 29.05.2017 subsequently. | Proposal sanctioned on 18.02.2019. Revalidated on 03.06.2020. | Rs 50 Lakh released on 26.02.2019 during F.Y. 2018-19 but could not be utilized. Rs. 4.00 Cr. released in FY 2019-20 and fully utilized. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21. Expenditure during current F.Y. = Rs. 3.51 Cr. as per the PFMS dt. 08.02.2021 Addl. funds sought in FY 20-21 -- Rs. 7.00 Cr. Rs. 8.00 Cr. sought in BE 2021-22. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Hyderabad CGST
Hyderabad CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Hyderabad CGST | Hyderabad 916/14/Const./Hyderabad/HRD/16 | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | CBIC/ CPWD. | 1.3 | No | ____ | Original proposal received on 24.10.2016. File submitted to the Ministry on 14.02.2017, 02.03.2017 & 04.07.2017. Ministry returned the file with observations on 23.02.2017, 10.04.2017 & 28.08.2017. | Proposal sanctioned on 07.03.19. Comm'te vide letter dated 30.07.2020 has stated that demarcation of land is pending and no funds are required till demarcation is completed. | Rs. 10.00 lakhs were released in 2018-19 but could not be utilized Rs. 50.00 lakhs has been released on 29.07.2019. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Jaipur CGST
Jaipur CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Jaipur CGST | Udaipur/ 916/11/Const./ Jaipur-II/HRD/11 | Construction of office building CGST division Bhilwara. Land area: 1858.06 sqm. Office space : 750.00sqm. | CBIC/ CPWD | 9.72 | No | ___ | Original proposal recieved on 08.09.2014. Query letter sent on 31.10.2014, reply recieved on 15.04.2015. Query letter sent on 18.05.2015 followed by several reminders. | Proposal sanctioned on 21.02.2019. Revalidated on 25.08.2020. Construction started on 07.10.2019. | Rs 1.5 Cr. released on 26.02.2019 but could not be utilized. During 2019-20 Rs. 50.00 lakhs released on 25.07.2019. During F.Y. 2020-21 Rs. 3.00 Cr released which was fully utilized as per PFMS dt. 08.02.2021. Addl. funds required in F.Y. 2021-22 = Rs. 4.00 Cr. Rs.4.52 Cr. sought in BE 2021-22. Further addl. funds of Rs. 1.20 Cr. has been sought vide letter dated 26.02.2021 over & above funds allocated in RBE 2020-21 | Sanctioned | Sanctioned
2 | Jaipur CGST | Jodhpur/ 916/19/Const./Jodhpur/HRD/18 | Comprehensive Consultancy Services for Master Planning of Campus & Design of Office cum Residential Campus for CGST at Jodhpur | CBIC/ CPWD | 1.11 |  |  | Not Sanctioned | Proposal for Master planning has been sanctioned on 25.09.2019. Comm'te vide letter dated 27.07.2020 has stated that revalidation/funds is not required for the project for F.Y. 2020-21, till MoU is signed with Income Tax. | In F.Y. 2019-20 Rs. 10.00 lakhs have been released on 01.10.2019. | Sanctioned | yet to sanction
3 | Jaipur CGST | CGST Udaipur 916/4/Const./Udaipur/HRD/19 | Construction of new office building for Udaipur CGST Comm'te | CBIC/ CPWD | 42.07 |  |  |  | Proposal sanctioned on 09.03.2020. Revalidated on 25.06.2020. Period of completion of the project - 18 months. Construction started on 26.08.2020. | Rs. 10.00 lakh released in F.Y. 2019-20. Rs. 50.00 lakh released in F.Y. 2020-21 which was fully utilized as per PFMS dt. 08.02.2021. Addl. funds sought in FY 20-21 -- Rs. 7.50 Cr. Accordingly, addl. funds of Rs. 5.00 Cr. has been sought vide letter dated 26.02.2021 over & above funds allocated in RBE 2020-21. Rs. 8.00 Cr. sought in BE 2021-22. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Lucknow CGST
Lucknow CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Lucknow CGST | Agra/ 916/05/Const./Agra/HRD/2018 | Construction of conference hall in the building of CGST Comm'te Agra. | CBIC/ CPWD | 0.12 |  | Proposal is under process at DGHRD |  | Project sanctioned on 13.08.19. Revalidated on 18.09.2020. | Project completed | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Meerut CGST
Meerut CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Meerut CGST | CGST Ghaziabad & 916/5/Const./ Meerut/HRD/17 | Construction of office building including boundary wall and culvert over Nala at allotted land measuring 2.21 acres (8894 sqm.) to CGST Ghaziabad, Audit-II, Ghaziabad, Noida | CBIC/ CPWD | 116.42 |  |  |  | Project sanctioned on 03.10.19. Revalidation approved on 03.06.2020. As per status report submitted by the Comm'te vide letter dt. 12.11.2020 work related to construction of boundary wall is almost completed and as regards culvert over nala, work is held up as permission is required from forest department for cutting of green trees. The foundation stone for the buidlng was laid down by the Chairman, CBIC on 18.02.2021. | Rs. 1.00 cr. released on 14.10.2019 in F.Y. 2019-20, out of which Rs. 53,500/- were utilized. Rs. 5.00 Cr. released on 16.06.2020 in F.Y. 20-21, out of which Rs. 3.00 Cr. has been surrendered on 04..02.21. Out of remaining Rs. 2.00 Cr. Rs.0.52 Cr. has been utilized as per PFMS dt. 08.02.2021. Rs. 10.00 Cr. sought in BE 2021-22. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Mumbai CGST
Mumbai CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai CGST | Raigad 911/4/Misc./Kharghar/HRD/15 | Construction of residential qtrs. at Kharghar by NBCC. Total land- 20,000.32 sqm. Total qtrs.-187 Type wise qtrs.- Type-II=42 Type-III=70 Type-IV=44 Type-IV (Spl)=20 Type-V=09 Type-VI=02 | CBIC/ NBCC | 110.11 | Yes | Project in advanced stage. |  | Proposal sanctioned on 18.04.2019. Revalidated for Rs. 22.00 Cr. on 25.06.2020, Work Commenced on 10.02.2020. Construction work is in full swing and completed upto plinth beam level as reported by the Comm'te. | Rs. 21.01 Cr. released in FY 2019-20. Rs 22.00 cr. were released on 27.08.2020. Out of which Rs. 7.62 Cr. have been transferred to NBCC on 23.11.2020. Expenditure bill amount in Rs. 9.46 Cr. submitted by M/s NBCC are under process Addl. funds sought in FY 20-21 Rs. 25.11 Cr. Rs. 25.00 Cr. sought in BE 2021-22. | Sanctioned
2 | Mumbai CGST | Palghar 916/5/Const./ Mumbai/HRD/ 16 | Construction of 3 Div. offices and 14 ranges offices on plot bearing Nos P-34 at MIDC, Boisar-reg. | CBIC/ CPWD | 33.25 | No | ____ |  | Proposal sanctioned on 01.07.19. Revalidated on 25.06.2020. Comm'te vide letter dt. 28.9.2020 has intimated that the tender process has been completed and tender has been awarded. CPWD has been requested to get the plan approved. Bhoomi Pujan & commencement of construction work of the projec has commenced on 27.02.2021. | Rs. 1.00 Cr. released on 19.07.19. Out of which Rs. 12.60 lakhs utilized. Rs. 5.00 Cr. released on 19.08.2020 in F.Y. 2020-21. Rs. 3.00 Cr. have been surrendered in PFMS. Out of remaining Rs. 2.00 Cr. Rs. 14.29 lakhs has been utilized as per PFMS dt. 08.02.2021 Rs. 10.00 Cr. sought in BE 2021-22. | Sanctioned | Sanctioned
3 | Mumbai CGST | Thane 916/15/Const./Thane/HRD/2018 | Proposal for payment of total station survey and GEO Technical Investigation (Soil Investigation) at Thane | CBIC / CPWD | 0.03 |  |  | Not Sanctioned | Proposal sanctioned on 04.10.2019. Revalidation request/ status of project awaited from the Comm'te, reminder sent on 13.07.2020. | Fund amounting to Rs. 3,23,363/- released on 16.10.19. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Mumbai-I Cus.
Mumbai-I Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai Zone-I Customs | Mumbai (Gen.) 911/3/Custom Enclave/Mumbai/ HRD/16 | Construction of Office complex and residential quarters at Customs Enclave Plot, Wadala, Mumbai through CPWD at a cost of Rs. 495.5 Cr. for office complex and Rs. 480 cr. For residential complex Office space 30000sqm. Total qtrs. -769 | CBIC/ CPWD | 975.72 | Yes | Project is being developed on self-sustaining basis. All the offices of GST Excise, DRI, DGCEI etc. will be relocated in the said project. | This land was given free of cost by the Salt Department 1980's. Due to the construction of roads we now have 46 acres encrochment free land where godowns exist. Initially it was thought that Govt. will pay for the construction which was to be done by CPWD. However, with the approval of Revenue Secretary it has been deceided to nominate NBCC to construct the office building and residential quarters without any cost to the Govt. The cost of construction only is likely to be Rs. 2700 crores. | Proposal Sanctioned on 11.11.2019. Revalidated on 31.07.2020. Commissionerate vide letter dated 15.01.2021 informed that the presentation by bidders for evaluation of techinical bid stage - II was held & the tentative date for award of work is 11.03.2021 and the expected date for completion of the project is 24.11.2024. | Rs. 5.00 Cr. (Rs. 2.50 Cr. for office & Rs. 2.50 Cr. for residence) released on 11.11.2019. Rs. 30.00 Cr. released on 13.08.2020 (Rs.15 Cr. for 4059 & Rs.15 Cr. for 4216). Out of Rs. 30 Cr. released during current F.Y. Rs. 29.67 Cr. have been surrendered under PFMS. Out of remaining Rs. 33 lakhs Rs. 9.33 lakhs have been utilized. Rs. 10.00 Cr. (Rs. 5.00 Cr. for MH-4059 & Rs. 5.00 Cr. for MH-4216) sought in BE 2021-22. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## NACIN
NACIN
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | NACIN | Hyderabad NACIN 916/02/Const./ Hyderabad/ HRD/13 | Construction of RTI, NACIN, at Attapur, Hyderabad Total built up area- 11940 sqm. | CBIC/ NBCC | 46.71 | Yes | Proposal sanctioned on 30.12.2016. | Original proposal received in Jan., 2013 . File submitted to Ministry on 26.02.2014, 10.11.2014, 04.09.2015,18.04.2016 & 23.11.2016. | Project sanctioned on 30.12.2016. Commencement of construction 01.06.2018. The project is being executed by NBCC. The construction work is in full swing. Revalidation request for an amount of Rs. 5.00 Cr. and funds have been released on 6.7.2020. File submitted to Ministry through E-office on 23.12.2020 for approval of the additional works in the auditorium at a cost of Rs. 2.76 Cr. within the original sanctioned total project cost of Rs. 46.71 Cr. IFU has certain observations which have been conveyed to NACIN. | Rs. 37.85 Cr. have been released/utilized till F.Y. 2019-20. Rs. 5.00 Cr. released on 06.07.2020 which is yet to be transferred to the M/s NBCC as reported by NACIN Attapur vide letter dt. 08.02.2021. Rs. 3.50 Cr. required in F.Y. 2021-22 and the same are sought in BE 2021-22. | Sanctioned
2 | NACIN | NACIN Cochin 916/7/Const./RTI NACIN Munnar/HRD/18 | Const. of RTI NACIN Munnar, Kerala | CBIC / CPWD | 0.03 (Enabling works) 0.93 (For boundary wall) |  |  | Not Sanctioned | Proposal for enabling works sanctioned on 08.01.2019. Revalidated on 12.06.2020. Main building proposal awaited. | Rs. 2.75 lakh released in F.Y.2019-20 not utilized in F.Y. 2019-20. Rs. 2.75 lakhs released on 06.07.2020 in F.Y. 2020-21. F.Y. 2020-21: Rs. 47 lakh (Savings taken in RBE out of Rs. 50.00 lakh sought in BE) | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Pune CGST
Pune CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Pune CGST | Pune-II/ 916/5/Const./ Pune/ HRD/2014 | Construction of office building and 02 nos. residential quarters for CGST Ranges office at Pandharpur, Distt. Solapur, Maharashtra. Total land : 2230.22 sqm. Office space :146.50 sqm. One quarter Type IV | CBIC/ CPWD | 2.05 | No | ___ | Original proposal received on 25.04.2014. Query letter sent on 27.07.2014, 29.08.2016 & 16.02.2017. followed by several reminders. Reply received on 11.12.2015, 08.02.2016 & 17.02.2017 respectively. | Proposal sanctioned on 23.12.2019. Revalidated on 25.06.2020.Commisionerate vide mail dated 01.12.2020 informed that Soil testing work has been completed, demoliton work will start from 01.12.2020 and process of Local body approval is in progress. | Rs. 20.00 lakhs released on 30.12.2019. Rs. 1.31 Cr. released on 06.07.2020 in F.Y. 2020-21, out of which Rs. 0.01 Cr. utilized as of now. | Sanctioned | Sanctioned
2 | Pune CGST | Kolhapur/ 916/21/Const. /Pune/HRD/14 | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur-reg. Land area: 12854.8 sqm. Office space : 9244.1 sqm. | CBIC/ CPWD | 42.44 | No | ____ | Original proposal received in March 2015. Query letter sent on 10.04.2015 followed by several reminders. | Proposal sanctioned on 25.06.2020. Ministry approved the release of Rs. 1.00 cr for enabling works. Rs. 1.00 cr released on 23.10.2020.Commisionerate vide mail dated 01.12.2020 informed that the work of desiging of project and floating of tender would be undertaken in January 2021. Rs. 6.00 Cr. sought in BE 2021-22. | Rs. 1.00 cr. released on 23.10.2020 | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Patna Cus.
Patna Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Patna Cus. | Patna Cus. (Prev.) 916/16/Const./Patna (P)/HRD/2016 | Proposal for construction of Residential complex at Land Customs Station jogbani, a/ a & e/s of Rs.7,99,52,000/- Total qtrs.- 21 Type wise qtrs.- Type-II=7 Type-III=12 Type-IV =02 | CBIC/ CPWD | 7.99 | No | ___ | Original proposal received on 21.11.2016. Query letter sent on 13.12.2016. Reply received, file submitted to the Ministry on 06.02.2017, IFU returned file with certain queries, file resubmitted to ministry after clarifying the queries on 10.08.2017. | Project sanctioned on 11.06.2018. Revalidated on 15.10.2020. As per PE period of completion is 16 months. | Rs. 2.59 Cr. utilized till F.Y. 2019-20. For F.Y. 2020-21, Rs. 4.00 Cr. released on 02.11.2020. Rs. 1.00 Cr. sought in BE 2021-22. | Sanctioned | yet to sanction
2 | Patna Cus. | Patna Cus. (Prev.)/ 916/15/Const./Patna/HRD/14 | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul Total land- 2.74 acre Residential space-5,730 sqm. Total qtrs.-21 Type wise qtrs.- Type-III=06 Type-IV=14 Type-IV (Spl)=01 | CBIC/ CPWD | 11.85 | Yes | Sanctioned | Original proposal received in September 2014. Query letter sent on 17.11.2014, 25.06.2015, 20.07.2015. Reply received on 03.03.2015, 25.08.2015. File submitted to the Ministry on 08.11.2016 and 04.07.2017. | Project sanctioned on 22.09.2017. Revalidated on 25.08.2020. As per PE period of completion is 24 months. | Rs. 3.14 Cr. utilized till F.Y. 2019-20. For F.Y. 2020-21, Rs. 4.00 Cr. released on 31.08.2020. Out of which Rs. 1.70 Cr. utilized. Rs. 6.00 Cr. sought in BE 2021-22. | Sanctioned | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Visakhaptnam CGST
Visakhapatnam CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Visakhapatnam CGST | Tirupati 916/55/Const./ Anantpur/HRD/ 06 | Construction of office building at Anantapur, Andhra Pradesh. Office space: 1292.70 sqm. | CBIC/ CPWD | 7.07 | No |  | Original proposal received on 06.07.2006.Revised PE received on 11.12.2015.Query letter sent on 28.11.2016, 11.04.2016, 29.07.2016, 14.12.2016 followed by reminders and DO letter dated 25.04.2017. | Proposal sanctioned on 21.12.2018. Revalidated on 28.09.2020. | Rs. 3.39 Cr. utilized till F.Y. 2019-20. F.Y. 2020-21 Released = Rs. 2.00 Cr. (08.10.2020). Addl. funds required in current F.Y. 1.30 Cr. Rs. 2.00 Cr. sought in BE 2021-22. Building is 97% completed & traget date of completion is March 2021. | Sanctioned | yet to sanction
2 | Visakhapatnam CGST | CGST Tirupati/ 916/4/Const./ Kurnool (A.P.)/HRD/2012 | Construction of 7 Nos. Type-IV Quarters and Guest House for Kurnool (Tirupati Comm’te), Andhra Pradesh-reg. Total Land :606.88 sqm. | CBIC/ CPWD | 3.96 | No | ____ |  | Proposal sanctioned on 10.09.2018. Revalidated on 25.06.2020. | F.Y. 2018-19 Released = Rs. 1.18 Cr., Utilized Rs. 20 lakhs. F.Y. 2019-20 Released = Rs. 50.00 lakhs. utilized Rs. 50 lakh F.Y. 2020-21 Released = Rs. 1.97 Cr. (06.07.2020) Building is 80% completed & traget date of completion is March, 2021. | Sanctioned | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Trichy Cus.
Trichy Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Trichy Cus. | Tuticorin 916/19/ Const./ Tuticorin/HRD/14 | Construction of additional residential quarters (T-II, T-III & T-IV) at Port Area, Tuticorin. Total qtrs.- 06 Type wise qtrs.- Type-II=1 Type-III=2 Type-IV =3 | CBIC/ CPWD | 1.62 | Yes | Project in advanced stage. As this is a small project construction will be completed within 1 year. | Original proposal received on 09.11.2014. Query letter sent on 14.11.2014, 30.06.2015, 17.07.2015. File has been submitted to the Ministry on 01.09.2016. | Project sanctioned on 25.08.2017. Revalidated on 20.08.2020. Two Type-III qtrs & one Type-II qtr are completed. Three Type-IV are yet to be completed as reported by the Comm'te on 20.11.2020 | F.Y. 2018-19 Released = Rs. 1.47 Cr. Utilized = Nil F.Y. 2019-20 Released = Rs. 1.47 Cr. Utilized = Rs. 0.52 Cr. F.Y. 2020-21 Released Rs. 96.00 lakh on 27.08.2020. Rs. 43.81 lakh have been utilized during current F.Y. 80% work completed. Project is likely to be completed in next F.Y. as informed verbally on 15.02.2021. | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14