## Ahmedabad CGST
Ahmedabad CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad CGST | Bhavnagar / 916/21-A/Const./Bhavnagar/HRD /11 | Construction of office building for CGST Commissionerate and Customs Division at Bhavnagar Total land- 7104 sqm. Office space-4807.50 sqm. | CPWD/ CPWD | 40.61 | Yes | Project in advanced stage and funds will be provided by CPWD. | Original proposal received on 16.01.2014. Query letter sent on 04.03.2014 & 22.12.2014. Reply received on 19.11.2014 & 17.10.2016. File submitted to the Ministry on 09.01.2017 & 12.05.2017. | Project sanctioned on 30.08.2017. But due to change in PAR 2019, a revised proposal was forwarded by the Comm'te, which was submitted to the Min. for a/a & e/s for the increased amount on 26.02.2020. Financial Advisor upon consultation with Revenue Secretary has advised on 16.04.2020 to keep the proposal in abeyance for the time being. Conveyed to the Comm'te, also informed the COVID-19 financial constraints. The file was submitted to the Ministry on 23.12.2020 for reconsidering the proposal. As discussed with FA, file is to be submitted in the first week of March, 2021 | CPWD FUNDS | With Ministry | Sanctioned
2 | Ahmedabad CGST | Ahmedabad (Audit) 916/13/Const./Ahmedabad/HRD/2019 | Construction of office premises on land measuring 3972.22 sqm. of final plot No. 175 of TP No. 3 of the commissioner of CGST (Audit), Ahemedabad. | CBIC | 75 |  |  |  | Proposal was received on 15.07.19 alongwith two PEs (CPWD & NBCC). DGHRD raised queries reg. non.encumbrance certificate, the PE to be taken up etc. and the same were conveyed to the Comm'te on 26.12.2019. After clarifications file submitted to the Min. on 01.05.2020. IFU vide note dated 27.05.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te on 03.06.2020. |  | IFU has turned down the proposal | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Ahmedabad Cus.
Ahmedabad Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ahmedabad Cus. | Jamnagar 916/17/Const./Jamnagar (Res.)/HRD/19 | Construction of Staff quarters at Jamnagar | CBIC/CPWD | 18.86 |  |  |  | Proposal received on 09.09.19. Savings of HRA of the staff/officers has not informed accordingly query letter issued on 09.10.19. File submitted to the Min. on 17.01.2020. File returned back by Min. with observations reg.cost of const. per flat, area of quarters etc. communicated to the Comm'te on 05.03.2020. Incomplete reply received in September, 2020, further clarifications regarding sq.ft.cost of construction, area of T-VI qtrs.etc. sought vide letter dated 01.10.2020. Reminder issued on 27.11.2020. |  | With Ministry | With Ministry
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Bengaluru CGST
Bengaluru CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bengaluru CGST | Belgavi / 916/8/Const./Belgaum/ HRD/13 | Construction of office building and staff quarters at Belgaum (Gulbarga Division)-reg. Office space: 191.16 sqm. Total Quarters =04 Type II=01 Type III=02 Type IV= 01 | CBIC/ CPWD | 3.36 | No | ____ | Original proposal received on 11.02.2013. Deficiency letter sent on 05.04.2013 followed by several reminders. Revised proposal received on 27.12.2016. Query letter sent on 10.03.2017. | Revised proposal received on 28.01.2019. File submitted to the Ministry on 19.03.2020. IFU vide note dated 22.05.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te on 03.06.2020. |  | With Ministry | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Bengaluru Customs
Bengaluru Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bengaluru Cus | Bengaluru (Airport) 916/16/Const./ Bengaluru/HRD/ 2019 | Construction of new customs House Building at bengaluru International Airport | CBIC/CPWD | 57.37 |  |  |  | Fresh proposal was received in October, 2019 After clarifications of queries of DGHRD, file was submitted to Min. on 20.01.2020. File returned back by the Min. with certain observations reg. calculation of space, cost per sq. ft., cost benefit analysis etc. which where conveyed to the Comm'te on 11.03.2020. Followed by reminders on 05.06.2020, 09.07.2020. Reply received and file sent to Ministry on 13.08.2020 for approval. IFU again has made certain observations and advised not to take up the proposal in current FY due to financial constraints because of COVID-19. Communicated to the Commissionerate on 02.10.2020. Reply awaited. |  | With Ministry | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Bhubaneshwar CGST
Bhubaneshwar CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Bhubaneshwar CGST | Bhubaneswar/ 916/12/Const. /Bhubaneswar/ HRD/14 | Const. of Retaining wall and Approach Road and from the main road to the office plot at Bagbrindaban Mauja of Balasore Town in state of Odisha. | CBIC/ CPWD | 1.57 | No | ____ | Original proposal received in September 2014. Query letter sent on 29.12.2014, 03.12.2015 & 23.08.2016. followed by several reminders. | CPWD has submitted a revised P.E for Rs 1.57 Cr. File submitted to the MInistry for a/a & e/s on 26.12.2019. File received back from the Min. with observations reg.ofice space, approach road etc. Communicated to Comm'te on 14.02.2020. Reminders sent on 11.06.2020, 13.07.2020 & 02.12.2020. Reply awaited |  | IFU query | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Chennai Cus.
Chennai Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Chennai Cus. | Chennai 916/12/Const/Jaffer Syarang-Chennai/HRD/19 | Construction of office accomodation building for Chennai Customs Audit and Import Comm'te and Partner Govt. Agenciesat Jaffer Syarang Street, Chennai. | CBIC/ CPWD | 86.75 |  |  |  | Proposal was received in July, 2019. . IFU vide note dated 20.07.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te. on 21.07.2020. Based on the justification submitted by the Comm'te , the file is re-submitted to Ministry for a/a & e/s on 23.12.2020 through E-office. |  | IFU query
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## DRI
DG: DRI
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | DRI | Chennai 916/02/Const./DRI Chennai/HRD/2020 | Construction of office building of DRI Zonal Unit at Trustpuram Kodambakkam, Chennai | CBIC/ CPWD | 31.38 |  |  |  | Proposal received on 05.02.2020. IFU vide note dated 18.05.2020 returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. DRI Chennai again requested to reconsider the proposal in the current F.Y. 2020-21, file submitted to Ministry for approval on 23.11.2020. IFU raised certain observations reg. plinth area & sanctioned/working strength, same communicated to Comm'te on 22.01.2021. Based on the clarification submitted by DRI Chennai, file re-submitted to Ministry on 11.02.2021 through E-office. |  | IFU query | Sanctioned
2 | DRI Delhi | DRI (HQ), 916/15/Const./Vasant Kunj (DRI)/HRD/19 | Construction of office building for DRI (HQ.) at Vasant Kunj, Delhi | CBIC/CPWD | 77.86 |  |  |  | Proposal received on 23.03.2020. File submitted to the Ministry for approval on 25.08.2020. IFU raised observations reg. space calculations, budget availablity etc. conveyed to DRI on 01.10.2020. DRI Delhi (HQ.) again requested to reconsider the proposal in the current F.Y. 2020-21, file submitted to Ministry for approval Ministry on 09.12.2020 through e-office. |  | IFU query
3 | DRI | Lucknow/ InW/CONS/OFF/1/ 2021 | Construction of DRI Lucknow Zonal Unit office at Plot No. 07/13-B-2, Gomti Nagar Extension, Lucknow - reg. | CBIC/ CPWD | 35.22 |  |  |  | Proposal received on 16.12.2020. After scrutiny of the proposal, DGHRD raised certain observations reg. space requirement, working strength, cost benefit analysis etc. communicated to DRI on 04.02.2021. Repy awaited. |  | DGHRD query

## Guwahati CGST
Guwahati CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Guwahati CGST | Dibrugarh 916/4/Const./ Shillong/HRD/15 | Construction of office cum residential qtrs. at Dibrugarh. Total office space: 3562 sqm. Total quarters: 56 (Type-II 14, Type-III 28 & Type-IV 14) | CBIC/ CPWD | 60.37 | No | ____ | Original proposal received on 04.09.2015. Deficiency letter sent on 22.09.2015 followed by several reminders. Do letter to forward consolidated proposal sent on 22.03.2017. | The proposal was submitted to the Ministry on 21.05.2018. IFU had made some observations regarding budget head, cost index, carpet area and the same were conveyed to Comm'te on 12.09.19. Incomplete reply received, Comm'te vide letter dated 14.01.2020 was again requested to submit a proper reply. Reminders sent on 16.07.2020, 04.12.2020 & 23.02.2021. |  | IFU query | Sanctioned
2 | Guwahati CGST | Imphal (Manipur) 916/3/Const./Shillong/HRD/19 | Const. of office building and boundary wall at Lamphel at Imphal Shillong | CBIC/CPWD | 46.4 |  |  |  | Proposal was received on 16.09.2019. In the meantime, a reference was received from Sh. Bhabananda Singh, M.P. (Rajya Sabha) for allotting this work to MANIDCO. After clarification from the Comm'te and based on its reply the proposal was processed for awarding the work to State PWD. Accordingly, the proposal was forwarded to Min. for a/a & e/s on 07.01.2020. File returned back by IFU with certain observations reg. revenue collection,cost benefit analysis, built up area, per sq.ft. cost of const. communicated to the Comm'te on 05.03.2020. Reminder issued on 21.09.2020 & 01.12.2020. |  | IFU query | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Hyderbad CGST
Hyderabad CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Hyderabad CGST | Secunderabad/ 916/13/Const./ Hyderabad/HRD/15 | Completion of 287 unfinished Dept. qtrs taken over from M/s Sri Durga Estate Pvt. Ltd. at Hyderabad | CBIC/ NBCC | 49.75 | Yes | MoU has been approved by Ministry. 287 Qtrs. in dilapidated condition will become habitable on the nominal cost of Rs. 21.3 Cr. (approx.) | Original proposal received on 02.11.2015.Miinistry gave concurrence to appoint NBCC as PMC on 24.12.2015. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Comm'te vide letter dt. 01.12.2020 has submitted only Preliminary Estimate of Rs. 65,27,60,633/- prepared by NBCC for construction of office cum resdential. Comm'te vide letter dt.17.12.2020 has requested to submit consolidated proposal with justification for selecting NBCC. Reply awaited. | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Funds released on 20.09.2018. | IFU query | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Jaipur CGST
Jaipur CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Jaipur CGST | Jaipur 916/2/Const. Jaipur/HRD/19 | Dismantling and reconstruction of T-VI/3 Bunglow at C.Ex. Officers residence colony, JLN Marg, Jaipur | CBIC/ CPWD | 2.07 |  |  |  | Proposal for const. of RCC wall for Rs. 1.11 Cr. sanctioned on 09.01.2020. Revalidated on 18.09.2020. Proposal for demolition of the existing flat for Rs. 0.05 Cr. sanctioned on 19.05.2020. Based on the justification submitted by the Comm'te for construction of T-VI qtrs., the file submitted to Ministry for a/a & e/s on 23.12.2020 through E-office. IFU raised observations regarding demand survey etc. communicated to Comm'te on 28.01.2021. Reply awaited. | Rs. 5.00 lakh released on 14.09.2020. Rs. 1.11 cr. released on 25.09.2020 | Member query | yet to sanction
2 | Jaipur CGST | Udaipur 916/1/Const./HRD/2018 | Proposal for repair/renovation and upgradation of staff houses at Udaipur. | CBIC / CPWD | 2.6 |  |  | Not Sanctioned | Fresh proposal was received on 08.04.2019 IFU vide note dated 24.06.2020 has returned the file advising not to take up the work of retrofitting as it is on the higher side, so this proposal may be taken up at the a later stage. Further the special repairs of 22 quarters at a cost of Rs. 2.60 Cr. is also on the higher side. IFU has advised to review the cost of special repairs and submit the proposal for repair of urgent nature only. Accordingly, Comm'te vide letter dt. 01.02.2021 submitted a revised proposal for special repair of 22 qtrs. which has been processed and submitted to Ministry for a/a & e/s on 22.02.21 through e-office. |  | RS has turned down the proposal
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Lucknow CGST
Lucknow CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Lucknow CGST | Agra 916/5/Const./Aligarh/HRD/19 | Const. of new office building for CGST Division at Aligarh. | CBIC/CPWD | 11.34 |  |  |  | File submitted to the Ministry on 20.02.2020 and observations reg. space calculation etc. made by IFU were communicated to comm'te on 11.05.2020. Last reminder sent on 12.11.2020 . |  | IFU turned down the proposal | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Mumbai-II Cus
Mumbai-II Customs
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Mumbai-II Cus. | Nhava Sheva (Gen.) 916/17/Const./ Raigad/HRD/16 | Construction of additional office building (G+7) (To provide more space to officers of Mumbai Zone-II) at JNCH NHAVA SHEVA Dist. Raigad-Mumbai Available area - 14900 sqm. Office space - 8551.80 sqm. | CBIC/ CPWD | 80.61 | No | ___ | Original proposal received in nov. 2016. Query letter sent on 13.12.2016 followed by several reminders and DO letters. | Proposal for enabling works (Rs 51 Lakh) was sanctioned in March, 2018. Proposal for office sanctioned on 14.02.2019. Comm'te vide letter dt. 29.12.2020 has intimated that pre-construction activities like soil investigation, digital survey. But as per survey soil investigation carried out by IIT, Bombay the soil condition in this area has been found to be extremely poor with marine clay starting from just 3m below the existing ground level, as such CPWD has advised to review the project. Accordinglt, a revised proposal amounting to Rs.80.61 Cr. has been submitted by the Comm'te on 01.02.2021 which has been processed and submitted to Ministry through e-office for a/a & e/s on 25.02.2021. | Rs. 43 lakh for enabling works was released on 19.07.2019. Rs. 5.00 Cr. sought in BE 2021-22. | IFU turned down the proposal | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## NACIN
NACIN
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | NACIN | RTI Hindupur/ 916/8/Const./ Hindupur/HRD/15 | Construction of New Academy of NACIN at Palasamudram (V), (Hindupur) Ananthpur Dist., Andhra Pradesh-Requirement of funds for construction of compound wall road along the boundary etc. Total land- 500 acre | CBIC/ CPWD | 15.14 | No | ___ |  | Proposal for boundary wall & gate complex involving Rs. 15.14 Cr. was sanctioned on 20.11.18. Out of total 8.4 km boundary wall 4.6 km is completed and balance is under dispute with neighbours and requires re-allignment. Proposal for consultancy services involving Rs. 1.15 Cr. was sanctioned on 16.10.19. Revalidation approved on 28.07.2020 for an amount of Rs. 4.85 Cr. for boundary wall. Revised proposal for consultancy services at a cost of Rs. 2.00 cr. approved by Ministry on 29.01.2021. | Rs. 7.45 Cr. have been utilized till F.Y. 2019-20. Rs. 10.00 Cr. sought in BE 2020-21, out of which Rs. 4.85 Cr. released during current FY on 07.08.2020 for construction of boundary wall. Out of Rs. 4.85 Cr. Rs. 1.50 Cr. are to be surrendered, accordingly, Rs. 3.35 Cr. sought in RBE 2020-21. Rs. 5.00 Cr. sought by project owner for F.Y. 2021-22 accordingly, Rs. 5.00 Cr. sought in BE 2021-22. | IFU has turned down the proposal | Sanctioned
2 | NACIN | NACIN Chennai 916/5/Const./ Chennai/ HRD/ 15 | Const. of NACIN Complex at Nolambur, Chennai-reg. | CBIC/ UPRNN | 79.8 | No | ___ | Land measuring 3.26 acre was acquired in 16.02.2015. Formal proposal awaited. | File was submitted to the Ministry for approval on 04.03.2020. IFU vide note dated 06.05.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. Further, it has advised to utilize the existing NACIN/RTI premises for training purposes. IFU obeservation communicated on 26.05.2020 | F.Y. 2020-21: Rs. 50 lakh (Provisioned) F.Y. 2020-21: Rs. 40 lakh (Savings taken in RBE) F.Y. 2021-22: Rs. 10 lakh (Sought for line opening) | IFU has turned down the proposal | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Nagpur CGST
Nagpur CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Nagpur CGST | Nagpur-I 916/18/Const./Nagpur/HRD18 | Const. of 6 nos. of T-VI qtrs.for Central Excise at B.No. 12, Seminary Hills, Nagpur Internal Water Supply, Sanitary Installation, Drainage and Internal Electrical Works involving an expenditure of Rs. 734.63 lakhs. | CBIC / CPWD | 7.35 |  |  | Not Sanctioned | Proposal received and submitted to the Min. on 15.07.19 for approval. IFU vide note dated 23.06.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to CC Nagpur letter dated 06.07.2020. |  | IFU has turned down the proposal
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Pune CGST
Pune CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Pune CGST | Goa/ 916/1/Const./Goa/HRD/2019 | Redevelopment of 52 nos. of staff quarters and community centre for CGST Goa Commissionerate, Goa at Alto-porvorim | CBIC /CPWD | 27.16 |  |  |  | File was submitted to the Min. on 08.01.2020. File receievd back from IFU with certain observations reg. GRIHA norms, cost of const. of per flat, cost index etc., which were conveyed to the Comm'te on 28.02.2020. Reminder sent on 21.09.2020 & 27.11.2020. |  | IFU has turned down the proposal
2 | Pune CGST | Goa Cus. 916/10/Const./Goa/HRD/17 | Construction of addl. staff quarters for Customs Department at Customs Colony, Headland Sada, Marmagoa, Goa. | CBIC/ CPWD | 37.28 |  |  |  | Proposal for demolition of dilapidated RCC overhead tank sanctioned on 16.01.2020. Acoordingly, Rs. 2,39,000/- released on 27.01.2020. In view of limited fund availability due to COVID-19 pandemic IFU vide note dated 29.05.2020 has turned down the main construction proposal. Conveyed to Comm'te on 08.06.2020. Revalidation of Rs. 2,39,000/-, approved on 20.08.2020. | Rs. 2,39,000/- released on 27.08.2020. | IFU has turned down the proposal | yet to sanction
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Ranchi CGST
Ranchi CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Ranchi CGST | Ranchi InW/CONS/OFF/3/ 2021 | Proposal for (i) Topographical Survey & Soil Investigation and (ii) Construction of boundary wall, main gate & guard room at HEC area, Nagri, Ranchi | CBIC/ CPWD | 2.45 |  |  |  | The proposal for (i) Topographical Survey & Soil Investigation (Rs. 91,200/-) and (ii) Construction of boundary wall, main gate & guard room (Rs. 1,54,63,000/-) at HEC area, Nagri, Ranchi received vide letter dt. 25.01.2021 has been processed and submitted to Ministry through e-office on 24.02.2021 for a/a & e/s. |  | DGHRD query
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14

## Visakhapatnam CGST
Visakhapatnam CGST
S. No. | Zone | Commissionerate/ File Number | Proposal in brief | Funds/ Const. Agency | Cost of Project (Rs. in Cr.) | Whether feasible or not in 2017-18 | Reason for feasibility | History of proposal | Present Status | Funds status
1 | Visakhapatnam CGST | Cus. (P.), Vijaywada 916/15/Const./Visakhapatnam/HRD/16 | Const. of buildings for newly formed Customs Comm'te (P.), Vijaywada-HQRS. Office Complex and Residential Quarters at Sy. No. 29/8 (3.84 acres) of Kesarpally Village of Gannavaram Mandal of Krishna Dist. Andhra Pradesh | CBIC / NBCC | 65.49 |  |  | Not Sanctioned | Revised proposal received on 01.03.2019, proposing to award this work to NBCC the proposal was submitted to Min. for a/a & e/s. While perusing Member (Admn.) returned the file and asked to Comm'te to get in writing a letter from CPWD showing their inability before awarding this work to NBCC. Comm'te vide letter dated 09.12.2020 has intimated that they have taken up the matter with CPWD for PE & drawings, reply from CPWD is awaited. |  | IFU has turned down the proposal | Sanctioned
2 | Visakhapatnam CGST | Tirupati/ 916/06/Const./Tirupati/HRD/2015 | Construction of office building and staff quarters at Tirupati | CBIC / CPWD | 57.06 |  |  | Not Sanctioned | Earlier, Revenue Secretary on 22.06.2017 made observations regarding PPP Model, Cost benefit analysis etc. Comm'te withdrew the proposal. Revised proposal was submitted to the Ministry and Revenue Secretary upon discussing the proposal with FA has disagreed the proposal on 20.02.2020. The same were conveyed to the Comm'te on 16.03.2020. Tirupati Comm'te vide letter dated July, 2020 stated that to protect the land from encrochment & returning of land to State Govt. urgent need of const. of boundary wall is felt. Letter sent to Comm'te on 06.07.2020 requesting to submit seprate PE for boundary wall at the earliest. |  | IFU has turned down the proposal | Sanctioned
3 | Visakhapatnam CGST | Guntur/ 916/11/Const./Guntur/HRD/18 | Construction of office building at Eluru (A.P.) | CBIC / CPWD | 6.95 |  |  | Not Sanctioned | File was submitted to Min. for approval on 14.01.2020. File returned by the Min. on 28.02.2020 with certain queries reg. per sq. ft. cost, layout plan etc. & has also dropped the proposal due to very less rental outgo at present which were conveyed to the Comm'te on 05.03.2020. Reminder sent on 05.06.2020. |  | IFU has turned down the proposal | Sanctioned
3
2
0.1
0.02
0.58
3
1.5
14.8
14.7
0.14
2.3
42.14