## Under construction
Infrastructure projects under construction (funded by CBIC grant)
S. No. | Zone | Proposal in brief | Cost of Project (Rs. in Cr.) | Present Status | Funds status | Expected date of completion
1 | Chennai Cus. | Construction of residential qtrs. at Anna Nagar, Chennai. | 348.77 | Project sanctioned on 13.10.2017. 58% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 80.00 Cr. released on 17.06.21 | Expenditure till F.Y. 2020-21 = Rs. 124.00 Cr. Fund requirement in F.Y. 2021-22 = Rs. 175.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 80.00 Cr. | 30.09.2022
2 | Delhi CGST | Construction of residential qtrs. at Dwarka | 227 | Project sanctioned on 25.07.2018. 58% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 40.00 Cr. released on 09.06.21 | Expenditure till F.Y. 2020-21 = Rs. 107.50 Cr. Fund requirement in F.Y. 2021-22 = Rs. 111.46 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 40.00 Cr. | 07.04.2022
3 | Ahmedabad Cus. | Construction of office building at Jamnagar | 43.67 | Project sanctioned on 13.12.2017. 95.50% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 8.00 Cr. released on 22.06.21 | Expenditure till F.Y. 2020-21 = Rs. 28.70 Cr. Fund requirement in F.Y. 2021-22 = Rs. 8.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 10.00 Cr. | 31.10.2021
4 | Guwahati CGST | Construction of office building (Audit Circle, Custom division & CGST Division) at Agartala | 28.04 | Proposal sanctioned on 18.02.2019. 46% work completed. File submitted to IFU for revalidation on 29.06.2021. | Expenditure till F.Y. 2020-21 = Rs. 9.00 Cr. Fund requirement in F.Y. 2021-22 = Awaited Funds provisioned in F.Y. 2021-22 = Rs. 8.00 Cr. | 01.04.2022
5 | Mumbai CGST | Construction of residential qtrs. at Kharghar by NBCC. | 110.11 | Proposal sanctioned on 18.04.2019. 32% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 25.00 Cr. released on 22.06.21 | Expenditure till F.Y. 2020-21 = Rs. 41.67 Cr. Fund requirement in F.Y. 2021-22 = Rs. 53.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 25.00 Cr. | 09.02.2022
6 | Patna Cus. | Construction of 21 nos. of staff quarters, guest House/ Multi-purpose Hall and Boundary wall at LCS, Raxaul | 11.85 | Project sanctioned on 22.09.2017. 76% work completed. File submitted to IFU for revalidation on 06.07.2021. | Expenditure till F.Y. 2020-21 = Rs. 5.80 Cr. Fund requirement in F.Y. 2021-22 = Rs. 4.66 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 6.00 Cr. | March, 2022
7 | Patna Cus. | Proposal for construction of Residential complex at Land Customs Station jogbani, | 7.99 | Project sanctioned on 11.06.2018. 49% work completed. File submitted to IFU for revalidation on 05.07.2021. | Expenditure till F.Y. 2020-21 = Rs. 2.59 Cr. Fund requirement in F.Y. 2021-22 = Rs. 3.73 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 1.00 Cr. | March, 2022 | s
8 | Jaipur CGST | Construction of office building CGST division Bhilwara. | 9.72 | Proposal sanctioned on 21.02.2019. 60% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 4.52 Cr. released on 06.07.21 | Expenditure till F.Y. 2020-21 = Rs. 3.5 Cr. Fund requirement in F.Y. 2021-22 = Rs. 6.22 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 4.52 Cr. | 31.10.2021
9 | DRI | Construction of DRI office Building at Kolkata | 64.5 | Proposal sanctioned on 08.02.2019. 25% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 10.00 Cr. released on 29.06.21 | Expenditure till F.Y. 2020-21 = Rs. 9.50 Cr. Fund requirement in F.Y. 2021-22 = Rs. 15.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 10.00 Cr. | 25.12.2022
10 | Chennai Cus. | Construction of 36 residential quarters at Nungambakkam, Chennai | 49.02 | Project sanctioned 24.12.2018. 03% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 10.00 Cr. released on 22.06.21 | Expenditure till F.Y. 2020-21 = Rs. 2.70 Cr. Fund requirement in F.Y. 2021-22 = Rs. 15.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 10.00 Cr. | 26.10.2022
11 | Mumbai CGST | Construction of 3 Div. offices and 14 ranges offices at Boisar | 33.25 | Proposal sanctioned on 01.07.19. Enabling works completed. Construction work commenced from April, 2021. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 10.00 Cr. released on 24.06.21 | Expenditure till F.Y. 2020-21 = Rs. 3.12 Cr. Fund requirement in F.Y. 2021-22 = Rs. 18.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 10.00 Cr. | 13.04.2022
12 | Mumbai Zone-I Customs | Construction of Office complex and residential quarters at Customs Enclave Plot, Wadala, Mumbai | 975.72 | Proposal Sanctioned on 11.11.2019. Comprehensive consultancy work awarded on 15.02.2021. Main Construction work is yet to start. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 10.00 Cr. released on 28.06.21 | Expenditure till F.Y. 2020-21 = Rs. 20.00 lakh Fund requirement in F.Y. 2021-22 = Rs. 70.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 10.00 Cr. | March, 2025
13 | Meerut CGST | Construction of office building including boundary wall for CGST Ghaziabad, Audit-II, Ghaziabad, Noida | 116.42 | Project sanctioned on 03.10.19. Boundary wall completed. . Main Construction work is yet to start. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 10.00 Cr. released on 21.06.21 | Expenditure till F.Y. 2020-21 = Rs. 2.53 Cr. Fund requirement in F.Y. 2021-22 = Rs. 40.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 10.00 Cr. | August, 2023
14 | NACIN | Construction of New Academy of NACIN at Palasamudram (V), (Hindupur) Ananthpur Dist., Andhra Pradesh (Construction of compound wall road along gate complexes & Consultancy work) | 17.14 | Project for construction of compound wall road along gate complexes was sanctioned on 20.11.2018. Revalidation for F.Y. 2021-22 for construction of compound wall road along gate complexes approved by IFU. Rs. 2.44 Cr. released on 02.07.21 Proposal for consultancy services work involving Rs. 2.00 Cr. sanctioned on 27.01.2021. Revalidation for F.Y. 2021-22 for consultancy services work approved by IFU. Rs. 2.00 Cr. released on 22.06.21 | Expenditure for boundary wall till F.Y. 2020-21 = Rs. 10.35 Cr. Fund requirement in F.Y. 2021-22 = Rs. 2.44 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 5.00 Cr. Expenditure for consultancy work till F.Y. 2020-21 = NA Fund requirement in F.Y. 2021-22 = Rs.2.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 5.00 Cr. | Main construction proposal awaited
15 | NACIN | Construction of office building of RTI NACIN at Attapur, Hyderabad | 46.71 | Proposal sanctioned on 30.12.2016 93.7% work completed. Revalidation request is awaited from NACIN | Expenditure till F.Y. 2020-21 = Rs. 42.85 Cr. Fund requirement in F.Y. 2021-22 = Awaited Funds provisioned in F.Y. 2021-22 = Rs. 3.50 Cr. | 30.11.2021
16 | Visakhapatnam CGST | Construction of office building at Anantapur, Andhra Pradesh. | 7.07 | Proposal sanctioned on 21.12.2018. 100% work completed. Revalidation request for an amount of Rs. 2.00 Cr. was received. Query letter regarding items included in Rs. 2.00 Cr. sent on 02.06.2021 and 25.06.2021 | Expenditure till F.Y. 2020-21 = Rs. 5.40 Cr. Fund requirement in F.Y. 2021-22 = Rs. 2.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 2.00 Cr. | Work completed. Builiding not yet occupied. Balance funds to be released after getting clarifications from field formations.
17 | Visakhapatnam CGST | Construction of 7 Nos. Type-IV Quarters and Guest House for Kurnool (Tirupati Comm’te), Andhra Pradesh | 3.95 | Proposal sanctioned on 10.09.2018. 100% work completed. Revalidation for F.Y. 2021-22 approved by IFU. File submitted to AD-VIII for issuance of Sanction order on 05.07.2021 | Expenditure till F.Y. 2020-21 = Rs. 3.02 Cr. Fund requirement in F.Y. 2021-22 = Rs. 25.00 lakh. Funds provisioned in F.Y. 2021-22 = Rs. 25.00 lakh | Work completed Balance funds to be released after getting the sanction order revalidated for the Ministry.
18 | Jaipur CGST | Construction of new office building for Udaipur CGST office at Udaipur including GH | 42.06 | Proposal sanctioned on 09.03.2020. 20% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 8.00 Cr. released on 21.06.21 | Expenditure till F.Y. 2020-21 = Rs. 60.00 lakh. Fund requirement in F.Y. 2021-22 = Rs. 15.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 8.00 Cr. | 26.02.2022
19 | Pune CGST | Construction of office building for CGST Commissionerate Kolhapur, at Tarabai Park, Kolhapur | 42.44 | Proposal sanctioned on 25.06.2020. 01% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 6.00 Cr. released on 22.06.21 | Expenditure till F.Y. 2020-21 = Rs. 10.00 lakh. Fund requirement in F.Y. 2021-22 = Rs. 10.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 6.00 Cr. | 16.10.2022
20 | Ahmedabad CGST | Construction of new building in the Custom House Compound for CGST North Commissionerate at Ahmedabad. | 31.87 | Project sanctioned on 11.06.2018. Comm'te vide status report dt. 23.11.2020 has intimated that the project is stuck pending approvals of local authorities as CPWD has not factored in the parking requirements as specified by Ahmedabad Municipal Corporation. Their alternatives are not viable as the main building is almost 5 decades old. AMC has asked the Commissionerate to come up with fresh and long term viable proposal after consulting CPWD. Letter issued on 18.02.2021 to ascertain the latest updates in this matter. Revised proposal awaited from the Commissionerate. | Expenditure till F.Y. 2020-21 = Rs. 36.00 lakh. Fund requirement in F.Y. 2021-22 = NA Funds provisioned in F.Y. 2021-22 = Rs. 50.00 lakh | Revised proposal awaited from the Commissionerate.
21 | Bengaluru CGST | Construction of office building and staff quarters for Bagalkot Range and Range D of Vijaypura Division under Belagavi CGST Comm'te | 2.19 | Project sanctioned on 10.01.2018. 100% work completed.Building has not yet been occupied. Revalidation request for F.Y. 2021-22 awaited. | Expenditure till F.Y. 2020-21 = Rs. 2.19 Cr. Fund requirement in F.Y. 2021-22 = NA Funds provisioned in F.Y. 2021-22 = NA | Construction work completed but not yet handed over by CPWD.
22 | Bengaluru Customs | Providing Barbed wire fencing and Name Boards to properties belonging to Customs Department at Karwar, for Rs. 89,56,000. | 0.89 | Project sanctioned on 15.09.2017. Out of total 39 properties, fencing work has not started in 17 properties due to disputed land title, land being claimed by salt department etc. The purpose of fencing at present is to save the land from any encroachment. Fencing work is completed in 18 properties. Revalidation request for F.Y. 2021-22 awaited. | Expenditure till F.Y. 2020-21 = Rs. 60.00 lakh Fund requirement in F.Y. 2021-22 = Awaited Funds provisioned in F.Y. 2021-22 =NA | March, 2022
23 | Chandigarh CGST | Construction of boundary wall with concertina wire fencing around the land at Solina, Srinagar for construction of office and residential buildings of Customs & CGST Division, Srinagar | 4.14 | Proposal sanctioned on 31.07.2020. File submitted to IFU for revalidation on 06.07.21 | Expenditure till F.Y. 2020-21 = NIL Fund requirement in F.Y. 2021-22 = Rs. 3.00 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 3.00 Cr. | Construction yet to start
24 | DRI | Construction of boundary wall by DRI Zonal Unit, Lucknow | 0.98 | Proposal sanctioned on 23.03.2020. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 58.00 lakh released on 22.06.21 | Expenditure till F.Y. 2020-21 = Rs. 40.00 lakh. Fund requirement in F.Y. 2021-22 = Rs. 58.00 lakh. Funds provisioned in F.Y. 2021-22 = Rs. 58.00 lakh | March, 2022
25 | NACIN | Const. of RTI NACIN Munnar, Kerala | 0.03 (Enabling works) 1.59 Cr. (For boundary wall) | Proposal for enabling works sanctioned on 08.01.2019. . Proposal for boundary wall was received in Jan, 2021 certain observation regarding accessibility to the plot made on 25.06.2021. Reply awaited. | Expenditure till F.Y. 2020-21 = Rs. 1.00 lakh Fund requirement in F.Y. 2021-22 = NA Funds provisioned in F.Y. 2021-22 = NA | March, 2022
26 | Pune CGST | Construction of office building and 02 nos. residential quarters for CGST Ranges office at Pandharpur, Distt. Solapur, Maharashtra. | 2.05 | Proposal sanctioned on 03.09.2020 20% work completed. Revalidation for F.Y. 2021-22 approved by IFU. File submitted to AD-VIII for issuance of Sanction order on 05.07.2021 | Expenditure till F.Y. 2020-21 = Rs. 51.00 lakh Fund requirement in F.Y. 2021-22 = Rs. 1.5 Cr. Funds provisioned in F.Y. 2021-22 = Rs. 1.5 Cr. | 31.03.2022
27 | Trichy Customs | Construction of additional residential quarters (T-II, T-III & T-IV) at Port Area, Tuticorin. Total qtrs.- 06 Type wise qtrs.- Type-II=1 Type-III=2 Type-IV =3 | 1.62 | Project sanctioned on 25.08.2017. Two Type-III qtrs & one Type-II qtr are completed. Three Type-IV are yet to be completed as reported by the Comm'te on 20.11.2020. Revalidation request awaited from the Commissionerate. | Expenditure till F.Y. 2020-21 = Rs. 1.11 Cr Fund requirement in F.Y. 2021-22 = Awaited Funds provisioned in F.Y. 2021-22 = NA | March, 2022
28 | Hyderabad CGST | Construction of compound wall & office building at Mamidipally, Near Shamshabad Airport, Hyderabad. | 1.3 | Project sanctioned 07.03.2019. 30% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 00.60 Cr. released on 28.06.21 | Expenditure till F.Y. 2020-21 = Rs. 32.00 lakh Fund requirement in F.Y. 2021-22 = Rs. 60.00 lakh. Funds provisioned in F.Y. 2021-22 = Rs. 60.00 lakh | March, 2022
29 | Ahmedabad Customs | Construction of office building at the site of shore guard, Dwarka, Jamnagar. | 1.24 | Proposal sanctioned on 04.03.2020. Commencement of construction 04.09.2020. 90% work completed. Revalidation for F.Y. 2021-22 approved by IFU. Rs. 50.00 lakh released on 09.06.2021. | Expenditure till F.Y. 2020-21 = Rs. 40.00 lakh. Fund requirement in F.Y. 2021-22 = Rs. 50.00 lakh Funds provisioned in F.Y. 2021-22 = Rs. 50.00 lakh | 31.10.2021
Infrastructure projects under construction (funded by MoHUA grant)
30 | Bengaluru CGST | Construction of office building & guest house for Central Excise Division Office at Udupi (Mangalore Commissionerate) | 4.58 | Project was sanctioned on 04.03.2016. | 80% work completed
31 | Chandigarh CGST | Construction of office cum residential qtrs.and boundary wall at Jalandhar for CGST Jalandhar Commissionerate Total land - 06 acre Total qtrs.- 116 Type wise qtrs.- Type-II=19 Type-III=62 Type-IV =32 Type-V A=01 Type-V B=01 Type-VI=01 | 67.57 | Project was sanctioned on 4.8.2017 | Approx.Rs. 5.74 Cr have been utilized
32 | Panchkula CGST | Construction of office building in Sector-3, Rohtak for Central Excise Commissionerate, Rohtak. | 34.47 | Project sanctioned on 20.10.2015 Construction started in March 2019. Comm'te vide letter dt. 19.11.2020 has intimated that progress of the project is slow due to paucity of funds and they have already been taken up with the ADG (CPWD) Chandigarh to release of funds for the Project. | Approx.Rs. 5.43 Cr have been utilized and 35% work has been completed.
33 | Patna Cus. (Prve.) | Construction of office building for Customs & Central Excise at Vibhuti Khand, Gomti Nagar, Lucknow | 88.74 | Project sanctioned on 19.01.2015. Matter regarding shortage of funds has been taken up with CPWD. Further, a revised proposal enhancing the project cost to Rs. 150.59 Cr. which was further reduced to Rs. 122.25 Cr. Justification for the revised proposal has been sought vide letter dated 20.02.2020 followed by reminders dated 28.08.2020 13.01.2021, 25.02.2021 and 25.06.2021. Reply awaited. | Approx.Rs. 65.05 Cr have already been utilized and 68% work has been completed.