## IFU-Ministry
Infrastructure projects under consideration with IFU / Ministry (funded by CBIC grant)
S. No. | Zone | Proposal in brief | Cost of Project (Rs. in Cr.) | Present Status
1 | Ahmedabad CGST | Construction of office premises on land measuring 3972.22 sqm. of final plot No. 175 of TP No. 3 of the commissioner of CGST (Audit), Ahemedabad. | 75 | IFU vide note dated 27.05.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. File submitted to IFU on 15.04.2021 for reconsideration. Presently, file is with IFU.
2 | Ahmedabad Cus. | Construction of Staff quarters at Jamnagar | 18.86 | Proposal received on 09.09.19. After satisfying various rounds of IFU observations, file has been again submitted to IFU for consideration on 22.03.2021.Presently, file is with IFU.
3 | Chennai Cus. | Construction of office accomodation building for Chennai Customs Audit and Import Comm'te and Partner Govt. Agencies at Jaffer Syarang Street, Chennai. | 86.75 | Proposal was received in July, 2019. After satisfying various rounds of IFU observations, file has been again submitted to IFU for consideration on 02.06.2021.Presently, file is with IFU.
4 | Delhi CGST | Construction of office building at Nangal Raya, New Delhi. | 32.83 | Proposal sanctioned on 13.06.2016. Complete amount has been released to the Comm'te. Comm'te vide letter dt. 06.02.2019 has intimated that civil work is completed. Proposal amounting to Rs. 3.97 Cr. for providing new load of 1408KW submitted to IFU on 07.04.2021. After concurrence from IFU, approval of Revenue Secretary has been obtained. File submitted to AD-VIII for issuance of Sanction order on 06.07.21
5 | DRI | Construction of office building of DRI Zonal Unit at Trustpuram Kodambakkam, Chennai | 31.38 | Proposal sanctioned on 29.06.2021. Funds are being released.
6 | DRI | Construction of DRI Lucknow Zonal Unit office at Plot No. 07/13-B-2, Gomti Nagar Extension, Lucknow - reg. | 35.22 | Proposal received on 16.12.2020. File submtted to IFU for approval on 31.05.2021. Presently, file is with IFU.
7 | DRI Delhi | Construction of office building for DRI (HQ.) at Vasant Kunj, Delhi | 77.86 | Proposal received on 23.03.2020. After various rounds of observations, file re-submitted to IFU on consideration in December, 2020. Presently, file is with IFU.
8 | Lucknow CGST | Construction of boundary wall for office building and staff quarters at Raibareli. | 0.29 | IFU has approved the proposal. Commitment is being ought from EMC and thereafter file will be submitted to AD-VIII for issuance of sanction order.
9 | Mumbai-II Cus. | Construction of additional office building (G+7) (To provide more space to officers of Mumbai Zone-II) at JNCH NHAVA SHEVA Dist. Raigad-Mumbai Available area - 14900 sqm. Office space - 8551.80 sqm. | 80.61 | Proposal for enabling works (Rs 51 Lakh) was sanctioned in March, 2018. Proposal for office sanctioned on 14.02.2019 for an amount of Rs. 90.26 Cr. In February, 2021, a revised proposal with cost of Rs. 80.60 Cr. was received due to change in the foundation plan. IFU has made certain observations which have been convyed to the Commissionerate on 05.07.21
10 | Visakhapatnam CGST | Construction of office building at Eluru (A.P.) | 6.95 | File was submitted to Min. for approval on 14.01.2020. In F.Y. 2020-21 IFU advised to drop the proposal in view of low strength and less rental outgo. File submitted to IFU for reconsideration on 23.04.2021.
11 | DRI | Construction of office building for DRI Hyderabad Zonal Unit at Jubilee Hills at Hyderabad | 24.14 | Proposal received in March, 2021. File submtted to IFU for approval on 11.06.2021. Presently, file is with IFU.
Infrastructure projects under consideration with IFU / Ministry (funded by MoUHA grant)
12 | Ahmedabad CGST | Construction of office building for CGST Commissionerate and Customs Division at Bhavnagar Total land- 7104 sqm. Office space-4807.50 sqm. | 40.61 | Project sanctioned on 30.08.2017. But due to change in PAR 2019, a revised proposal was forwarded by the Comm'te, which was submitted to the Min. for a/a & e/s for the increased amount on 26.02.2020. Financial Advisor upon consultation with Revenue Secretary has advised on 16.04.2020 to keep the proposal in abeyance for the time being. File is under submission to Revenue Secretary for reconsideration.