## DGHRD field formations
Infrastructure projects under consideration with DGHRD/field formations
S. No. | Zone | Proposal in brief | Cost of Project (Rs. in Cr.) | Present Status
1 | Visakhapatnam CGST | Construction of office building and staff quarters at Tirupati | 57.06 | Earlier, Revenue Secretary on 22.06.2017 made observations regarding PPP Model, Cost benefit analysis etc. Comm'te withdrew the proposal. Revised proposal was submitted to the Ministry and Revenue Secretary upon discussing the proposal with FA has disagreed the proposal on 20.02.2020. The same were conveyed to the Comm'te on 16.03.2020. Tirupati Comm'te vide letter dated July, 2020 stated that to protect the land from encroachment & to prevent the taking back the land by the State Govt., there is urgent need of const. of boundary wall. Accordingly, letter sent to Comm'te on 06.07.2020 requesting to submit seprate PE for boundary wall at the earliest. Reminder sent on 29.06.2021. Response awaited.
2 | Bengaluru CGST | Construction of office building and staff quarters at Belgaum (Gulbarga Division)-reg. Office space: 191.16 sqm. Total Quarters =04 Type II=01 Type III=02 Type IV= 01 | 3.36 | Revised proposal received on 28.01.2019. IFU vide note dated 22.05.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the F.Y. 2020-21 due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to Comm'te on 03.06.2020. Response from Commissionerate awaited.
3 | NACIN | Const. of NACIN Complex at Nolambur, Chennai-reg. | 79.8 | File was submitted to the Ministry for approval on 04.03.2020. IFU vide note dated 06.05.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. Further, it has advised to utilize the existing NACIN/RTI premises for training purposes. IFU obeservation communicated on 26.05.2020. Reminder sent on 29.06.2021. Response awaited
4 | Nagpur CGST | Const. of 6 nos. of T-VI qtrs.for Central Excise at B.No. 12, Seminary Hills, Nagpur Internal Water Supply, Sanitary Installation, Drainage and Internal Electrical Works involving an expenditure of Rs. 734.63 lakhs. | 7.35 | Proposal received and submitted to the Min. on 15.07.19 for approval. IFU vide note dated 23.06.2020 has returned the file advising not to take up the construction, keeping in view the need to regulate/minimize the expenditure in the current F.Y. due to COVID -19 situation and cash position of the Central Govt. The same has been communicated to CC Nagpur letter dated 06.07.2020. Response from Commissionerate awaited.
5 | Visakhapatnam CGST | Construction of Nellore CGST Comm'te Divisions for CGST, Audit Circle and SGCP Unit at Nellore | 0.96 | Proposal for const. of boundary wall received in May, 2020. In view of the Financial constraints due to COVID 19, Comm'te advised to submit a consolidated proposal for const. of building and boundary wall on 03.06.2020. Response awaited.
6 | Bengaluru Cus | Construction of new customs House Building at bengaluru International Airport | 57.37 | Fresh proposal was received in October, 2019 IFU has made certain observations regarding space calculation, cost of const., cost benefit analysis etc. and advised not to take up the proposal in F.Y. 2020-21 due to financial constraints because of COVID-19. Communicated to the Commissionerate on 02.10.2020. Reminder sent on 30.06.2021. Response awaited.
7 | Visakhapatnam CGST | Const. of buildings for newly formed Customs Comm'te (P.), Vijaywada-HQRS. Office Complex and Residential Quarters at Sy. No. 29/8 (3.84 acres) of Kesarpally Village of Gannavaram Mandal of Krishna Dist. Andhra Pradesh | 65.49 | Revised proposal received on 01.03.2019, proposing to award this work to NBCC the proposal was submitted to Min. for a/a & e/s. While perusing Member (Admn.) returned the file and asked to Comm'te to get in writing a letter from CPWD showing their inability before awarding this work to NBCC. Comm'te vide letter dated 09.12.2020 has intimated that they have taken up the matter with CPWD /Commissionerate for PE & drawings, reply from CPWD is awaited. Reminder sent on 29.06.2021.
8 | Bhubaneshwar CGST | Const. of Retaining wall and Approach Road and from the main road to the office plot at Bagbrindaban Mauja of Balasore Town in state of Odisha. | 1.57 | IFU made certain observations reg.ofice space, approach road etc. in December 2019. Communicated to Comm'te on 14.02.2020. Reminders sent on 11.06.2020, 13.07.2020 & 02.12.2020. Response awaited
9 | Guwahati CGST | Construction of office cum residential qtrs. at Dibrugarh. Total office space: 3562 sqm. Total quarters: 56 (Type-II 14, Type-III 28 & Type-IV 14) | 60.37 | The proposal was submitted to the Ministry on 21.05.2018. IFU had made some observations regarding budget head, cost index, carpet area and the same were conveyed to Comm'te on 12.09.19. Incomplete reply received, Comm'te vide letter dated 14.01.2020 was again requested to submit a proper reply. Reminders sent on 16.07.2020, 04.12.2020, 23.02.2021 & 01.07.2021. Response awaited.
10 | Guwahati CGST | Const. of office building and boundary wall at Lamphel at Imphal Shillong | 46.4 | Proposal was received on 16.09.2019. IFU made observations reg. revenue collection,cost benefit analysis, built up area, per sq.ft. cost of const. communicated to the Comm'te on 05.03.2020. Incomplete reply was received in May 2021. Letter sent to Commissionerate on 13.05.2021 to submit a comprehensive reply. Response awaited.
11 | Jaipur CGST | Proposal for repair/renovation and upgradation of staff houses at Udaipur. | 2.60 | Fresh proposal was received on 08.04.2019 IFU in March, 2021 made observations regarding revised PE, area per quarter etc. Same communicated to the Commissionerate on 22.03.2021. Response awaited
12 | Lucknow CGST | Const. of new office building for CGST Division at Aligarh. | 11.34 | File submitted to the Ministry on 20.02.2020 and observations reg. space calculation etc. made by IFU were communicated to comm'te on 11.05.2020. Last reminder sent on 12.11.2020. Response awaited
13 | Pune CGST | Redevelopment of 52 nos. of staff quarters and community centre for CGST Goa Commissionerate, Goa at Alto-porvorim | 26.86 | File was submitted to the Min. on 08.01.2020. File receievd back from IFU with certain observations reg. GRIHA norms, cost of const. of per flat, cost index etc., which were conveyed to the Comm'te on 28.02.2020. Reminders sent on 21.09.2020, 27.11.2020 & 30.06.2021. Response awaited.
14 | Guwahati CGST | Construction of combined office cum residential projects for CGST Shillong, Customs (NER) Shillong, CGST Audit Comm'te and NACIN Shillong | 258.96 | Proposal received in Dec, 2019. Certain observations reg. check list, hostel space, commercial space, demand survey etc. communicated to the Comm'te on 26.12.2019. Last reminder sent on 01.07.2021. Response awaited.
15 | Jaipur CGST | Comprehensive Consultancy Services for Master Planning of Campus & Design of Office cum Residential Campus for CGST at Jodhpur | 1.11 | Proposal for Master planning has been sanctioned on 25.09.2019. Comm'te vide letter dated 27.07.2020 has stated that revalidation/funds is not required for the project for F.Y. 2020-21, till MoU is signed with Income Tax. Present status awaited from Commissionerate.
16 | Meerut CGST | Construction of boundary wall around office cum residential plot to CGST Division, Hapur | 0.89 | Proposal received 31.01.2020, upon scrutiny DGHRD queries reg. consolidated proposal, existing qtrs. etc. have been communicated to Comm'te. Last reminder letter dated 03.12.2020. Response awaited.
17 | Mumbai CGST | Construction of compound wall for Customs ( M&P) department at Satpati, District Palghar | 0.38 | Proposal received on 29.07.2020. Observations regarding check list, main const. proposal etc. communicated to the Comm'te on 11.08.2020. Incomplete reply received on 12.04.2021, queries raised by DGHRD, letter sent on 22.06.2021. Response awaited.
18 | Mumbai -I Customs | Construction of Customs Guest House building (GF+6 storeys) for Customs Department at Reti Bunder Mahim Mumbai | 5 | Proposal received 27.11.2019, upon scrutiny DGHRD queries has been communicated to Comm'te. Last reminder letter dated 11.12.2020.Response awaited. | 56
19 | Nagpur CGST | Construction of office building (G+3) storey and 2 qtrs Ahmednagar, Aurangabad Comm’te. Land area: 2310.84 sqm. Office space : 1672 sqm. Total qtrs.: 02 (Type IV-Spl) | 12.21 | Incomplete proposal was received therefore Commissionerate was requested to submit a comprehensive proposal with revenue collection, space calculation, check list, etc. Reply received and queries raiased by DGHRD reg. demand survey, calculation of space etc., communicated to Comm'te on 14.02.2020. Reminders sent on 03.12.2020 & 01.07.2021.
20 | Ranchi CGST | Proposal for (i) Topographical Survey & Soil Investigation and (ii) Construction of boundary wall, main gate & guard room at HEC area, Nagri, Ranchi | 2.45 | The proposal for (i) Topographical Survey & Soil Investigation (Rs. 91,200/-) and (ii) Construction of boundary wall, main gate & guard room (Rs. 1,54,63,000/-) at HEC area, Nagri, Ranchi received in Jan, 2021 has been processed and observations regarding CC recommendation and possession of land communicated on 03.03.2021. Repy awaited
21 | Vadodara CGST | Demolition of old residential quarters (04 nos. T-IV and 08 nos. T-I) in Central Excise Custom Colony situated at Vapi. | 2.94 | Similar proposal was received for const. of 14 residential qtrs. at Kachigham accordingly, the Comm'te vide letter dt. 20.01.2020 requested to forward a consolidated proposal for both the projects. Query letter regarding check list, demand survey sent on 09.03.2021
22 | Vadodara CGST | Construction of 08 nos. T-IV, 05 nos. T-V & 01 No. T-VI residential quarters at R.S. No. 193/A, Kachhigam, Vapi | 10.22 | Similar proposal was received for demolishing of old qtrs. and re-const. of 06 T-IV qtrs. at Customs Colony at Vapi accordingly, the Comm'te vide letter dt. 20.01.2020 requested to forward a consolidated proposal for both the projects. After clarification query letter regarding check list, demand survey sent on 09.03.2021
23 | Visakhapatnam CGST | construction of office building and staff quarters for CGST Division and ranges at Kadapa | 18.47 | Tirupati Comm'te vide letter dated July, 2020 stated that to protect the land from encrochment & returning of land to State Govt. urgent need of const. of boundary wall is felt. Letter sent to Comm'te on 06.07.2020 requesting to submit separate PE for boundary wall at the earliest. Further certain deficiencies in the construction proposal have also been communicated to the Comm'te on 16.07.2020. Reminders issued on 07.12.2020 & 01.07.2021. Response awaited.
24 | Kolkata CGST | Construction of office building & Guest House for Customs & CGST at Behrampore, Bolpur Commissionerate, Kolkata. | 17.62 | Proposal received in September, 2020. On scrutiny of the proposal, observations regarding check list etc. communicated to the Comm'te on 11.11.2020. Last remiders sent on 15.01.2021 & 30.06.2021. Response awaited.
25 | Nagpur CGST | Construction of office buiding and 19 residential quarters at Nanded | 18.51 | The initial proposal for Rs. 11.50 cr. was sanctioned by the Min. on 08.05.2015 but the Comm'te vide letter dt. 26.07.19 has sought approval for increased amount of Rs. 18.51 Cr. After various rounds of observations still comprehesnive reply is awaited regarding number of quarters and validity of PE. Communicated to the Commissionerte on 19.03.2021. Reminder sent on 30.06.2021. Response awaited.
26 | Hyderabad CGST | Completion of 287 unfinished Dept. qtrs taken over from M/s Sri Durga Estate Pvt. Ltd. at Hyderabad | 49.75 | Proposal for enabling works (Rs. 8.50 lakhs) sanctioned on 12.09.2018. Comm'te vide letter dt. 01.12.2020 has submitted only Preliminary Estimate of Rs. 65,27,60,633/- prepared by NBCC for construction of office cum resdential. Comm'te vide letter dt.17.12.2020 has requested to submit consolidated proposal with justification for selecting NBCC. Response awaited.
27 | Thiruvanthapuram CGST | Construction of residential qtrs. at Chilavanoor, Cochin Total land - 16762.80 sqm. Total qtrs-228 Type-III =118 Type-IV = 102 Type-V = 7 Type-VII = 01 | 106.59 | Initial proposal for const. of 228 qtrs.was sanctioned Jan, 17. Due to change in plinth area norms CPWD has recommended to revise the proposal. Inspite of repeated reminders revised proposal is still awaited. A D.O. letter from Pr. DG,HRD issued on 29.01.2020 requesting the Comm'te to revisit the proposal and forward the same at the earliest. Last reminder sent on 29.06.2021.
28 | Patna Cus. (P.) | Construction of LCS Building residential quarters and allied facilities at LCS, Bhimnagar |  | Land was purchased in March, 2018. Letter sent for forwarding construction proposal. Response awaited.
29 | Jaipur CGST | Const. of office building, 06 nos. residential quarters & GH for CGST division at Chittorgarh. Total qtrs. -06 | 12.28 | Proposal received on 12.11.2018. Letter written to Comm'te on 19.03.20 seeking further calrification on land use. Comm'te vide letter dated 14.08.2020 has stated that the project may be kept on hold till the conversion land is finalized by State Govt. Authorities
30 | Jaipur CGST | Construction of Office Building of CGST Comm’te Alwar (including 2 Divisions & 01 Audit Circle, Alwar),residential quarters and GH for CGST Commissionerate at Alwar (Raj.) | 34 | Proposal received 04.02.2020, certain queries raised by DGHRD reg. calculation chart, immovable assets, cost of const. of GH etc. and communicated to the Comm'te on 24.02.2020. An incomplete reply has been received, letter sent on 16.07.2020 for clarifications.Comm'te vide letter dated 25.08.2020 has stated that the project may be kept on hold till the conversion land is finalized by State Govt. Authorities.